## Slide 1
Radiation Detector & Imaging (RD&I) Group
Cameron Clarke, BRIC Staff Scientist
Standard Phototube
Position sensitive phototube
SiPM array
Standard Phototube
Position sensitive phototube
SiPM array
Standard Phototube
Position sensitive phototube
SiPM array
Standard Phototube
Position sensitive phototube
SiPM array
Streaming Readout PET
LDRD Q1 Report – January 21, 2026

## Slide 2: Q1 Accomplished Goals
A) Detector prototype development
  Front end boards in hand and scalers tested
  3D printed housings, cooling, and assembly
  Synch distribution board received, in progress
B) SRO data processing system development
  Successfully factorized analysis into ERSAP
  Multi-node horizontal parallelization added
  Delayed synch distribution board procurement has delayed Q1 SRO system integration step
C) Broader scope project work
  2nd provisional patent filed, IEEE RT Abstract
  Contract P.R. placed with UMAB PET facility
  Trained to use NERSC Spin and Perlmutter
ISP Challenge: EPSCI's Mike Goodrich Solution: NERSC support and re-allocate FTE as AmSC settles
2
Updated streaming architecture for multi-node horizontal scaling
FY 2025 Starting Points
Front-end boards in-hand and testing underway
FY 26 Q1 Implementation Progress
SD Board in-hand and firmware on-track

## Slide 3: Spending
Spending is generally on target – electronics finalized, software on track, UMAB contract P.R. placed
  Labor: Spent ~$24k on labor
  Equipment: Spent ~$12k on signal/synchronization distribution board procurement delayed from last year
  Travel: Cancelled IEEE meeting attendance, retracted 2 papers, due to government shutdown chaos
3

## Slide 4: Backups
4

## Slide 5: Deliverables
Deliverables – milestones and timeline:
Three primary aims
  Implement ERSAP to existing SRO PET detectors, DAQ, and analysis system in FY 25
  Design and build improved version of modular PETIROC ASIC PET detectors in FY 25
  Deploy detector array, perform imaging and parallelized scaling tests with distributed computing in FY 26
Year 1 |  |  | Year 2 |  | 
1) | Implement ERSAP in FY 25: (✔) Implement FPGA based PETIROC signal digitization (✔) Factorize analysis components into ERSAP microservices (✔) Reproduce old system performance with ERSAP system (✔) Vertical multi-threaded, horizontal multi-node scaling | FY 2025: Month 3 Month 6 Month 9 Month 12 | 3) | Deploy detector array, imaging and parallelized scaling tests in FY 26: (✔) Procure and test new detector front-ends (O ) Integrate modular 8-detector array with new SRO system Verify detector and imaging performance for new system Deploy the system and perform phantom imaging tests at UMAB NERSC streaming with JIRIAF control plane Finalize reports on local and farm streaming scalability tests | FY 2026: Month 3 Month 3 Month 6 Month 6 Month 9 Month 12
2) | Design and build modular PETIROC ASIC PET detectors in FY 25: (✔) Optimize FPGA multi-detector readout firmware (✔) Optimize detector power supply and readout cabling (✔) Design and order new PETIROC modular detector PCBs (✔) Get electronics parts, build, and test 8 new detectors | FY 2025: Month 3 Month 3 Month 6 Month 12 |  |  | 
5

## Slide 6: Detector Prototype Development
Designed concept for v2.0 front end layout
  Modular detector design
  Aiming for 4-side buttable
  SiPM and scintillator separated
  Flex cable permits multiple orientations
  & permits thermal and optical isolation
  USB-C connector simplifies connections
  Communication board (not shown) synchronizes and powers all detectors
6
2x PETIROC ASICs
(64 channels)
Artix Ultrascale+
AU15P FPGA
USB-C
(power & communication)
~25.8mm
~25.8mm
>75mm
<125mm

## Slide 7: SRO Platform Development
Explored SRO analysis architecture options
  Event-based processing from FPGA
  Time-windowing at singles or geometry processor
  Potential for time- windowing in the FPGA
  Updated diagram for one potential architecture
    All time-interleaving in a single actor option
Finalized ERSAP-based software development
  Completed GitLab CD/CI implementation
  Finished converting KMax singles and geometry processors into ERSAP actors
7

## Slide 8: Summary
We are on track to meeting deliverable goals
  SRO platform development is proven, under iterative refinement
  Detector front-end design work is underway, finishing up the details now
  Sub-contracted imaging studies are on track for FY26
  Talks at conferences are being planed
8