## Slide 1: Click to add title
Click to add subtitle
Allison Lung
S & T Review
July 28-30, 2015
12 GeV Upgrade Project - Status

## Slide 2: OUTLINE

## Slide 3: Project Description
TEC = $310.5M
OPC = $ 27.5M
TPC = $338M
Upgrade max e- energy of accelerator from 6 to 12 GeV (11 GeV for existing Halls A, B and C)
Construct new experimental area (Hall D Complex)
Fabricate new spectrometers for Halls B, C and D
Enhance the capabilities of existing Hall A experimental area
Double the cryogenic capacity
Infrastructure [i.e., CHL Bldg., upgrade the LCW and electrical distribution systems]
We are here

## Slide 4: 12 GeV Scientific Capabilities
Hall D – exploring origin of confinement by studying exotic mesons
Hall B – understanding nucleon structure via generalized parton distributions
Hall C – precision determination of valence quark properties in nucleons/nuclei
Hall A – form factors, future new experiments (e.g., SoLID and MOLLER)
Notes: 4
Note BSM not included in project

## Slide 5: 12 GeV Upgrade Project: Schedule
    16-month installation:
    May 2012 - Sept 2013
    Accelerator commissioning:
    Oct 2013 – May 2014
    Hall A commissioning:
    Feb 2014
    Hall D commissioning:
    Oct – Dec 2014
    Hall C commissioning start: September 2016
    Hall B commissioning start: December 2016
    Project Completion: September 2017

## Slide 6: Civil Construction: 99% Complete
New Construction ~10,080 sq ft
Add to Existing Buildings ~8,400 sq ft
Expansion of existing utilities
One FY15 task remains: Tunnel AC
CHL Building Addition
Hall D Complex
North Access Building Addition
Chiller at East Arc

## Slide 7: Accelerator Construction: 100% Complete
September 2014
N. Linac
Cryomodules
RF - Klystrons
Coldbox
Arc 10
Recombiner
Extraction
Acceleration:
  10 new cryomodules; 8 cavities each
  high-performance, quadruple the gradient
  each cavity has dedicated m-wave source
  duplicate existing cryogenics plant
BEAM TRANSPORT | Existing Upgrade/Replace | Arc 10 New
Dipoles | 357 | 32
Quads | 730 | 40
Power Supplies | > 2000 | 81
Diagnostics | > 700 | 32
Vacuum Line | > 5 km | 0.3 km

## Slide 8: CD-4A Key Performance Parameters
# | System | Technical Definition | PEP Date | ACTUAL
1 | Accelerator | 12 GeV capable 5.5 pass machine installed | Dec 2014 | June 2014
2 | Accelerator | 11 GeV capable beamline to Halls A/B/C installed | Dec 2014 | June 2014
3 | Accelerator | 12 GeV capable beamline to Hall D tagger area installed | Dec 2014 | April 2014
4 | Accelerator | Accelerator commissioned by transporting a > 2 nA electron beam at 2.2 GeV (1 pass) | Dec 2014 | Feb 2014
5 | Civil | New experimental Hall and Counting House: > 10,500 sq. ft. | Dec 2014 | June 2012
See A. Freyberger’s talk

## Slide 9: CD-4 Requirements
Received CD-4A Approval ahead of schedule; ESAAB July 30, 2014
‘Accelerator Project Complete and Start of Operations’
Prior to CD-4 | Timing |  | CD-4A | CD-4B
Verify that Key Performance Parameters and have been met. | CD-4A & CD-4B |  |  | 
Issue a Project Transition to Operations Plan | CD-4A & CD-4B |  |  | 
Conduct a formal assessment of the project's Readiness to Operate. | CD-4A & CD-4B |  |  | 
Finalize the Hazard Analysis Report. | CD-4A |  |  | 
Revise Environmental Management System, as appropriate. | CD-4B |  | NA | 
Post CD-4 | Timing |  | CD-4A | CD-4B
Submit all CD documents to APM. | CD-4A & CD-4B |  |  | 
Finalize PARS II reporting. | CD-4B |  | NA | 
Within 90 days, submit Lessons Learned to PSO and APM. | CD-4A & CD-4B |  |  | 
Within 90 days, submit Initial Project Closeout Report | CD-4B |  | NA | 

## Slide 10: CD-4B Key Performance Parameters
# | System | Technical Definition | PEP Date
6 | Hall B | Detector operational: events recorded with a > 2 nA electron beam at > 6 GeV beam energy (3 pass) | Sep 2017
7 | Hall C | Detector operational: events recorded with a > 2 nA electron beam at > 6 GeV beam energy (3 pass) | Sep 2017
8 | Hall D | Detector operational: events recorded with a > 2 nA electron beam at > 10 GeV beam energy (5.5 pass) | Sep 2017
Hall D: GlueX Spectrometer

## Slide 11: Hall D: Complete / Installed
TOF (FSU)
BCAL (UR)
FCAL (IU)
START (FIU)
FDC inside BCAL bore
CDC (CMU)

## Slide 12: Hall D – Key Performance Parameter
KPP achieved – December 2014
Thanks to dedicated effort by Accelerator Ops, Engineering, Hall D staff, and GlueX Collaboration
Target (1cm plastic) location
Z,cm
2-day running period: 50-100nA, 10.08 GeV electrons
See A. Freyberger’s talk
See J. Stevens’ talk
    Commissioning run: 3 weeks in Oct-Dec 2014
Hall D Tagger

## Slide 13: Technical Highlights (1)
Hall D : Silicon Photomultipliers (SiPMs)
What: Avalanche photodiode pixels operating in Geiger mode
Why: immune to strong field; good PDE; compact; no HV needed
Application: GlueX experiment & Bio-imaging
Hamamatsu
4×4 Array of
3×3 mm2 SiPMs
50 mm
Accelerator: C100 Cryomodules
Evolved from CEBAF C20 design & C50 program (reduce field emission & raise gradient)
Requirement 98 MeV, designed for 108 MeV
Experience being leveraged for FRIB and LCLS-II
C100 Cryomodule Energy Gain
Beam Current/pass (mA)
– 150
ENERGY GAIN (MeV)
– 50
– 100
– 200
98 MeV
108 MeV
Array of 80 SiPMs
(See D. Weisenberger’s talk)

## Slide 14: Halls B & C: Estimate-To-Complete
Hall C
$5.3M
Hall B
$9.1M
Chart: 
| 1.4.2.2 Detectors | 1.4.2.3 Computing | 1.4.2.4 Electronics | 1.4.2.5 Beamline | 1.4.2.6 Infrastructure | 1.4.2.7 Torus/Solenoid Magnets | 1.8.2.2 Hall B Pre-Ops Total
 | 0.38097 | 0.38555 | 0.18784 | 0.29818 | 1.6868 | 4.818 | 1.3656
Chart: 
| 1.4.3.1 Magnet | 1.4.3.2 Detector | 1.4.3.3 Computing | 1.4.3.4 Electronics | 1.4.3.5 Beamline | 1.4.3.6 Infrastructure | 1.8.2.3 Hall C Pre-Ops Total
 | 3426.515 | 36.808 | 0 | 0 | 280.165 | 1108.369 | 481.527

## Slide 15: Hall C: SHMS
Dipole
Q3
Q2
Q1
HB
Magnet Power Supplies
Cryogenics Distribution
Concrete Detector Shield House
Pivot
Heavy Gas Cerenkov
Noble-Gas Cerenkov
Drift Chambers
Shower Counter
S2 Hodoscope
S1 Hodoscope
PreShower Counter
Particle Detectors

## Slide 16: Hall C: Detector Progress
Quartz Hodoscope
(NCA&T)
Complete
Shower Counters
(ANSL/Nikhef)
Complete
Drift Chambers
(HU)
Complete
PreShower Counters
Complete
6 of 7 Complete;
3 Installed
NGC (UVa)
HGC Cerenkov
(UR)
Complete
Complete
Scintillator Hodoscopes
(JMU)
Funded through NSF-MRI:
Scintillator; Quartz;
Drift Chambers; Mount

## Slide 17: Hall C: SHMS Magnets
Dipole Collaring
(Sigma Phi, France)
Q2 splicing
(Sigma Phi, France)
Q3 coil assembly
(Sigma Phi, France)
Q1 (SMI, UK)
Installed on carriage
Cooled down
Power test to 110% of operational current
Acceptance tests complete
HB (MSU/FRIB)
Installed on carriage
Cooled down
Initial power test to 10% of operational current
ERR - one open issue
HB
Q1

## Slide 18: CLAS12 Schematic
Project equipment
Forward Detector (FD)
  - TORUS magnet (6 coils)
  HT Cherenkov Counter
  Drift Chamber system
  LT Cherenkov Counter
  Forward ToF system
  Pre-shower Calorimeter
  E.M. Calorimeter
Central Detector (CD)
  SOLENOID magnet
  Silicon Vertex Tracker
  Central ToF system
Notes: To meet the physics requirements of high statistics measurements for exclusive processes, the equipment underwent major upgrades. CLAS12 has two major parts to its base equipment with different functions, the Forward Detector (FD) and the Central Detector (CD). The FD covers polar angle range of 5◦ to 35◦ and the CD from about 35◦ to 125◦.
The TORUS has six superconducting coils symmetrically arranged around the beam line, and provides six sectors for charged particle detection. Each sector has its own tracking and particle identification detectors. Tracking is accomplished with a set of 3 regions of drift chambers with 12 layers of hexagonal drift cells arranged in a pattern optimized to provide measurements for pattern recognition and subsequently track reconstruction; then PID (K/p separation up to 4.5 GeV) is obtained using the time-of-flight system from beta measurements. For improved PID, measurements from 2 Cherenkovs are employed: a high threshold counter for e-/pi separation and a low threshold counter for K/pi separation. Neutral reconstruction done using the calorimeters; physics program require the identification of single high energy photons and separation from π0 → γγ up to 9 GeV achieved by adding a preshower calorimeter (PCAL) in from of the electromagnetic calorimeter. For tracks produced at angles larger than 35◦ tracking is done using the Silicon Vertex tracker (up to 4 space points) and PID from beta measurement obtained from C. Time of Flight scintillator barrel. Several upgrades including the micromega detectors are aimed at improving tracking resolutions; the RICH with improve charged particle ID, the CND give neutron ID. A quasi-real photon forward tagging system (FT) will measure electrons at scattering angles from 2◦ - 4◦ .

## Slide 19: Hall B: Detector Progress
FTOF 1-a, 1-b Installed (USC)
Drift Chambers
(ODU, ISU, JLab)
PCAL Installed
(OU)
Complete
Complete
Complete
LTCC
SVT Region 4
CTOF Counters
HTCC Mirror in Vessel
3 of 7 Complete;
2 Installed

## Slide 20: Hall B: CLAS12 Magnets
Coil LN2 Test @ JLab
Schematic @ ETI (PA)
Solenoid
Torus
Trial fit 1st coil on hub
1 (of 2) Inner coils
Conductor for intermediate coil
All 6 coils
installed
Inner
Intermediate
Shield
He channel
C1-4 bobbin

## Slide 21: Technical Highlights (2)
Hall B: Silicon Vertex Tracker
Track low p particles with few % angular resolution at high L
New technology to JLab, strong collaboration with FNAL
Good S/N achieved
Leverage for HPS
 | Hall B |  | Hall C |  |  |  | 
 | Torus | Solenoid | HB | Q1 | Q2 | Q3 | Dipole
Type | 6-fold | Self Shielding | “C”, Septum | Cold Iron | Cos 2Θ | Cos 2Θ | Cos Θ
Vendor | JLab/FNAL | ETI | MSU / FRIB | SMI | Sigma Phi | Sigma Phi | Sigma Phi
B0/G0 (T;T/m) | 2.78 Tm @ 5° 0.54 Tm @ 40° | 5.0 | 2.56 | 7.9 | 11.8 | 7.9 | 3.9
Aperture (cm) | 13 | 78 | 14.5 x 18 | 40 | 60 | 60 | 60
Weight (T) | 28 | 20 | 6.8 | 18 | 70 | 18 | 163
Current (A) | 3770 | 2416 | 3930 | 2460 | 3630 | 2480 | 3270
Stored E (MJ) | 14.2 | 16.9 | 0.2 | 0.382 | 7.6 | 3.4 | 13.7
Halls B & C: Superconducting Magnets
7 new; wide variety
Vendors:
  Labs, Univ, US, Foreign
Expanded JLab staff
Leverage for SC
magnet projects

## Slide 22: 12 GeV Project: University Detector Work
Hall | University | Activity | Status
B | Idaho State U | Drift Chamber | Complete
B | Old Dominion U | Drift Chamber | Complete
B | U South Carolina | TOF Counters | Complete
B | Moscow State U (RU) | SVT Testing | Complete
C | Michigan State U | HB Magnet | Testing
C | U Virginia | Noble Gas Cerenkov | Construction
D | U Athens (GR) | Monitoring BCAL, FCAL | Complete
D | Carnegie Mellon U | Central Drift Chamber | Complete
D | Catholic U | Tagger Hodoscope | Complete
D | U Connecticut | Tagger Microscope | Complete
D | Florida International U | Start Counter | Complete
D | Florida State U | TOF Counters | Complete
D | Indiana U | Forward Calorimeter | Complete
D | U Regina (CA) | Barrel Calorimeter | Complete
D | U Santa Maria (CL) | SiPM, Lightguides for BCAL | Complete
B, C, D | U Massachusetts | Electronics Testing | Complete
NSF-MRIs funded most
12 GeV Hall C Detectors
Internat’l contributions
for detectors beyond
base equipment
NSF-MRIs funded
Hall B PCAL Detector,
Long. Polarized Target

## Slide 23: SUMMARY
12 GeV Upgrade Project = 95% Complete
  Accelerator complete & commissioned
  Civil Construction essentially complete (tunnel AC – FY15)
  CD-4A Approval ahead of schedule
  Hall A complete ; Hall D / GlueX complete
  5.5 passes > 10 GeV achieved ……… Hall D Key Performance Parameter met
Technical Accomplishments leveraged for Office of Science Projects (and beyond)
Strong University collaborations critical to detector construction/commissioning
  Hall B:
3 (of 7) detectors complete, 2 installed
Torus 6 (of 6) coils installed
Solenoid 2 (of 5) coils wound/potted
Solenoid is Project critical path
  Hall C:
6 (of 7) detectors complete, 3 installed
Q1 magnet installed & fully tested
HB magnet installed; technical issue under study
D/Q2/Q3 construction making excellent progress
Great Progress in FY2015!

## Slide 24: 12 GeV Upgrade Project
New Hall
Add arc
Enhanced capabilities
in existing Halls
Add 5 cryomodules
Add 5 cryomodules
20 cryomodules
20 cryomodules
Upgrade arc magnets
and supplies
CHL upgrade
Completion of the
12 GeV CEBAF Upgrade was ranked the highest priority in the 2007 NSAC Long Range Plan.
Upgrade is designed to build on existing facility: vast majority of accelerator and experimental equipment have continued use.
Maintain capability to deliver lower pass beam energies: 2.2, 4.4, 6.6….
Project Scope (~95% complete):
Doubling the accelerator beam energy - DONE
New experimental Hall D and beam line - DONE
Civil construction including Utilities - ~99%
Upgrades to Experimental Halls B & C - ~87%
TPC = $338M
ETC = ~$18M