## Slide 1
Early Physics Program
  Initial Physics Planning
  Ongoing Experiments – FY15
  Upcoming Physics – FY16 & FY17
Rolf Ent

## Slide 2
Initial Physics Planning - General
The Halls presented their commissioning and early physics plans to PAC-39 in 2012. Hall A’s plan was revisited, and plans were shown again to PAC-40 in 2013
Many factors come into the commissioning and early physics planning:
    Science priority
    Impact on field
    Practicalities
        Early beam specifications and requirements
        Appropriateness for commissioning new apparatus
        Readiness of ancillary equipment
        Analysis time to publication
    Involvement of young scientists
PAC-41 looked at overall reprioritization of the approved program for the initial 3-5 years of physics – and declared a select set of experiments as of high impact, to fold into the scheduling process.
(see also J. Napolitano presentation)
high impact

## Slide 4
Experiment Scheduling Process Started
Started process in 2014, one call per year – only for those experiments with “frozen floor layout” and near-final equipment construction
Introduced electronic beam requests – all user-provided information (still few wrinkles)
2nd call ongoing, will release schedule for up to June 2017 by October 1, and for up to end of 2017 by April 1, 2016.
Scheduling remains rough, to fold in:
  12 GeV pre-ops
  establishing robust accelerator operations
  budget uncertainties
  experiment goals
Nominal Dates for Scheduling Process
June 1 Call for Scheduling (Beam Time) Request
June 30 Deadline for Scheduling Request Submissions
September 1 Draft 18-Month Schedule Released
September 15 Deadline for Input of User Community on Draft Schedule
October 1 18-Month Schedule Released
Year 1 January – June Schedule Reaffirmed
Year 1 July – December Firm Schedule
Year 2 January – June Tentative Schedule
March 1 Draft 18-Month Schedule Released
March 15 Deadline for Input of User Community on Draft Schedule
April 1 18-Month Schedule Released
Year 1 July – December Schedule Reaffirmed
Year 2 January – June Firm Schedule
Year 2 July – December Tentative Schedule
https://www.jlab.org/exp_prog/experiments/scheduling.html

## Slide 5
Plans for Early Beam Physics in Hall A
16 mo. Shutdown
Early Experiments
12 GeV Commissioning
SuperBigbite Spectrometer
Beam 1st to Hall A
FY 2015
FY 2016
FY 2014
FY 2017
SBS Experiments
SBS Project
DVCS-I / GMp
3H/3He PREX / (A1n, APEX)
CREX
11 GeV
EM Form Factor
Access to GPDs
d/u at High x
Short-range correlations
Neutron skin
EM Form Factors
at high Q2
3 A-rated experiments in first years of running
DVCS (HRS-L + calo) and GMp (HRS-R) run is combined
Plan to run 3H and PREX/CREX expts as groups also
Some flexibility incorporated
12 GeV Projects:
1. Moller polarimeter
2. Compton polarimeter
3. Energy Meas. upgrade
Neutron spin structure
high impact
high impact
high impact
high impact
FY 2018
FY 2019
high impact

## Slide 6
Plans for Early Beam Physics in Hall B
Commissioning & early 11 GeV Experiments
Construction & Installation
11 GeV
6 A-rated experiments in first 5 years: HPS, PRad, pDVCS, nDVCS, pSIDIS, g1p/g1n
g1p , g1n - large x
spin structure
< 6 GeV beam
pDVCS & GPDs
pSIDIS &TMDs
neutron F2
nDVCS & GPDs
nSIDIS & TMDs
Installation
QCD in nuclei
CLAS12
non-CLAS12
high impact
high impact
FY 2015
FY 2016
FY 2017
FY 2018
FY 2019
high impact

## Slide 7
Plans for Early Beam Physics in Hall C
SHMS Installation
Early Experiments
12 GeV Commissioning
1st 11 GeV Beam
FY 2018
FY 2016
FY 2019
FY 2017
FY 2018
Polarized 3He Experiments
p, d,A(e,e’), A(e,e’p), d(e,e’p)
TMDs, CSV, (e,e’K)
High x nucleon structure
Short-range nuclear structure
Basic SIDIS cross sections
Charge Symm. Violation
Deep Exclusive Kaon Prod.
Straightforward “commissioning experiments”
Basic SIDIS and easiest L/T separation
Base equipment in early years
Ramping up to systematic understanding of Hall/SHMS and A-rated experiments
Neutron Spin Structure
A1n, d2n
high impact

## Slide 8: Early Hall C running plans – “Year 1”
Spring 2016: hope to have beam dump refurbished and have minimal beamline and beam dump checkout (risk reduction)
        (but would require readiness review)
Fall 2016: 12 GeV pre-ops
Fall 2016/Spring 2017 ~25 PAC days – Commissioning “Experiment”:
  9 days of E12-06-107 search for color transparency
  A(e,e’p) only – “easy” coincidence measurement
  11 days of E12-10-002 F2p,d structure functions at large x
  Inclusive momentum scans help understand acceptance
  2 days E12-10-108 EMC Effect in (some) light nuclei (B, Be, C)
  Integrate light nuclei with F2 run,
  Point target helps acceptance studies
  3 days of E12-10-003 D(e,e’p) – push to large missing momentum
  If time available
  Push to lower cross sections
Notes: F2 and C12 scans good for acceptance studies

## Slide 9: Early Hall C running plans – “Years 2-3”
~2017/18:
E12-09-017 Pt dependence of basic SIDIS cross sections
Push particle ID capabilities of SHMS
E12-09-002 Precise +- ratios in SIDIS – Charge Symmetry Push understanding of detector efficiencies
E12-09-011 L/T separated p(e,eK+) factorization test
Easiest L/T separation – push systematic understanding
~2018/19:
Choose a “High Impact Experiment”
E12-06-101 Pion Form Factor (needs well understood SHMS)
E12-06-105 x>1 (needs well understood background reduction)
E12-06-110 A1n (needs high-luminosity 3He)
Recall that Hall C is the high precision spectrometer Hall
high impact

## Slide 10
Plans for Early Beam Physics in Hall D
Search for Gluonic Excitations (GlueX)
h, h’ couplings, rare decays using Primakoff reaction
Light quark mass ratio
h and h’ mixing angle
108g/s preparations
GlueX
12 GeV Commissioning
E < 12 GeV
unpolarized
Primakoff
hgg
Hardware
Polarized Beam
E = 12 GeV
polarized
107g/s
high impact
FY 2016
FY 2014
FY 2017
FY 2015
FY 2018

## Slide 11
Towards the 3D Structure of the Proton: Hall A DVCS
Simplest process: e + p  e’ + p + g (DVCS)
DVCS
BH
p
p
e
e
Hall A data for Compton form factor (over limited Q2 range) agree with hard-scattering
Im C’
3rd Generation DVCS Experiment
Goals for E12-06-114 (Hall A DVCS):
To measure precise absolute cross-sections (3-5% stat and 4% sys uncertainties),
To test the scaling of the DVCS amplitudes,
To separate the Re and Im part of the DVCS Compton amplitudes.
12 GeV projections: confirm formalism
high impact

## Slide 12
DVCS and GMp: Concurrent Experiments in Hall A at 11 GeV
High impact experiment for 3D nucleon imaging
  Deeply Virtual Compton Scattering (DVCS) provides access to Generalized Parton Distributions (GPDs)
Will provide highest available Q2 measurement of the DVCS cross section
  Demonstration of scaling critical to full JLab 12 GeV GPD program
5 weeks in Spring ‘15
DVCS
GMp
High Q2 Form Factors
  Reducing GMp uncertainties will enable Super BigBite high impact program of Form Factor Measurements
DVCS and GMp:
7 graduate thesis students (MIT, Ohio, Orsay, Catholic, William and Mary, ODU, Hampton)
now ’16
now ’16

## Slide 13
DVCS: online results from Fall’14 run
p0 ’s reconstructed in DVCS calorimeter
DVCS events
(1.5 h of beamtime)
Beamline commissioning:
Moller measurement (P = 88%)
BPM calibration (+ harps operational)
BCM calibration
New raster
(Refurbished) beam dump
DVCS experiment commissioning:
Coincidence (e + g) trigger
1 GHz sampling electronics
ep → ep calorimeter elastic calibration
Completed the 1st DVCS kinematic setting

## Slide 14: Alternate Physics Program: (Epass= 1.0 GeV)
Hall-A: Commissioning beam line + e- polarimeters
Hall-B: Physics/HPS
Ribbon beam for dark matter search
Hall-D: Detector commissioning only
First coherent bremsstrahlung spectrum
48µm
294µm
Si detectors
BEAM goes here, 1mm gap in Si
Compton Asymmetry
Notes: With CEBAF reconfigured at a lower energy, progress in all three halls.
Hall-A commissioned their upgraded polarimeters and were able to measure an asymmetry in the compton polarimeter.
Hall-B has transitioned from commissioning the dark matter experiment to taking data. This experiment requires a ribbon beam to pass between SI strip detectors that reside 0.5mm from the beam. Stability!!!
Hall-D has established the alignment of the diamond radiator and the generation of a coherent bremsstrahlung photon beam.

## Slide 15
Towards Gluonic Excitations: Hall D
high impact
See presentation of J. Stevens for further update on GlueX science, on detector commissioning and understanding,
and further plans.

## Slide 16: Heavy Photon Search at JLAB
Since they couple to electric charge, A’s can be electro-produced and can decay to e+e-.
Heavy photons may mediate DM annihilation and interactions of DM with regular matter.
The Heavy Photon Search (HPS) identifies A’s as mass bumps with finite decay length in a compact forward spectrometer at JLAB.
Dark Matter may reside in a Hidden Sector, carry “dark charge”, and couple to hidden sector gauge bosons (“heavy photons”, A’s)
Heavy Photons mix with the SM , so will couple weakly (e, ~10-3) to electric charge.
An actual e+e- pair, produced in the HPS W target, is tracked by the 6-layer silicon vertex tracker (SVT) placed inside an analyzing magnet. The highly segmented PbWO4 Ecal, downstream of the SVT, was used to trigger the event. The A’ signal must be identified above a huge background of QED tridents. https://confluence.slac.stanford.edu/display/hpsg/Heavy+Photon+Search+Experiment
Run 5623 Event 62 N. Graf
Beam’s Eye View of Si Vertex Tracker
high impact

## Slide 17
Heavy Photon Search - Spring 2015 Run @ 1 GeV
This was achieved by extending the beam schedule – after the power loss and the resulting cryo problems – up to May 18. HPS only ran in late evenings/nights and in weekends to ensure there was no interference with CLAS12 installation.

## Slide 18: Heavy Photon Search at JLAB
HPS was fully installed and commissioned for the Spring 2015 Engineering Run. Beamline, detector, and trigger work as designed!
Took 1/3 week of data at 1.05 GeV with the SVT just 500 mm from the electron beam. Search for an A’ in uncharted territory has begun. First results by March 2016?
Looking for opportunistic data taking at 2.2 and 4.4 GeV in FY16. John Jaros: “Chance for a game changing discovery!”
HPS Reach and Existing Limits
2
4.5 
2015
2017
Preliminary!

## Slide 19
Potential for Hall B non-CLAS12 Science - PRad
Proton Radius Puzzle
Discrepancy between proton radius as extracted from muonic hydrogen Lamb shift measurements and the determinations from the slope of e-p elastic form factor measurements at small q2.
The PRad experiment determines the e-p elastic cross section by electromagnetic calorimetry only  can rule out origin of discrepancy if due to any systematics of e-p scattering
high impact

## Slide 20
Early Physics Program - Summary
We have made all the necessary preparations to ensure high-impact science already early in the schedule
The Experiment Readiness Review process has been revised, with high praise of external committee at the accelerator readiness review phase II (see earlier presentation and also presentation by Javier Gomez)
We have re-started the (18-month) scheduling process to guarantee priorities
In Hall A, equipment is on the floor to execute together both a 3rd generation DVCS experiment to validate the formalism towards 3D spatial imaging in the simplest process, and a precision measurement of the elastic e-p cross section - a necessary ingredient of the JLab form factor program.
In Hall D, all preparations have been made to possibly reap science benefit from the engineering run. With 30 days of engineering run exciting discovery science can come out if we are lucky… We already can do r photoproduction.
In Hall B, two experiments installed in the up- and downstream beam line alcove could run, if compatible with CLAS-12 installation, to do a Heavy Photon Search (some data are in!) and to measure the Proton Radius.