## Slide 1: Assessment of the SVT Project SVT technical project lead
Yuri Gotra
CLAS12 Silicon Vertex Tracker
Director’s CLAS12 Detector Assessments
Jefferson Lab
June 5, 2015

## Slide 2: Outline
SVT System Overview
Current Project Status: work completed
  SVT assembly
  Detector Hardware and Cabling
  DAQ
  Slow Controls
  Calibration and Commissioning
  Documentation
Project Work Remaining
  Status
  Schedule
  Cost Estimates
Off Project Work Remaining
  Status
  Schedule
  Cost Estimates

## Slide 3: CLAS12 in Hall B
High Threshold
Cerenkov Counter (HTCC)
5 T SC Solenoid
Central TOF
Silicon Vertex Tracker (SVT)
Low Threshold
Cerenkov
Forward TOF
Pre-Shower
Calorimeter
Electromagnetic
Calorimeter
SC Torus Magnet
Drift Chambers
Moeller Shield
Beam-line:
Raster magnets
Beam Position
Targets
Moeller System,
etc.

## Slide 4: CLAS12 Central Detector

## Slide 5: CLAS12 SVT Physics Requirements
Essential parts of the physics program, such as GPD’s, require tracking of low momentum particles with few percent momentum and ~1 degree angle resolution at large angles. This is achieved by the Silicon Vertex Tracker (SVT).
Silicon detector technology makes an excellent match to the central tracking system in the CLAS12 configuration, small space and high luminosity operation of CLAS12 that is needed for accurate measurements of exclusive processes at high momentum transfer.
SVT provides standalone tracking capabilities in the central detector region
  Measure recoil baryons & large angle pions, kaons
  Polar angle coverage: 35-125o
  Azimuthal angle coverage: > 90%
  Momentum resolution : pT < 50 MeV/c for 0.3 < pT < 1.5 GeV/c
  Angle resolution:  < 10-20 mr,  <5-10 mr
  Tracking efficiency: > 90%
  Match up tracks with hits in the CTOF for β vs p measurement (particle ID)
Stable operation in 5 Tesla magnetic field at instantaneous luminosities L=1035cm-2s-1 for liquid hydrogen targets, and over periods of several years.
Expected integrated luminosity per year: Ldt  500 fb-1

## Slide 6: SVT Technical Parameters
PARAMETER | DESIGN VALUE
Number of regions (radii, mm) | 4 (65, 93, 120, 161)
Sectors (modules)/region | 10, 14, 18, 24
Module dimensions (L x W x T) | 41.9 cm x 4.2 cm x 0.39 cm
Number of silicon layers/module | 2 (U, V)
Strip layout | (0o— 3o) Graded angle
Sensor thickness | 320 μm
Readout pitch | 156 µm (hybrid side)
Number of readout channels/module | 512
Total number of readout channels | 33,792
Readout ASIC | FSSR2
Backend electronics | Custom-made VXS cards
Angular coverage θ | 35°–125°
Angular coverage Φ | ~2π
Spatial resolution | 50-65 μm
Momentum resolution | ~6%
θ resolution | 10–20 mrad
φ resolution | ~5 mrad
Designed to operate at a luminosity of | 1035 cm-2s-1

## Slide 7: SVT Overview
Module
Downstream Ring
Mounting Tube
Cold Plate
Upstream Ring
Beam Line
Silicon Vertex Tracker (SVT)
Four regions
Sectors (10, 14, 18, 24)
Silicon area ~ 1.5 m²
Channels: ~34,000
Bonds: ~200,000
Region radii, mm: 65, 93, 120, 161
Hybrid temperature 24C with coolant at 15C

## Slide 8: SVT Module Features
Carbon fiber skin (.190 mm) with Rohacell 71 core (2.5 mm)
Carbon fiber is K13C2U
Rohacell 71 core replaced by copper core (2.5 mm) under electronics
Bus cable (0.078 mm) used for grounding carbon fiber and passing HV bias to sensor
HFCB: Hybrid Flex Circuit Board with Front End electronics (FSSR2 readout chips)
Carbon fiber skin and bus cable are co-cured
Downstream Tab
Pitch Adapter
Rohacell
Co-cured Carbon Fiber/Bus cable
Heat Sink
HFCB
Sensors

## Slide 9: SVT DAQ
VSCM: VXS Silicon Control Module
  Each VSCM handles 2 HCFBs (a total of 1,024 strips)
  Converts FSSR2 data driven DAQ architecture to JLab triggered event DAQ architecture
SD: Signal Distribution Module
TI: Trigger Interface Module
HCFB<->VSCM cable:
~5m length
CPU
VXS-Crate
TI
VSCM
VSCM
VSCM
VSCM
VSCM
VSCM
VSCM
VSCM
VSCM
VSCM
VSCM
SD
CPU
VXS-Crate
TI
VSCM
VSCM
VSCM
VSCM
VSCM
VSCM
VSCM
VSCM
VSCM
VSCM
VSCM
SD
CPU
VXS-Crate
TI
VSCM
VSCM
VSCM
VSCM
VSCM
VSCM
VSCM
VSCM
VSCM
VSCM
VSCM
SD
Gigabit Ethernet (to event builder)
Fiber Optics (from global trigger crate)
66x High Density Round
Shielded (100 Ohm twisted pair)

## Slide 10: SVT Slow Controls

## Slide 11: SVT QA/QC and Manufacturing Plan
Responsibilities during manufacturing:
  Module components pass vendor QA
  Reception QA/QC on module components by JLab @JLab
  Sensor QA test by FNAL @FNAL
  Module production by FNAL @FNAL
  Mechanical surveys during module production by FNAL @FNAL
  Module production testing and burn in by JLab @FNAL
  Module acceptance test by JLab @JLab
  Barrel Integration and testing by JLab @JLab
  SVT Commissioning and System Checkout by JLab @JLab
Module testing during production by JLab @FNAL:
  Module tested electrically during assembly:
    after chips are wire bonded
    after chips are encapsulated
    after hybrid placement on the backing structure
    after wire-bonding the sensors (each side)
  Hybrids are burned in after chips are wire bonded
  Assembled modules tested
  Multi-module burn-in test conducted at SiDet

## Slide 12: Outline
SVT System Overview
Current Project Status: work completed
  SVT assembly
  Detector Hardware and Cabling
  DAQ
  Slow Controls
  Calibration and Commissioning
  Documentation
  Cost Estimates
Project Work Remaining
  Status
  Schedule
  Cost Estimates
Off Project Work Remaining
  Status
  Schedule
  Cost Estimates

## Slide 13: SVT Module Production and QA Complete
Average production rate (2 modules per week) sustained
Good noise performance
Low leakage currents
Precise sensor placement (within few mm)
Passed QA testing and burn-in
Module QA data/plots uploaded to the database
No additional bad channels after burn-in
Modules transported to JLab and tested
Contract with Fermilab completed
Letter sent to FNAL on 04/06/15
Completed by March 2015

## Slide 14: SVT Region 1 assembly

## Slide 15: SVT Region 2 assembly

## Slide 16: Region 3 Assembly

## Slide 17: Region 4 Survey and Alignment

## Slide 18: Region 4 Assembly

## Slide 19: Region 4 Assembled

## Slide 20: SVT Assembly: Cabling and Faraday Cage

## Slide 21: SVT Detector Hardware and Cabling
Power Supplies and crates: LV & HV delivered, tested
HV distribution boxes: assembled and tested, 1 spare
VXS crates: received and tested
VSCM, Crate Controllers, TI, SD boards: received and tested
VME patch panel: assembled, tested
VME ADC boards (450, 4120, 2232, 3122, RS232 for chiller)
  received, tested, drivers developed
Cables:
  HV/LV/slow control: fabricated and tested
  Pulser and Data: delivered, tested
  Cables for VME patch panel: 4 types, tested
PCB for temperature and RH monitoring: installed on the R2/R3/R4 rings
COMPLETE

## Slide 22: SVT DAQ, Trigger, and PS Checkout in EEL124
COMPLETE

## Slide 23: SVT Slow Controls Tasks Complete
Control and Monitoring
Control & Monitor LV & HV to the SVT Modules
Monitor HFCB temperatures
Monitor detector internal temperatures and humidity
Monitor ambient temperatures and humidity
Monitor dew point
Monitor MPOD Crate Status
Monitor DAQ Crate Status
Monitor & control SVT Chiller
Monitor Cold Plate inlet and outlet temperatures
Monitor coolant flow
Monitor gas system
Interlock and Alarms
Provide user settable warning and alarm interlock levels
Provide user enable / disable of alarm control actions
Provide network watchdog timer
User Interface and Data Logging
Provide multi‐level GUI interfaces. (Expert level, User level, DQM, DCS/DSS)
Provide data logger interface & record system values
Provide integrated GUI interface to data logger
Provide real‐time strip‐charts of key system values
Recall / store system initialization values

## Slide 24: Checkout the SVT cooling system

## Slide 25: SVT Web Monitoring
R1
R2
R3
R4
Alarm Handler

## Slide 26: SVT Monitoring: Ambient Temperature
Ambient temperature in the clean room
R1-R4
Temperature, C

## Slide 27: SVT Monitoring: Sensor Leakage Currents
R1
R2
Current, μA
Current, μA

## Slide 28: SVT Calibration, R1-R4

## Slide 29: SVT Calibration, R1-R4

## Slide 30: SVT commissioning with cosmic rays
Trigger paddles
Collected data with Regions 1 - 3

## Slide 31: Reconstruction of tracks in the SVT
Determination of space points
  Central tracker strip ``intersection’’ determination
    1. Clustering of adjacent firing strips (2D hit)
    2. Determination of intersections of cluster centroids (double layer)
Pattern Recognition in (r,f) view
  Cut-based algorithm (> 95% efficient)
  * require 3 out of 4 intersections
  * allows skipped region
Track Fitting
  Global Fit to Helix
  Kalman Filter
  (in development)
Viewing a reconstructed simulated pi- track propagated in ~5-T solenoidal magnetic field
Based on CLAS12 software released on 05/22/15
Notes: Track in the BST are bent into a helix due to the 5T solenoidal field. So the first step of the reconstruction is to find space points. There are three daisy-chained sensors in each of the 8 layers of the current design. Each layer has 256 strips with linearly varying angles from 0 to 3 degrees. The orientation of the strips in a double layer is such that they are mirror images of each other, so that when superimposed the strips intersect to yield an estimate for the track’s trajectory intersection with the sensor plane. Because depending on the track angle and momentum more than one strip can fire at the region of intersection clustering if adjacent firing strip is first done to get a subsequent estimate of intersecting cluster lines (centroid). The pattern recognition (selection of groups of points consistent with a track) is done in r, phi to select points consistent with a circle and has a loose tandip requirement for r,z. The selected points are then fit. We check the reconstruction using GEMC data. // The strips in the hybrid sensor of Layer B are connected to the pitch adapter and
// and implanted with 156 micron pitch. There are 256 strips oriented at graded angle
// from 0 to +3 deg with respect to the bottom edge of layer B which corresponds to the z-direction.
// Strip number 1 in Layer B is parallel to the bottom of the sensor.

## Slide 32: Strip Occupancy

## Slide 33: SVT commissioning with cosmic muons
Module PS off
Channels masked
Each point represents position of a reconstructed cross
R1-R3 standalone trigger rate ~50 Hz
Several million events recorded

## Slide 34: SVT Databases
Fermilab SVT Project Document Database
SVT Module Production Database
SVT Module Testing Logbook
SVT Sensors Database
SVT Construction Database
SVT Configuration Database
SVT Conditions Database
SVT Geometry Database
SVT Calibration Database
SVT Alignment Database
SVT Commissioning Database

## Slide 35: SVT Web page in Clas12Docs
http://clasweb.jlab.org/clas12offline/docs/detectors/html/svt/introduction.html

## Slide 36: Construction Project Status
Project completion 99.9%

## Slide 37: Outline
SVT System Overview
Current Project Status: work completed
  SVT assembly
  Detector Hardware and Cabling
  DAQ
  Slow Controls
  Calibration and Commissioning
  Documentation
Project Work Remaining
  Status
  Schedule
  Cost Estimates
Off Project Work Remaining
  Status
  Schedule
  Cost Estimates

## Slide 38: Summary of project work remaining
Activity Percent remaining Cost Estimate Finish Date
Clean Room:
Slow controls software development 26% $5223 06/30/15
Full system test and burn-in, R3 60% ElecEng 0.3 MW, Sci 1.2 MW 06/15/15
Full system test and burn-in, R4 60% ElecEng 1.2 MW, Sci 1.5 MW 06/22/15
Full system test, integration of R3/R4 80% MechEng 0.8 MW, ElecEng 0.8 MW, Sci 0.8 MW 07/22/15
Procure SVT mounts and cart 100% $34194 08/21/15
Hall B:
Initial mount, cable, and check 100% MechTech 6 MW, ElecTech 2 MW, Sci 2 MW 04/20/16
Roll in and align after beam run 100% MechTech 1.2 MW, Sci 0.8 MW 12/20/16

## Slide 39: Slow Controls Software Development
Activity ID: 242211402
Budgeted cost: $5223
Percent remaining: 26%
Activity finish date: 06/30/15
Remaining steps, weight, and expected finish date:
  Develop user interfaces 15% 06/15/15
  Develop backup and restore tool 4% 06/05/15
  Integrate and test SC system into CLAS12 7% 12/01/15

## Slide 40: Full System Test and Burn-In in the Clean Room: R3
Activity ID: 2822X015
Resources: ElecEng 0.3 MW, Scientist 1.2 MW
Percent remaining: 60%
Activity finish date: 06/15/15
Remaining steps, weight, and expected finish date:
  Checkout DAQ and Trigger 50% 06/17/15
  Checkout of Safety System 10% 06/30/15

## Slide 41: Full System Test and Burn-In in the Clean Room: R4
Activity ID: 2822X020
Resources: ElecEng 1.2 MW, Scientist 1.5 MW
Percent remaining: 60%
Activity finish date: 06/22/15
Remaining steps, weight, and expected finish date:
  Checkout DAQ and Trigger 50% 06/22/15
  Checkout of Safety System 10% 06/30/15

## Slide 42: Checkout SVT DAQ and Trigger

## Slide 43: Full System Test: Integration of R3/R4
Activity ID: 2822X025
Resources: MechEng 0.8 MW, ElecEng 0.8 MW, Scientist 0.8 MW
Percent remaining: 80%
Activity start date: 07/01/15
Activity finish date: 07/22/15
Expected delivery of integration tooling: 07/05/15
Review of the integration procedures: 06/22/15
Remaining steps, weight, and expected finish date:
  Install Faraday cage over R4 20% 07/01/15
  Insert and attach R3 to R4 20% 07/14/15
  Survey position of R3 with respect to R4 20% 07/16/15
  Hook all services 20% 07/22/15

## Slide 44: SVT – Region 4 Integration
SVT Mounting & Alignment System
Support Tube
Integration and Transport Fixture
SVT
R4 Integration Adapter
R4 Support Tube
Region 4
Protective Enclosure

## Slide 45: Initial Mount, Cable, and Check SVT System in the Hall B
Activity ID: 2822X110
Resources: MechTech 6 MW, ElecTech 2 MW, Scientist 2 MW
Percent remaining: 100%
Activity start date: 03/31/16
Activity finish date: 04/20/16
Delivery of service cart: 06/30/15
Remaining steps, weight, and expected finish date:
  Install SVT cart 30% 04/05/16
  Install SVT electronics 50% 04/19/16
  Place SVT on cart 20% 04/20/16

## Slide 46: Central Detector Installation in Hall B
Central Tracker Service Cart
SVT Crates
Solenoid

## Slide 47: Roll In and Align SVT System After Beam Run
Activity ID: 2822X115
Resources: MechTech 1.2 MW, Scientist 0.8 MW
Percent remaining: 100%
Activity start date: 12/14/16
Activity finish date: 12/20/16
Remaining steps, weight, and expected finish date:
  Assembly setup 10% 12/15/16
  Assemble Region 4 50% 12/19/16
  Assemble outer shell and Faraday cage 40% 12/20/16

## Slide 48: Outline
SVT System Overview
Current Project Status: work completed
  SVT assembly
  Detector Hardware and Cabling
  DAQ
  Slow Controls
  Calibration and Commissioning
  Documentation
Project Work Remaining
  Status
  Schedule
  Cost Estimates
Off Project Work Remaining
  Status
  Schedule
  Cost Estimates

## Slide 49: Off Project Activities
Long term stability test
Calibration suite (documentation, benchmarking, integration to CLAS12 framework)
Databasing (conditions, configuration, run)
Commissioning with cosmic muons (local calibration, tracker performance)
Tracker alignment
Validating track reconstruction R1-R3, R1-R4, SVT-MVT)
Monte Carlo Validation suite
Commissioning in the Hall B without beam
Commissioning with beam (magnet on/off)
Resources:
Scientist 30 MW, Senior Staff 10 MW, Elec Eng 22 MW

## Slide 50: Summary
Assembly of the SVT regions done
Checkout of hardware systems done
Detector performance within the specs
Detector commissioning started
Remaining on project tasks are well defined
Remaining off project tasks are well defined
Project construction completion 99.9%