## Slide 1
Youri Sharabian, Jefferson Lab
CLAS12 High Threshold Cerenkov Counter
Assessment of the HTCC Construction Project
Collaborating Institutions:
Argonne National Laboratory
California State University
Fairfield University
Institute of Theoretical and Experimental Physics
Rensselaer Polytechnic Institute
University of Connecticut
North Carolina Agricultural and Technical State University
Florida International University

## Slide 2
  HTCC General Description
  Current Construction Status
    Ellipsoidal Mirrors
    Half-sector Mirrors
    HTCC Combined Mirror
    Containment Vessel
    Combined Mirror Installation
    Alignment of the PMT Mounting Units
    Light Monitoring System
  Project Work Remaining
    Status
    Schedule
    Cost Estimate
  Off-project Activities
    Status
    Schedule
    Cost Estimate
  Summary
Content

## Slide 3
    HTCC provides:
    Electron identification in experiments with electron beam
    Charged pion identification over momentum range up to ~ 5 GeV (in combination with other detectors)
HTCC occupies space between Central Detector and Region 1 Drift Chambers
CLAS12 Spectrometer
Torus Magnet
Drift Chambers
FTOF
LTCC
Calorimeters
5T Solenoid
ND
CTOF
SVT

## Slide 4
HTCC Requirements
Requirements for the HTCC are defined to meet/guarantee the main CLAS12 parameters (luminosity, acceptance, momentum and angular resolution).
The feature of the detector is that the HTCC has to be placed between Central Solenoid and Torus superconductive magnets in front of CLAS12 tracking detectors.
  The limit for thickness of the Cerenkov Mirror defined to be 200 mg/cm 2 or less
  (i.e. of the order of radiator gas thickness)
  Acceptance coverage:
    Polar angle in range of 5 to 35
    Azimuthal angle in full range (100%)
  Operational in magnetic field of 30 to 35 Gauss
  Multichannel detector with minimal number of reflections of Cerenkov light
  and minimal number of channels
  Electron detection efficiency close to 100%
  Rejection of charged pions ~ 500 or better
  Improved (simplified) maintenance

## Slide 5
PARAMETER | DESIGN VALUE
Working Gas | CO2@1atm, 25oC
Angular Coverage | ϑ= 5o – 35o; f= 0o – 360o
Threshold | 15 MeV/c (electrons)
Threshold | 4.9 GeV/c (charged pions)
Rejection of pions at 2 GeV/c | 103 (99.9% electron detection efficiency)
Rejection of pions at 4 GeV/c | 0.5x103 (99.9% electron detection efficiency)
Overall Dimensions |  15 ft and L = 6 ft along beam direction
Mirror Type | Combined Ellipsoidal, dimensions of 8 ft in diameter
Mirror Substrate Structure | Acryl (0.01”) + PMI Foam (0.6”) + Acryl (0.01”)
Mirror Thickness | (130 – 135) mg/cm 2
Number of Channels | (12x4) = 48
Photomultiplier Tubes | Electron Tubes 9823QKB (5”, quartz window)
Number of Reflections | 1 (80%) + 2 (20%)
Magnetic Field | 35 Gauss (along PMT axis)
Magnetic Shield | Multilayer with compensation coil
HTCC Technical Parameters

## Slide 6
TARGET
The HTCC will be used to generate fast trigger signal. It will provide high rejection of charged -mesons, low noise for reliable identification of scattered electrons.
The detector will provide efficient acceptance coverage and introduce minimal amount of materials.
The HTCC is a one unit detector with core component of Ellipsoidal Combined Mirror (60 Mirror Facets).
Main components:
Containment Vessel (Entry Cone and Dish, Moller Cup, thin entry and exit Windows etc.)
Combined Ellipsoidal Mirror (48 focal points)
5″ Quartz PMTs ET- 9823, Winston Cones, Magnetic Shields with Compensation Coils
Light Monitoring System
PMT
WC
ENTRY CONE
ENTRY DISH
(shown in red)
PMT FRAME PLATE
Combined Ellipsoidal Mirror
1
2
3
HTCC General Description
MOLLER CUP

## Slide 7
STRUCTURE :
COMPOSITE ENTRY WINDOW
ENTRY DISH
ENTRY CONE
MOLLER COP
PMT HOUSING UNITS containing 5-ich PMTs, Winston Cones, Magnetic Shields, Compensation Coils.
WELDEMENT PART
OUTER SHELLS
COMBINED MIRROR
EXIT WINDOW
1
2
3
4
5
6
7
8
9
Containment Vessel: In the middle are ENTRY CONE (3) with ENTRY WINDOW (1)
3
1
Assembled MOLLER CUP (4) installed along [beam] axis of ENTRY CONE
4
Containment Vessel

## Slide 8
# 4
#3
# 2
# 1
Δφ = 30°
8 ft.
■ Mirror is ~ 8 ft. of diameter and ~ 0.62  of thickness
■ Gaps, i.e. the glue joint thicknesses between adjacent
mirrors are designed to be ~ 0.005 
■ Combined mirror assembly tolerance of (0.010 – 0.020)
■ HTCC mirror is multifocal Ellipsoidal mirror
■ Consists of 12 identical sectors
■ Each sector consists of 4 ellipsoidal mirror facets
■ Angular acceptance of one sector:
5° < θ < 35°
Δφ = 30°
Combined Ellipsoidal Mirror

## Slide 9
Components (PMTs, Winston Cones, Mag. Shields)
The PMT Mounting Unit consists of:
Cylindrical Case
3-layer concentric Magnetic Shield
Compensation Coil
Along axis of the Mounting Unit will be placed 5″ Quartz PMTs ET- 9823 and Winston Cone.
Shielding with Compensation Coil are designed to attenuate ~35 to 40 Gauss fringe field generated by Central Superconducting Solenoid.
Required residual field of ~0.1 Gauss in the center of PMT photocathode can not be obtained by using of passive magnetic shields only.
Assembled Unit
Compensation Coil
Winston Cone
5″ PMT

## Slide 10
Light Monitoring System
1
2
4
5
Main components:
Integrating Sphere 4 of diameter
Fast Light Source
Adapter
Fiber bundle Harness
Light Monitoring System
3

## Slide 11
  Construction plan:
    Develop and establish technology of construction of the lightweight light collection mirrors to be done at JLab
    Manufacturing of the most critical HTCC components (such as ellipsoidal mirror facets) to be done at JLab
    Manufacturing of complete set of tooling for the mirror facets manufacturing, assembly and tests to be done at JLab
    Coating of the mirrors, manufacturing of Winston Cones, Passive Magnetic Shields to be done by vendors
    Manufacturing parts of the HTCC Containment Vessel to be done by vendors
    All assembly work and tests to be performed at JLab
    Build when necessary specialized test setups at JLab
  Tests and Quality Control
    Tests of mirror facets (reflectance, shape), and QA by vendor, JLab and Collaborating Institutions.
    Final tests QA of the assembled HTCC half-sector mirrors to be done at JLab and Collaborating Institutions
    Tests and Quality Control of 5 phototubes, magnetic shields to be done by JLab and Collaborating Institutions
    Alignment checks of components (including composite parts) of the Containment Vessel, establishing fiducial points of reference, tests to be done at JLab
    Final assembly and tests and QA of the HTCC detector to be done by JLab and Collaborating Institutions
Construction Strategy

## Slide 12
  HTCC General Description
  Current Construction Status
    Ellipsoidal Mirrors
    Half-sector Mirrors
    HTCC Combined Mirror
    Containment Vessel
    Combined Mirror Installation
    Alignment of the PMT Mounting Units
    Light Monitoring System
  Project Work Remaining
    Status
    Schedule
    Cost Estimate
  Off-project Activities
    Status
    Schedule
    Cost Estimate
  Summary
Content

## Slide 13
Ellipsoidal Mirrors
 110mm
161.4mm
Light collection pattern. Target of 10cm in 5T Field
cm
MC Simulations
2 GeV Electrons
Quartz PMT
Properties of Components
Photons impinging on the 5" PMT
Angle of incidence
Flat
Convex
CO2
Al+MgF2
Quartz
UV-glass
, nm
Radiation Length :
Required Designed
CO2 0.9% 0.9%
Mirror 0.8% 0.5%
(200mg/cm2) (130mg/cm2)

## Slide 14
Ellipsoidal Mirrors
MC Simulations
2 GeV Electrons
Quartz PMT
MC Results:
All Designed Parameters of the HTCC meet Technical Requirements
Rejection of π- mesons at 2.0 GeV
Rejection of π- mesons at 4.0 GeV
N p.e.1
N p.e.1
Np.e.2
Np.e.2
Nphe3(e=99.90%)
Nphe3(e=99.90%)
Channels
Channels
Photoelectrons
Signal strength. Quartz PMT
,deg
, deg

## Slide 15
Ellipsoidal Mirrors: Tooling
For the HTCC ellipsoidal mirror construction complete set of necessary tooling has been designed based on technology developed and established at JLab. Following tooling has been manufactured at JLab Machine Shop using 5-axis and 3-axis computer controlled milling machines:
  5 sets of tooling for ellipsoidal facet construction
  High precision vacuum table for the Half-sector Mirror assembly
  Vacuum table for the Ellipsoidal Combined Mirror construction
Set loaded with ACRYLM film ready for thermal shaping under pressure in the oven
ACRYLM – FOAM – ACRYL assembly being glued together under pressure
Thermal shaping

## Slide 16
Ellipsoidal Mirrors: Tooling
Assembly
ACRYLM – FOAM – ACRYL assembly being glued together under pressure
Trimming
Assembled mirror substrate being cut out on 5-axis milling machine
Set for construction of the mirror facets of one type (#3)
Sets for construction of the mirror facets of 5 different types

## Slide 17
Ellipsoidal Mirrors: Tooling
Design of the high precision vacuum table allows assembly of the Half-sector mirrors that would definitely fit into the final assembly without “overlaps” or leaving gaps. Geometry tests with laser beam also have been performed using the vacuum table.

## Slide 18
Ellipsoidal Mirrors: Tooling
  Vacuum table for the Ellipsoidal Combined Mirror construction consists of 12 half-sector tables identical to table for the Half-sector Mirror assembly. Whole structure is mounted on the 8x8 granite table. Two halves of the vacuum table can slide over the surface of the granite table.

## Slide 19
Ellipsoidal Mirrors: Fabrication and Tests
As of today we have all 60 Ellipsoidal Mirror Facets assembled, coated and tested.
We also have built additional ~10% of tested mirrors of each type.
Mirrors 4 (of smallest size) have on average better reflectance. Estimated Number of Photo Electrons for all
Mirrors 4 is in range of 25.3 p.e. to 28.8 p.e. We select 12 best Mirror Facets 4 which have reflectance in
range is of 27.3 p.e. to 28.8 p.e.
Best 12 mirrors of each type have the reflectivity above ~80% in the full wavelength range. Since other
facets, i.e. Mirrors 1L, 1R, 2 and 3, are focusing light generated by electrons traveling larger distances in
CO2 gas radiator and hence produce stronger signal, we estimate the NPE for all mirrors as follows:
Mirror1L 33.5 – 36.2
Mirror1R 31.8 – 34.9
Mirror2 30.6 – 35.4
Mirror3 27.8 – 32.4
All tested mirrors are suitable for our needs. As a final selection we choose 12 of each facet type with
a highest estimated signal which have least visible defects
STATUS :
71 mirrors inspected visually (for any defects) and tested by measuring reflectance using special setup
Test were carried out in both UV and optical range of 200 to 650 nm.
60 best mirrors (12 of each type) were chosen for the HTCC Combined Mirror construction
In addition 10 mirrors (2 of each type) are accepted and are being kept as a reserve

## Slide 20
Some typical results of measuring reflectance of mirrors in both UV and optical range are given bellow.
Ellipsoidal Mirrors: Fabrication and Tests

## Slide 21
Good mirrors:
1L : 1, 2, 3, 4, 5, 6, 7, 8, 9, 10, 11, 12.
1R : 1, 1_9_12, 2, 2_9_27_13, 3, 4, 5, 6, 8, 9, 10, 11.
2 : 1_9_27_13,1_8_15_12,2,2_8_16_12, 3,4,5,6,7,8,9,11
3 : 1, 2, 2_spare, 3, 4, 5, 6, 7, 7_MAY, 8, 9, 10_spare
4 : 1_2_7_12, 2_8_7_12, 3, 4_8_8_12, 5, 6_8_9_12,
7_8_10_12, 8_8_10_12, 9_8_11_12, 10, 11, 12
Reserve:
1L : 1_10_3_13, 2_10_1_13.
1R : 7, 12.
2 : 10, 12.
3 : 8_spare (rough surface), 1_old,
: 1_9_25_13, 2.
Bad:
3 :10(stain),
M3_10, M4_2, M2_12(gluing problems).
Before assembly of the first Half-sector Mirror we needed to :
Test glues and gluing procedures to find best solution (glue joint).
Maintain better environment in the HTCC Clean Room.
Check geometry of facets in standard environment using standard tooling.
STATUS :
Comprehensive tests successfully completed
Environment control in the CR established
Geometry checks completed successfully
Gluing requirements based on engineering analysis of mechanical integrity defined
Focal plane of Mirror 4
Focal plane of Mirror 3
Focal plane of Mirror 2
Focal plane of Mirror 1R
Adjustable Laser mount
Focal Planes
# 4
Table
# 3
# 2
# 1R
Geometry Test with Laser:
Geometry Test Fixture was used in tests.
Mirrors #4, #3, #2 and #1R were placed on the Table.
Laser beam was placed in target location and rasterized along center of mirrors. Images shown on pictures above.
Ellipsoidal Mirrors: Fabrication and Tests

## Slide 22
Half-sector Mirrors
Mirror facets M4, M3, M2, M1L and M1R were used in the assembly of the Half-sector Mirror after assembly procedure have been tested using rejected mirror facets.
Epoxy glue of high viscosity and small shrinkage was applied in dots to one side only covering ~25% of contact area (results of gluing tests) to minimize effects of glue shrinkage.
Geometry was tested before and after facets were glued together.
Environment in the HTCC Clean Room was not higher than RH=40%.
Assembly steps are illustrated in pictures.
Step 1
Step 2
Step 3
Step 4

## Slide 23
Step 5
Step 6
Assembled Half-sector Mirror was kept on the small vacuum table for 24 hours and then tested (next page) and moved onto Vacuum table for the Combined Mirror construction. It would stay off the tables for couple of minutes only in order to control glue polymerization process (full polymerization usually takes weeks)
Half-sector Mirrors

## Slide 24
Half-sector Mirrors
Results of geometry tests of the assembled Half-sector Mirror with laser beam (24 hours after gluing)
#4
#3
#2
#1

## Slide 25
HTCC Combined Mirror
Preliminary assembly is without gluing to check overall structure for
overlaps/gaps and establishing final positions of Half-sector mirrors by
measuring gaps between adjacent Half-sectors. Carbon Central Hub
is in the middle
Assembly of the Combined Mirror has been done in two stages :
  Preliminary assembly
  Final assembly

## Slide 26
HTCC Combined Mirror
Final assembly starts after completion (100%) of the Preliminary assembly.
The glue is applying on first Half-sector as shown above same way as during
assembly of Half-sectors.

## Slide 27
HTCC Combined Mirror
When all Half-sectors (except of #1 and #7) were glued together then
the Central Carbon Hub has been removed and two halves of the table
separated leaving a gap of ~1.5 wide

## Slide 28
HTCC Combined Mirror
Half-sector #1 has been glued to the left portion and #7 to the right portion of
the assembly. Then glue has been applied to them along the gap as shown
above. Last step is bringing the halves to contact leaving certain gap to
prevent glue dots overlapping.

## Slide 29
HTCC Combined Mirror
Final assembly of the Ellipsoidal Combined Mirror has been completed in 2 days

## Slide 30
Humidity tests of the HTCC Combined Mirror and Half-sector Mirror in the Clean Room completed . Space for HTCC final alignment available.
Containment Vessel with aluminum shells removed placed in the Clean Room.
Alignment of major structural components of the Containment Vessel completed.
Axis of the HTCC Entry Cone (beam direction) coincides with axis of the Moller Cup (offset less then 100 microns).
Entry Dish is concentric with Entry Cone within design specifications .
Center of the Weldment Part is off the beam direction less than previously reported shift of ~ 9mm .
Checks of alignment of the PMT Mounting Fixtures is unavoidable.
CV Alignment :
Containment Vessel upstream view
Containment Vessel downstream view
Entry Dish
Entry Cone
Moller Cup
PMT Mounts
Containment Vessel

## Slide 31
Combined Mirror Installation
Installation of the bridge parts
All 12 bridge parts glued to the Mirror
Installation of the Mirror Support Ring
Support Ring glued to the 12 bridge parts
Bridge Parts
Mirror Support Ring

## Slide 32
Combined Ellipsoidal Mirror has been installed in the Containment Vessel. Set of links holding the Mirror in the position allow fine adjustment with accuracy of ~ 0.01 inch or better.
The Carbon Central Hub has been adjusted to fit the Mirror leaving enough gap for glue and installed. Quality of installation has been checked.
Combined Mirror Installation

## Slide 33
May 12
May 19
May 12
May 19
RH = 0%
RH = 0%
RH Normal
RH Normal
Ø 1
Ø 3
Ø 5
Alignment of the PMT Mounting Units

## Slide 34
Alignment of the PMT Mounting Units

## Slide 35
Alignment of the PMT Mounting Units
STATUS:
Checks of alignment of all 48 channels is complete
36 out 48 channels are aligned
Part of remaining 12 channels might be aligned when HTCC is put horizontally
Work in progress
Before alignment
After alignment

## Slide 36
Light Monitoring System
The pulses leading edge is about 1.5ns slower than with passive divider and near perfect output termination with no signs of any ringing or after-pulsing
ET base, external amplifier HV=2.2kV
Modified active base at HV=1.6kV
 | Bare tube | Active base
Leading edge | 2.6ns | 3.8ns
Output range | 2.5V | 3V on each output
Outputs number | 1 | 2
Size and position of the PCB with active circuit (highlighted)

## Slide 37
Light Monitoring System
Typical Fit Result at low intensity of LED light
LMS Components :
(1) Integrating Sphere
(2) LED with Driver Board
Reference PMT with Am241 and YAP
(5) Harness and Fiber Bundle
(7) Magnetic Shield
Fitting the PMT Response :

## Slide 38
Light Monitoring System
Fitting function is stable across a wide range of intensities
Fit function accurately describes PMT response at low intensities (µ<1.0)
Position of the Peak stays within 5% of mean
STATUS:
New driver for the Light Source (LED) providing faster signals adjustable in wide range has been developed, manufactured
Module to operate remotely the LED driver has been developed, manufactured
PMT gain equalization software has been developed
Tests of all components successfully completed
LMS components installed
Fitting with Different Intensities :

## Slide 39
  HTCC General Description
  Current Construction Status
    Ellipsoidal Mirrors
    Half-sector Mirrors
    HTCC Combined Mirror
    Containment Vessel
    Combined Mirror Installation
    Alignment of the PMT Mounting Units
    Light Monitoring System
  Project Work Remaining
    Status
    Schedule
    Cost Estimate
  Off-project Activities
    Status
    Schedule
    Cost Estimate
  Summary
Content

## Slide 40: HTCC Remaining Activities as of May 31, 2015
Activity ID | Name | Activity Start | Activity Finish | Remaining Budgeted MWeeks or Proc. Cost
242241528, 630, 635 | Gas System Items | 5/4/15 | 6/30/15 | $24,357
242241610 | Install Window | 5/2/14 | 6/30/15 | 1.1
242241640 | Install/Check Mirror | 2/9/15 | 6/15/15 | 2.0
24267135 | Produce Cart Drawings | 3/9/15 | 7/22/15 | 1
24267140 | Procure Cart | 7/23/15 | 9/18/15 | $37,798
24267355, 360, 365, 370, 375 | Install in Hall B | 7/15/16 | 7/30/16 | 7.9
2822X030 | Install LMS | 2/6/15 | 7/10/15 | 5.7
2822X035 | QA during Mirror Install | 5/4/15 | 9/3/15 | 11
2822X040 | Optical Tests of Mirror | 6/16/15 | 7/15/15 | 6
Total is 34.7 mw, which is estimated at $77.0K direct ($17.4K HTCC, $24.7 Install, $34.9 Pre-ops) and is planned to be supported by Hall B personnel, including visiting postdoc and graduate student, and one contract designer

## Slide 41
Project Work Remaining
 | Activity | Percent Remaining | Cost Estimate | Finish Date
1 | Installation of the ellipsoidal mirror | 36% (9%*) | MT 2 mw | 06/30/2015
2 | Installation of the composite exit window | 45% | MT 1.1 mw | 06/30/2015
3 | HTCC - Produce Manufacturing Drawings for transport cart | 40% (1%*) | ME 1mw | 07/22/2015
4 | HTCC - procure transport cart | 100% | $37,798.00 | 09/18/2015
5 | Rig and Transport HTCC to Hall | 100% | MT 1mw | 07/18/2016
6 | Install HTCC cart | 100% | MT 0.5mw | 07/22/2016
7 | Install HTCC | 100% | MT 3mw | 07/26/2016
8 | HTCC-Verify mirror alignment and align detector to beam | 100% | SC 1.2mw, MT 1.2mw | 07/29/2016
9 | HTCC - Installation of LMS | 40% (10%*) | SCI 0.04mw, VU 1.6mw, PDUSTD 2.93mw, EE 0.3mw PDUSTF 0.53mw, ET 0.3mw | 07/10/2015
10 | HTCC - Quality control of the installed items | 50% | SC 3.5mw, VU 3.5mw PDUSTD 2.78mw PDUSTF 1.22mw, MT 0.6mw | 09/03/2015
11 | HTCC - Optical tests of mirror geometry in situ | 100% (25%*) | SCI 2mw, PUSTF 1mw PUSTD 1mw, VU 2mw | 07/15/2015
  NOTE: *) status as of today

## Slide 42
Activity ID 242241640
Budget cost 2mw
Percent Remaining 36%
Percent Remaining* 9%
Finish Date 06/30/2015
Remaining steps, weight, and expected finish date:
  Manuf. and installation of the composite limiting
  ring on the Moller Cup 2% NA
  Run checks of geometry of top 16 channels
  while purging separated volume with Mirror
  in it with Nitro gas at RH=0% 1% (done*)
  Alignment of the Mirror and Final geometry tests 30% (7%*) 06/30/2015
  Alignment of the top 16 PMT Mounting Fixtures
  using laser beam 3% (2%*) 06/17/2015
  NOTE: *) status as of today
Installation of the ellipsoidal mirror
Construction Project Work Remaining: WBS 1.4.2.2.4.1
Installation of the of the composite exit window
Activity ID 242241610
Budget Cost MT 1.1mw
Percent Remaining 45%
Finish Date 06/30/2015

## Slide 43
Activity ID 24267135
Budget Cost ME 1mw
Percent Remaining 40%
Percent Remaining* 1%
Finish Date 7/22/2015
  NOTE: *) status as of today
Produce Manufacturing Drawings for transport cart
Installation Project Work Remaining
Procure transport cart
Activity ID 24267140
Budget Cost $37,798
Percent Remaining 100%
Finish Date 09/18/2015

## Slide 44
Activity ID 24267155
Budget Cost MT 1.0mw
Percent Remaining 100%
Finish Date 07/18/2016
Rig and Transport HTCC to Hall
Installation Project Work Remaining
Install HTCC cart
Activity ID 24267160
Budget Cost MT 0.5mw
Percent Remaining 100%
Finish Date 07/22/2016

## Slide 45
Activity ID 24267170
Budget Cost SCI 1.2mw
MT 1.2mw
Percent Remaining 100%
Finish Date 07/29/2016
HTCC-Verify mirror alignment and align detector to beam
Installation Project Work Remaining
Install HTCC
Activity ID 24267165
Budget Cost MT 3.0mw
Percent Remaining 100%
Finish Date 07/26/2016

## Slide 46
Pre-Ops Project Work Remaining
HTCC - Installation of LMS
Activity ID 2822X030
Budget Cost SCI 0.04mw
VU 1.6mw
PDUSTD 2.93mw
PDUSTF 0.53mw
EE 0.30mw
ET 0.30mw
Percent Remaining 40%
Percent Remaining* 10%
Finish Date 07/10/2015
  NOTE: *) status as of today

## Slide 47
Activity ID 2822X035
Budget Cost SCI 3.5mw
VU 3.5mw
PDUSTD 2.78mw
PDUSTF 1.22mw
MT 0.6mw
Percent Remaining 50%
Finish Date 09/03/2015
Remaining steps, weight, and expected finish date:
  Align remaining 12 channels 4.5% 06/30/2015
  Vacuum leak check 8.9% 09/03/2015
  Gas leak tests of CV and fixing
  possible leaks 8.9% 07/31/2015
  Light leak check 8.9% 07/31/2015
  Cosmic ray tests 8.9% 09/03/2015
  Electronics tests with PMTs 8.9% 09/03/2015
HTCC - Quality control of the installed items
Pre-Ops Project Work Remaining

## Slide 48
Pre-Ops Project Work Remaining
HTCC - Optical tests of mirror geometry in situ
Activity ID 2822X040
Budget Cost SCI 2.0mw
VU 2.0mw
PDUSTD 1.0mw
PDUSTF 1.0mw
Percent Remaining 100%
Finish Date 07/15/2015
Remaining steps, weight, and expected finish date:
  Test 1st sector 7.7% 07/15/2015
  Test 2nd sector 7.7% 07/15/2015
  Test 3rd sector 7.7% 07/15/2015
  Test 4th sector 7.7% 07/15/2015
  Test 5th sector 7.7% 07/15/2015
  Test 6th sector 7.7% 07/15/2015
  Test 7th sector 7.7% 07/15/2015
  Test 8th sector 7.7% 07/15/2015
  Test 9th sector 7.7% 07/15/2015
  Test 10th sector 7.7% 07/15/2015
  Test 11th sector 7.7% 07/15/2015
  Test 12th sector 7.7% 07/15/2015
  Full mirror check 7.7% 07/15/2015

## Slide 49
  HTCC General Description
  Current Construction Status
    Ellipsoidal Mirrors
    Half-sector Mirrors
    HTCC Combined Mirror
    Containment Vessel
    Combined Mirror Installation
    Alignment of the PMT Mounting Units
    Light Monitoring System
  Project Work Remaining
    Status
    Schedule
    Cost Estimate
  Off-project Activities
    Status
    Schedule
    Cost Estimate
  Summary
Content

## Slide 50
Off-project Activities
Monitor long term stability of the HTCC Combined Mirror’s geometry
Develop ways of the installing laser for alignment checks in the HTCC target position without survey
Finalize calibration software
Integration of the HTCC calibration package incorporating LMS into the CLAS12 monitoring and calibration framework
Tests of PMTs linearity using LMS to define currents for the Compensation Coils of the PMT magnetic shields
Resources:
Scientist 32mw
Mech. Eng. 3mw
Mech. Des. 2mw
Mech. Tech. 25mw
Contributed Labor 22 mw

## Slide 51
  Installation of the composite components in the Containment Vessel is completed, the vessel surveyed, components aligned
  Assembly and tests of the HTCC Half–sector Mirrors and Combined Ellipsoidal Mirror completed
  The HTCC Ellipsoidal Mirror installed, surveyed, tested in working environment
  Modification of HV-dividers for 5 PMTs and corresponding upgrade of the HTCC Light Monitoring System is completed. PMT gain equalization software has been developed and tests completed
  Final installation of all components, tests and alignment are in progress
  Remaining project work defined
  Off-project activities defined
  Construction Project 99% complete
Summary