## Slide 1
Rolf Ent
JLab PAC44 Meeting
July 27, 2016
12 GeV Program Overview
You already heard about, or will hear about:
    12-GeV project progress
    Accelerator operations progress
    Hall A
    Hall B
    Hall C
    Hall D
  These slides will inform about:
  Experiment Readiness Reviews
  and Experiment Scheduling
  Equipment Enhancements

## Slide 2: Experiment Scheduling
2
Nominal Dates for Scheduling Process
July 1 Call for Scheduling (Beam Time) Request
July 30 Deadline for Scheduling Request Submissions
October 1 Draft 18-Month Schedule
November 1 18-Month Schedule Released
Year 1 January – June Schedule Reaffirmed
Year 1 July – December Firm Schedule
Year 2 January – June Tentative Schedule
April 1 Draft 18-Month Schedule
May 1 18-Month Schedule Released
Year 1 July – December Schedule Reaffirmed
Year 2 January – June Firm Schedule
Year 2 July – December Tentative Schedule
Experiment scheduling process was re-started in 2014
Only electronic beam time requests now, 1 scheduling requests per year.
Experiments can only submit requests when floor layouts frozen, construction is near-final and non-base equipment experiments passed the readiness review.
We shifted all dates by one month to be more compatible with info about budgets.
Schedule can still see changes, folding in
  12 GeV pre-ops time shifts
  Changes in operations
  Budget uncertainties

## Slide 3: ERR (Experiment Readiness Review) in a Nutshell
If your experiment includes one-of-a-kind equipment with potential novel safety implications (examples are SC magnets, tritium or high-power cryogenic targets) it requires a first-phase ERR for this equipment at the design stage.
If your experiment requires items in the category above and/or equipment beyond the declared base equipment (examples are new detector technologies, new beam lines, new spectrometers), it requires a second-phase ERR before scheduling can be requested. Always check if you need a second-phase ERR well in advance of considering a request for scheduling.
If your experiment only includes base equipment (as declared by the Deputy AD) and only in operation modes already executed, or only additional equipment that is a direct clone of base equipment, it only needs a third-phase ERR.
3

## Slide 4: 12 GeV Readiness Reviews
Experimental Hall | Project | Date
D | Solenoid Cool down | 11/6/2012
D | Solenoid Power up | 1/9/2013
D | Tagger Magnet | 12/3/2013
D | Cryo Target | 5/8/2014
D | GlueX | 7/1-2/2014
C | Q1 Power up | 1/21/2015
C | HB Power up | 3/25/2015
D | Solenoid Operation | 7/14/2015
B | Torus Cool down (2 reviews) | 4/13/2016 6/27/2016
B | Torus Power up | 7/18/2016
D | L3 trigger* | 7/22/2016
C | SHMS | 8/24-25/2016
4
* Not really 12 GeV Equipment transitioning, but closely related to the 12 GeV design for GlueX/hall D

## Slide 5: Experiment Readiness Reviews
Experimental Hall | Experiment | Date
A | Hall A restart | 12/9/2013
B | HPS | 7/10/2014
A | DVCS/GMp | 9/18/2014
Accelerator | Bubble Chamber Experiment | 8/18/2015
A | Tritium Target Review | 9/15/2015
B | Prad Experiment (2 reviews) | 11/12/2015 3/25/2016
LERF | DarkLight | 12/7/2015
A | Series of (4) Tritium Experiments | 3/16/2016
A | APEX | 4/7/2016
A | PREX-CREX | 6/1-2/2016
B | CLAS12 Ancillary Equipment | 6/13-14/2016
D | Primakoff Experiment | 7/20/2016
A | 40Ar Spectral Function | 7/21/2016
C | E12-06-107, E12-10-002, E12-10-003, E12-10-008, E12-09-017, E12-09-011, E12-09-002 | 8/24-25/2016
5

## Slide 6: Enhancements beyond 12-GeV Upgrade
• Hall A DVCS Calorimeter (France - Orsay) installed/in use
• Hall A SBS – WBS1 complete, WBS2,WBS3 ongoing (Capital Equipment (CE))
• Hall A SBS GEMs (Italy INFN, UK), Hadron Cal. (CMU+INFN) ongoing (ops)
• Hall A pre-R&D toward PV (MOLLER magnet concept, with MIT) ongoing (ops)
• Hall A SOLID (China, Temple, Duke, ANL, …) ongoing (magnet - CE)
• Hall A APEX septum magnet (Canada, Stony Brook) complete
• Hall B longitudinally polarized target (ODU …, NSF/MRI) ongoing (infrastr. - CE)
• Hall B forward tagger (Italy INFN & NSF/MRI) complete
• Hall B RICH sector(s) (Italy INFN, Chile) ongoing (PMTs, materials - CE)
• Hall B MicroMegas (France - Saclay) near-complete
• Hall B Central Neutron Detector (France - Orsay) complete
• Hall B Heavy Photon Search (HPS) (DOE HEP, France, INFN) complete/in use
• Hall B H Gas Target for Proton Charge Radius (NSF/MRI) complete/used
• Hall C Kaon Detection System (CUA …, NSF/MRI) installed
• Hall B,C Backward nucleon detection system (Israel/ODU/MIT) ongoing
• Hall C Neutral-Particle Spectrometer (CUA …/France/UK/Armenia, NSF/MRI) ongoing
• Hall D DIRC-based PID/Cherenkov system (JLab/IU/MIT) ongoing (CE)
• Hall D Discussions with China on calorimeter upgrades planning
• LERF: DarkLight Phase-I Equipment (MIT …, NSF/MRI) ongoing
• Injector: Bubble Chamber for 16O(g,a)12C inverse kinematics (ANL) ongoing

## Slide 7
Hall C – NPS & Halls A/C – Compact Photon Source
Neutral Particle Spectrometer – 2015 NSF/MRI funding & small UK grant approved
(Lead: CUA, with Glasgow, JLab, ODU, Ohio, Orsay, Yerevan)
Consisting of a highly segmented EM calorimeter preceded by a sweeping magnet
Provides precision coincidence setup with neutral-particle detection (HMS + NPS)
5 approved experiments: DVCS & SIDIS (e,e’p0), WACS & (g,p0), polarized WACS.
The idea of a Compact Photon Source also originated in NPS meetings, Fall 2014.
7
Compact Photon Source:
- an increase in FOM of ~30 (for H, D polarized targets)
- Concepts agreed upon:
~ 1 meter magnet
~ 2 Tm field
~ small few mm collimator about 1 m before target
- Recent: rotate polarized target
cell evades the beam raster!
Several ideas still worked on for implementation
Use magnet as dump
Small local dump after magnet
Chicane to transport electron beam to dump
Radiological impact studies ongoing
(maintenance, work/equipment on pivot, general background)

## Slide 8: Hall D: Forward Kaon Identification
Four of the BaBar DIRC bar boxes will be installed in front of the TOF wall.
This combined with the other PID systems in GlueX will allow to fully study final states with strange quarks:
  Strangeonium mesons & hybrids
  Hyperon & cascade baryons
Physics Division-led Review with DOE in attendance on 10/14/15
Very positive response from the committee, recommendations implemented
Revised Project Management Plan submitted to DOE/NP
Capital Equipment Project started in April 2016
Expected 2018
Joint collaboration between IU, JLab and MIT
8

## Slide 9: Summary
9
Very busy with experiment readiness reviews, both to transition 12-GeV equipment to (safe) operations stage and for upcoming experiments.
Impressive new equipment efforts of very active and engaged (international) user community showing large interest in JLab-12 GeV science program (we are now well above 1500 users).

## Slide 10: Halls B & C Start-up Schedule
Halls B and C – most likely schedule for start-up:
  Hall C Experiment Readiness Review: Aug. 24-25, 2016
  Hall C Accelerator Readiness Review: likely Nov. 2016
  Hall C online for pre-ops: likely January 2017
  Hall B Readiness Review in three stages:
    Ancillary equipment had Experiment Readiness Review in June 2016
    Initial Accelerator Readiness Review January 2017
    Final Accelerator Readiness Review (walkthrough) ~March-April 2017
  Hall B online for pre-ops: likely April 2017