## Slide 1: 12 GeV Upgrade Project Status & Plans
Science & Technology Review
May 9-11, 2012
C. H. Rode

## Slide 2: Agenda
Progress Highlights
  6-month Shutdown Accomplishments
  Subsystem Status
Problems
  Major – SC Magnets
  Minor
Funding
  FY11 – Project was funding limited
  FY12 - $16M cut
  FY13 – Major issue
Summary and Beam Goals

## Slide 3: Progress Highlights
As of 31-MAR-2012
  Percent complete 61%
  Percent obligated (including phased contracts) 74%
Effort had peaked at 210 FTEs during 6-Month Shutdown
Project is running:
4% over cost
4% late (8 weeks)

## Slide 4: 6-Month Shutdown - Accomplishments
7 of the 9 existing Magnet arcs were refurbished and upgraded – 175% of baseline plan
First Two
Last One: #208

## Slide 5: 6-Month Shutdown - Accomplishments
Refurbished Dipole Re-installation and New Arc 10 Beamline

## Slide 6: 6-Month Shutdown - Accomplishments
2 of the 10 Cryomodules were installed and commissioned.
CURRENT STATUS: All 10 strings complete.
4 cryomodules in tunnel: 1 being tested; 5 being assembled.
25-APR: 12 GeV gradients and full current.

## Slide 7: 6-Month Shutdown - Accomplishments
Hall D tunnel extension was completed.

## Slide 8: 6-Month Shutdown - Accomplishments
Low Conductivity Water (LCW) Upgrade was completed.

## Slide 9: Civil is Basically Complete
Two minor FY14 tasks remain.
CHL Addition
Hall D Counting House

## Slide 10: Accelerator
4 of 10 RF Zones operational.

## Slide 11: Accelerator (Continued)
CHL Compressors installed.

## Slide 12: Accelerator (Continued)
Upper Coldbox
Lower Coldbox

## Slide 13: Accelerator (Continued)
Hall D refrigerator installation started.

## Slide 14: Physics – Hall D
The 48 Hall D Barrel Calorimeter (BCAL) segments were delivered.
The Hall D Solenoid was installed.

## Slide 15: Physics – Hall D (Continued)
DETECTOR
The FDC is beyond the half-way point building chambers.
The CDC has all straw tubes and over half of the electrical hook-up done.
The FCAL leadglass detectors are done. The last part of the bases are underway at Indiana U.

## Slide 16: Physics – Hall C
All the Spectrometer support carriage parts are expected to arrive by June.

## Slide 17: Physics – Hall B – Drift Chambers
At ISU: Reg.1 #2 Being tested at ISU. #3 and #4 in progress.
At JLab: Reg.3 #1 and #2 in progress.
At ODU: Reg.2 #2 shipped to JLab for testing. #5 in progress.
We are at the half-way point!!!
ODU – Old Dominion Univ.
ISU – Idaho State Univ.

## Slide 18: Physics – Hall B – Silicon Vertex Detector
  Sensors are being manufactured by Hamamatsu.
Staves are being assembled by Fermilab.
Several external technical progress reviews have been held.

## Slide 19: Physics – Detector Beam Tests
  Hall B SVT Two Stave Test
  Hall D FCALTest
  Hall D Mini-BCAL Test
End view of mini-BCAL module showing showing light guides.

## Slide 20: Major Problem – Hall B SC Magnets
Two existing contracts have been terminated due to QA and schedule
  We have assumed the three machine shop sub-contracts.
  Five truck loads of equipment have arrived at JLab.
  We are attempting to qualify industrial conductor soldering vendors.
  We are in the process of setting up an in-house conductor soldering line.
Hall B Torus
  The Fermi Lab contract for cold mass fabrication has been awarded.
  Planning for Cryostat assembly has not started.
Hall B Solenoid
  We are out to bid to three industrial vendors.

## Slide 21: Major Problem – Hall C SC Magnets
Hall C Q2/Q3/Dipole
50% of the conductor has been soldered.
Prototype short Dipole
winding continues.
Vendor is procuring a second winding table.
Production winding has not started.
Schedule issues remain to be settled.
Dipole Final Design Review is 9-May.

## Slide 22: Minor Problems
We have canceled the contract for the 15 high power “Box PS”
  Schedule and cost issue
  The two high precision PS (ARC 1 & Hall A) have been awarded
  The rebid of Box PS proposals are due in late May
The two CHL coldbox and compressor deliveries were very late.
The commissioning of CHL #2 has been delayed to late in the Long Shutdown.

## Slide 23: 12 GeV - $310M TPC
ARRA Shift of $65M
from FY10/11 to FY09
FY12: reduction of $16M
FY13: Pres Request – no restoration
CD-4B may be at Risk

## Slide 24: 12 GeV Project Progress vs Funding

## Slide 25: FY12 - $16M Cut
The $16M cut forced the project to:
  Lengthen the 12-month shutdown to 16-month shutdown
    Reduced contractors ($1M)
    Delays some Accelerator procurements ($2M)
  Postpone remaining Civil to FY14 ($2M)
  Postpone Hall D replacement solenoid design to Jul-2013 ($1M), and FAB to APR 2014 ($7M)
  Reduce Hall B & C staffing ($1M)
  Postpone some Physics procurements ($3M)
No contingency for cost overruns

## Slide 26: 12 GeV Upgrade Project Schedule
    Two short parasitic installation periods in FY2010
    6-month installation
    May-Oct 2011
    12 16-month installation
    May 2012 - May Sept 2013
    Hall A commissioning start Oct 2013 Feb 2014
    Hall D commissioning start
    April 2014 Oct 2014
    Halls B & C commissioning start Oct 2014 Apr 2015
    Project Completion June 2015
    CD-4B may be at risk

## Slide 27: REVISED 12 GeV BEAM GOALS
We are proceeding to hold CD4A & 4B
  Jan-2014 Accelerator (4-month slip) Driven by FY12 funding
  Feb-2014 Hall A (4-month slip) Driven by 16 month shutdown
  Oct-2014 Hall D (6-month slip) Driven by UIM shutdown
  Apr-2014 Halls B & C (6-month slip) Driven by FY13 funding
If no additional FY13 funding becomes available, in 3QFY13 we may need to abandon CD-4B and slow down the project, primarily Hall B & Hall C.

## Slide 28: SUMMARY
Current status of 12 GeV Project:
  Performance Index: schedule 96% ; cost 96%
  Excellent progress to date
Concern about FY12 funding issue:
  $16M below profile
  Not restored in FY13
Although Project is progressing well, funding issues will severely challenge the schedule.