## Slide 1: Electron Cooling R&D
NP Community Panel Review of the EIC
Rockville, November 29 – December 2 2016
Geoffrey Krafft

## Slide 2: JLEIC Electron Cooling CTEs
R&D Item | Priority | Initial TRL | Final TRL | Performance Period | Burdened Cost
ECL1 – Electron Cooling Simulations | First | Low | High | 2017-2019 | 488k$
ECL2 – Bunched Beam Cooling Experiment at IMP | First | Med | High | 2017-2018 | 248k$
ECL3 – ERL Cooler Design for Single and Multi-turn Operations | First | Low | Med | 2017-2018 | 1710k$
ECL4 – Magnetized Source for the e-cooler 32mA | First | Low | Med | 2016-2018 | 0
ECL5 – Fast Kicker Prototype for Multi-turn Cooler | First | Med | Med | 2017-2018 | 911k$
ECL6 – Fast Kicker Test with Beam | Second | Med | High | 2019-2019 | 473k$
ECL7 – Integrated Test of Multi-turn Circulator Ring | Second | Med | High | 2019-2021 | 19899k$
ECL8 – Magnetized Source for the e-cooler 200mA | Second | Med | High | 2019-2021 | 4026k$

## Slide 3: Talk Organization
JLEIC High Energy Collider Cooler
  Development Plan
CTEs
  ECL2: Bunched Beam Cooling Experiment at IMP
  ECL1: Electron Cooling Simulation
  ECL4: Magnetized Source for e-cooler at 32mA (LDRD)
  ECL8: Magnetized Source for e-cooler at 200mA
  ECL5: Fast Kicker Prototype for Multi-turn Cooler
  ECL6: Fast Kicker Test with Beam
  ECL3: ELR Cooler Design for Single and Multi-turn Operation
  ECL7: Integrated Test of Multi-turn ERL Cooler
Schedule and Funding Profile (w/wo ECL7)

## Slide 4: JLEIC Collider Electron Cooler
ion beam
ion beam
cooling solenoid (B>0)
magnetization
flip
cooling solenoid (B<0)
top ring: Circulating Cooler Ring (CCR)
bottom ring: ERL
injector
beam dump
linac
fast extraction kicker
fast injection kicker
dechirper
rechirper
circulating bunches
extracted bunches
injected bunches
exchange
septum
vertical
bend
into ERL
vertical
bend
to CCR
Baseline Concept: Multi-turn Cooler

## Slide 5: Cooler Development Focus Areas
Beam Cooling Simulations and Benchmarking
  Key Issue: Short Electron Pulse Cooling Rate
  ECL2: Bunch Beam Cooling Experiment at IMP
  ECL1: Electron Cooling Simulation
Hardware Development
  Key Issue: Test Needed Hardware Elements
  ECL4: 32 mA Magnetized Source/ECL8: 200 mA Magnetized Source
  ELC5 and ECL6: Fast Kicker and Kicker Beam Test
Circulator Cooling Ring
  ECL3: ELR Cooler Design for Single and Multi-turn Operation
  ECL7: Integrated Test of Multi-turn ERL Cooler at LERF (Former JLAB FEL)

## Slide 6: Hardware Development Plan
Develop and Test
CCR- ECL7
Magnetized
Gun-ECL4
High Current Magnetized
Gun-ECL8
Single Turn ERL
Cooler
Multi-Turn CCR
Cooler
Baseline Cooler
Backup Cooler
Fast Kicker
ECL5 and ECL6

## Slide 7: Cooling Simulations and Benchmarking
ECL2: Bunched Beam Cooling Experiment at IMP: the first non-DC electron cooling experiment cooling a 12C+6 ion beam at 7 MeV/u was performed in May 2016 at the IMP’s CSRm ring.
Initial: TRL4

## Slide 8: ECL2: Bunched Beam Cooling Experiment
For the expected short electron pulses performing cooling in JLEIC cooler, the cooling rate will be reduced from that expected from a DC cooler (ions not in contact with cooling electrons at all times). Measurements with more control over the electron distribution, and with better diagnostics for the cooled ion beam will be supported through this proposal.
The total burdened cost of this project is 248k$, 195k$ for labor and 52k$ for non-labor items.
Final: TRL7 (Assuming Simulation Benchmark Success)

## Slide 9: 2nd Bunched Beam Cooling Experiment
Schedule: April 16 to 30, 2017, at Institute of Modern Physics (IMP) at China.
JLab Participating:
  4 JLab staff will travel to IMP to participate this experiment, sharing the tasks of hardware improvement and software development, and data taking and analysis;
  4 more staff have participated in studies and provided technical support
Experiment Scope: Bunched electron beam from 80 m to 3.4 m bunch length will cool a 12C+6 beam at 7 MeV/u and 30 MeV/u with a bunch length from coasting to 3.4 m.
Anticipated Improvements (over the 1st experiment):
  Better beam diagnostics
  More software support
  Higher ion current (scheme to accumulate ions using DC electron cooling)
Planed Measurements
  Momentum spread evolution over time, and longitudinal cooling rate
  Transverse emittance evolution over time, and transverse cooling time
  Cooling rate as a function of electron bunch length with fixed bunch current
  Cooling rate as a function of electron bunch length with a fixed average current
Courtesy: Y. Zhang and H. Wang

## Slide 10: ECL1: Electron Cooling Simulation
Electron cooling simulation is essential for a deep understanding of the electron cooling physics both qualitatively and quantitatively. Simulation study is also needed to optimize the parameters of the colliding ion beam and the cooling electron beam for better cooling. A new element to be understood is cooling with a pulsed (short duration) electron beam.
0.5 FTE for the first year, and 0.75 FTE for each year following. 2.0 FTE total. All the labor is Scientist labor. The total burdened cost of this project is 489k$, all of which is labor. This work previously supported by EIC R&D FOA.
Final: TRL7

## Slide 11
Simulation for the Strong Cooling Scheme
Cooling rate | 10-3 1/s | -4.708 | -11.787 | -0.554
IBS rate | 10-3 1/s | 12.894 | 0.669 | 0.992
Total rate | 10-3 1/s | 8.186 | -11.118 | -0.455
Strong cooling with electron current up to 3.2 nC/bunch
CM Energy 44.7 GeV
Cooling rate and IBS rate with design parameters. The horizontal IBS rate is much higher than the cooling rate.
Revise the proton beam parameters to reduce IBS:
current reduced to 82%
emittance 0.5/0.1 m 0.5/0.15 m
bunch length 1.0 cm to 1.5 cm
transverse coupling 40%
Introduce dispersion at the cooler
We can maintain the emittance for about two hours, but the longitudinal overcooling will break the equilibrium..
Courtesy: H. Zhang

## Slide 12
Max Error of Emit. For One Step Size |  | 
 | N=10,000 | N=100,000
Δt=1s | 1.54×10-5 | 2.42×10-6
Δt=10s | 3.06×10-4 | 1.04×10-4
Max Accu. Error of Emit. in One Hour |  | 
 | N=10,000 | N=100,000
Δt=1s | 5.70% | 0.88%
Δt=10s | 11.65% | 3.81%
Turn-by-turn Tracking for Electron Cooling
The smaller the time step is, the smaller the error we get.
The larger the number of particles is, the smaller the error we get.
If we use step size no more than one second, and number of particles no less than 100,000, the simulation results should be accurate enough (at least for now).
Up to 10 seconds, the proton beam maintains the Gaussian distribution.
Turn-by-turn tracking to check the accuracy of the RMS dynamic simulation
Cooler is modeled as a thin lens, which gives a momentum kick on each proton
Linear one-turn transfer map is used for proton transition.
Initially the protons have Gaussian distribution.
Calculate the relative errors of emittance in one second and 10 sends, and estimated the accumulated error for one hour.
Courtesy: H. Zhang

## Slide 13: Hardware Development
ECL4: Magnetized Source for e-cooler at 32 mA: A high charge (420 pC) magnetized source is funded by the Jefferson Lab LDRD program that should operate up to 32 mA average current. This project concludes in 2018.
Final: TRL5
Magnetized beam parameters:
= 1 – 5 mm, Bz = 0 – 2 kG
Bunch charge: 1 – 500 pC
Frequency: 15 Hz – 476.3 MHz
Bunch length: 10 – 100 ps
Average beam currents up to 32 mA
Gun high voltage: 200 – 350 kV

## Slide 14: ECL8: Magnetized Source at 200 mA
This R&D effort aims to demonstrate the full CW electron beam current (200 mA) required for a magnetized bunched electron beam weak cooler. This project required if the “backup” single turn ERL cooler is needed to build the JLEIC, or if the LDRD cooler cannot be upgraded to 75 mA.
The two main results to be demonstrated in this project are: (1) produce and control a suitable low emittance high average current electron beam and (2) demonstrate suitable photocathode lifetime in the magnetized source in case the photocathode gun is chosen. Work towards achieving 3.2 nC (strong cooling) performed.
Natural follow-on to ECL4 work.
Initial: TRL5

## Slide 15: ECL8: Magnetized Source at 200 mA
Addressing concerns and solving problems associated with gun reliability will be a major focus of ECL4 and ECL8 preparing for the eventuality that a highly reliable magnetized electron source will be needed for any collider cooler.
8.5 FTE over the three years of the project, including 1 FTE of engineering. Over one half of the procurement budget is needed for a full current power supply. The total burdened cost of this project is 4,025k$, 2,077k$ for labor and 1,949k$ for non-labor items.
Final: TRL7

## Slide 16
0 A
400 A
σ1 = 3.7 mm
σ2 = 4.9 mm
φ = 15°
= 38 neV s
= 38 neV s

## Slide 17: ECL5: Fast Kicker
ECL5: Fast Harmonic Beam Kicker. A first half-scale 476.3 MHz copper cavity has been prototyped, bench measured, and satisfies beam dynamic requirements for a Circular Cooler Ring design for the bunched electron cooler.
Initial: TRL4

## Slide 18: ECL5: Fast Kicker
The main task in this proposal is to build a full size prototype which can be installed and tested with beam. The project will have a complete a set of three harmonic cavities with engineered vacuum attachments and beam line compatible with a high vacuum pump station and beam pipe gate valves.
This concept for the fast kicker and results of R&D work based on the half scale prototype have been published in two PRST-AB papers and documented in Ms. Y. Huang’s PhD thesis.
The total burdened cost of this project is 911k$, 611k$ for labor and 300k$ for non-labor items.
Final: TRL6

## Slide 19: High-power Model
Vacuum model concept in progress
Can test in UITF, LERF or ???
Need to settle on a baseline kicking scheme (angle, frequency) to go to the next step.
Eagerly anticipating new postdoc position
Need to study multi-turn effects with magnetized beams
Courtesy: R. Rimmer and H. Wang

## Slide 20: ECL6: Fast Kicker Test with Beam
This proposal covers a beam test of the kicker supported by ECL5 at Jefferson Lab’s Upgraded Injector Test Facility. Demonstrate fast beam kicking by altering the trajectory of one of every six bunches and measuring the deflected and un-deflected beam properties.
0.6 FTE for installation, operations, and scientific labor for performing tests. Procurements mainly related to beam-line modifications to install kicker and proper diagnostics. A new wide-band RF amplifier is needed to drive the kicker. The total burdened cost of this project is 472k$, 147k$ for labor and 326k$ for non-labor items.
Final: TRL7

## Slide 21
8-channel RF source
Expected kicked beam on viewer, one out of six bunches
Install here
Electrodynamic, Phase II sbir
ECL6: Fast Kicker Test with Beam

## Slide 22
Harmonically resonant cavity
Harmonically resonant cavity as selective energy booster/kicker
Drive harmonically resonant cavity with RF to create powerful, short-lived E-field
Set laser rep rate to 1247.5 MHz, kicker driven at 1497 MHz plus harmonics
Use, Wien filter, chopper and/or 1D spectrometer to measure energy boost
Bunched beam on this circle,
No energy boost
On this circle,
energy boost
Courtesy: M. Poelker, B. Roberts, J. Grames

## Slide 23: ECL3: Circulator Cooling Ring
ECL3: ERL Cooler Design for Single and Multi-turn Operation. This proposal offers developing software and methods, in the context of completing a full (front-to-end) cooler design for the JLEIC collider. Design elements including: (1) simulating magnetized beam formation and injection, (2) preserving the magnetized beam quality during acceleration, and (3) utilizing and simulating high repetition rate beam exchange between the driver ERL and the CCR will be investigated.
7.0 FTE Scientific and Engineering Design Labor. The total burdened cost of this project is 1,710k$, all of which is labor.
Final: TRL5

## Slide 24: Longitudinal Behavior
420 pC ideal
420 pC S2E
420 pC ideal w/CSR
2 nC ideal
Courtesy: S. Benson and D. Douglas

## Slide 25: Where Are We and Where Do We Go?
Have to partition the cooling to match IBS.
Can use globally symmetric transport.
Need to simulate CCR with CSR shielding
Need to add space charge to CCR simulations
Need injector design (subharmonic)
Might want to use emittance exchange for either the ion ring or the cooler linac.
Need to look at ion trapping and HOM damping in linac.
Have to study BBU
Need to look at Injection/extraction details (e.g. energy slew, apeture)
Courtesy: S. Benson and D. Douglas

## Slide 26: ECL7: Integrated Circulator Ring Test
This proposed R&D covers a full beam test of the CCR concept in a ring constructed adjacent to the Jefferson Lab LERF.
R&D funding is required to construct the CCR, the transfer lines into and out of the ERL, install and integrate the magnetized source and fast beam kickers, and perform beam tests of the complete systems.

## Slide 27
Injector
IR Wiggler
Bunching Chicane
SRF Linac
Beam Exchange Test Insertion
Dump
CCR Test Ring
ERL Arc
ERL Arc
Exchange Insertion Schematic
ECL7: CCR Ring Driven by LERF

## Slide 28: ECL7: CCR Ring Driven by LERF
Significant First Demonstrations:
  Acceleration and transport of a magnetized beam through an ERL.
  Successful launch and stacking of bunches in the cooler ring.
  Preserving beam brightness over multiple turns in a cooler ring.
In our present judgement a CCR test will take the readiness of the cooling ring to TRL8.
10.0 FTE for the first year, 12.5 FTE for the second, and 16.0 FTE the third, mainly technical/installation labor. Costs include LERF Operations. The total burdened cost of this project is 19,900k$, 9,407k$ for labor and 10,493k$ for non-labor items.
Final: TRL8 (for Circulator Ring)

## Slide 29: Statement of Work
Graft a magnetized source onto the existing LERF injector.
Graft a magnetized-beam-appropriate merger into the existing LERF ERL.
Reconfigure the UV Driver ERL for operation as a CCR driver/recuperator (ERL will operate at ~55 MeV)
Modify the FEL back leg beam transport to serve as an ERL/CCR beam exchange region. The CCR will be vertically displaced, with a straight-line insertion lying directly above the FEL axis.
Rearrange existing components and install beam transfer elements (RF kickers, a septum, and a limited number of conventional beamline elements) along the FEL axis.
Fabricate and install CCR components.
Commission CCR.
Courtesy: S. Benson

## Slide 30: Schedule and Funding
Simulations and Benchmarking |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
ECL2: IMP Measurements |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
ECL1: Cooling Simulations |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Hardware Development |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
ECL4:LDRL Magnetized Gun |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
ECL8: Extend to 200mA |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
ECL5: Kicker |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
ECL6: Kicker Test |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Circulator Cooler Ring |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
ECL3: Cooler Design |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
ECL7: CCR Test |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
2017
2018
2019
2020
2021
10 M$
1521k$
1654k$
2615k$
9439k$
8057k$
7085k$
1032k$
1032k$

## Slide 31: Cooler Design Priorities (Reviewers)
Risk items:
  The JLAB design requires a high-average-current magnetized beam source. They are proposing a novel multi-turn accumulator ring to “recycle” the ERL beam, which to date has not been tested. The alternate (Note added: single pass ERL) approach requires a much higher average current magnetized source.
To demonstrate technical feasibility need:
  High current single-pass ERL for hadron cooling.
  Benchmarking of realistic EIC simulation tools against available data
  A high current magnetized electron injector
  High power fast kickers for high bandwidth (2 ns bunch spacing) feedback
  Integrated magnetized beam/kicker circulation test using the existing ERL infrastructure.

## Slide 32: R&D High Priority List - (A) and (B) (Reviewers)
Items in Red are highest priority (A) because they are required for all projects. All others are rated High (B).
High current single-pass ERL for hadron cooling
Strong hadron cooling
Note that neither of these corresponds to a specific proposal and demonstrate the reviewers appreciate the need in EIC for the best cooling
For Jefferson Lab Cooler
High power fast kickers for high bandwidth (2 ns bunch spacing) feedback
Develop a high current magnetized electron injector (thermionic gun?)
Integrated magnetized beam/kicker circulation test using the existing ERL infrastructure

## Slide 33: Cooler: R&D Priority (Reviewers)
The following are High (C) priorities (JLAB specific):
Electron cooling simulations
ERL Cooler design for single and multi turn operations
Magnetized source for the e-cooler 36 mA
Fast kicker prototype for multi turn cooler
The following are Medium priority:
Bunched beam cooling experiment at IMP
Fast kicker test with beam
Integrated test of multi-turn circulator ring
Magnetized source for the e-cooler 200 mA

## Slide 34: Cooler Plans– Notes and Recommendations
Integrate approaches with the CCR proposal at JLAB, for understanding of recirculating and ERL concepts.
Define and perform a demonstration of adequate hadron cooling with clear, pre-defined demonstration goals
Continue to pursue development of the CCR proposal and other recirculating and high average current ERL demonstrations, for example at CBETA (N.B., not at LERF!)
Continue the development of fast cooling with bunched magnetized electron beams, while studying alternate approaches such as CeC
Ensure that ongoing tests of pulsed beam cooling are relevant to the goal of hadron cooling for JLEIC

## Slide 35: Our Comments: Benson and Krafft
They recommend development of simulation tools but do not mention cooling simulations directly (taking broader view?)
The reviewers strongly stress the need to develop high current ERLs. This applies to JLAB and BNL and is significant common overlap. Cornell has the advantage for sources. JLAB has the advantage in ERL operation.
Can angular momentum affect BBU threshold? Probably not but we should think about it.
“The panel notes that an ex-parte communication obtained by a panel member following the panel’s meeting indicates that there could be significant challenges in achieving the required transverse cooling rates for one or more of the proposed designs” Clarification needed.
The panel mentions the use of emittance exchange in the CeC design. We might be using it as well.
Matching, injection, and extraction are considered risks. I would not place these high on the list of issues.
They want us to pursue CCR tests at LERF. How do we do this?
Can CeC work for JLEIC? (probably not but need to look at it)

## Slide 36: Energy Recovered Loop Accelerator
Energy Recovery Linac
Low Energy Loop
High Energy Loop
Expansion Cooling: Temperature ratio between
beams is equal to the ratio of the β-functions! Can
easily be large by design. See F. Lin, et al., IPAC’16

## Slide 37: Cooling Rates
Chart: Relative Cooling Rate tcooling/teq vs. trad/teq
Relative cooling time for Ni/Ne = 0 (tan, exact above), 0.08 (grey), 0.2 (blue), 0.5 (brown)

## Slide 38
f
2
Emitance Exchange Using SRF Bunching
i
1
Pros:
Well established SRF technology
No need for magnetized injector
Simple and stable in operation and control
Minimum impedance
Free of radial aberration to beam (at large
Cons (if any?...)
Instabilities in small emittance directions
Courtesy: S. Derbenev
Notes: Pros:
𝐕_𝟎

## Slide 39: Storage Rings With Emitance Exchange
Storage ring – high energy cooler
Two-energies storage ring –
high and medium energy cooler
Short period strong wigglers for radiative damping, minimum dispersion
EmEx to transplant energy spread to large horizontal transverse emittance
Flat to round beam transformers to match solenoid
Potential show-stopper (for both):
-intra-and inter-beam scattering
Courtesy: S. Derbenev
Abstracts submitted to IPAC 2017
Notes: Short period strong wigglers for radiative damping, minimum dispersion
EmEx to transplant energy spread to large horizontal transverse emittance
Flat to round beam transformers to match solenoid

## Slide 40: Summary
High quality bunched beam electron cooling is fundamental for JLEIC to achieve high luminosity.
Jefferson Lab scientists are well positioned and thoroughly conversant with the technology and issues regarding electron coolers.
Jefferson Lab has begun developing some of the required technology through LDRD and the kicker work. With support, this work should be rapidly built on to yield significant tests and prototypes.
The CTEs ECL1-5, with highest priority, are needed to continue and extend collider cooler development.
We are all ready and itching* to advance.
*“strongly desiring or craving” (Urban Dictionary)

## Slide 41: 2nd Cooling Experiment: Technical Preparations
Completed software and hardware preparations for the beam diagnostic systems both on the electron cooler and on the CSRm ion ring.
Upgraded control of the DC gun by grid voltage in both DC and pulsed modes (as short as 100 ns) with the electron peak current ~70 mA. All control hardware are JLab made with PLC and Labview remote controls.
Developed a method to use multiple trigger signals provided by CSR control center to do ion beam injection, acceleration and cooling during synchronization. Labview software have been developed for the data acquisition triggering, signal delay, and data recording, on-line analysis, and post data processing.
Developed a method to measure the electron, ion bunch length by four-electrode BPMs installed in the CSRm ring and in cooler. BPM signal filtering and amplification for the fast oscilloscope data recording, FFT and bench length, charge and peak current measurement by the BPM signals.
Developed a method to measure the ion beam DC current by the IMP DCCT in the CSRm ring and to integrate this signal to the BPM signals by the Labview program in order to confirm the bunched beam rep rate and bunch charges.

## Slide 42: 2nd Cooling Experiment: Technical Preparations
To measure the ion beam DC current by the IMP DCCT in the CSRm ring and to integrate this signal to the BPM signals by the Labview program in order to confirm the bunched beam rep rate and bunch charges.
To measure the ion beam bunch energy spread as the function of the time by the CSRm's longitudinal Schottcky spectrum, using Labview/EPICs program to capture the fast data scans during one fill of beam cycle (~ 1sec time frame). So the beam cooling rate can be measured by fitting this triggered spectrum record data.
To measure the ion beam transverse size as the function of cooling time to capture the ion chamber's beam profile image by the local video camera. The fast CCD and its driver software and data image capture will be done at IMP.
To measure the RF cavity voltage and phase during the ion beam capture, acceleration and cooling times.