## Slide 1: 12 GeV Project Status
12 GeV Project Status
CLAS Collaboration Meeting
Jefferson Lab
June 14, 2017
Glenn R. Young

## Slide 2: 12 GeV Upgrade Project
New Hall
Add arc
Enhanced capabilities
in existing Halls
Add 5 cryomodules
Add 5 cryomodules
20 cryomodules
20 cryomodules
Upgrade arc magnets
and supplies
CHL upgrade
Completion of the
12 GeV CEBAF Upgrade was ranked the highest priority in the 2007 NSAC Long Range Plan.
Upgrade is designed to build on existing facility: vast majority of accelerator and experimental equipment have continued use.
Maintain capability to deliver lower pass beam energies: 2.2, 4.4, 6.6….
Project Scope (~99.7% complete)
Doubling the accelerator beam energy - DONE
New experimental Hall D and beam line - DONE
Civil construction including Utilities - DONE
Upgrades to Experimental Hall C - DONE
Upgrades to Experimental Hall B - ~99.1%
TPC = $338M
ETC = $1.1M

## Slide 3: Physics Progress Overall
Detectors and Electronics - Complete
DAQ/Computing (software/firmware) - Complete
Beamline - Complete
Infrastructure - 99%
  Hall C, D - Complete
  Hall B - Install Solenoid magnet
Magnets – 99%
  Hall C, D – Complete
  Hall B Torus – Complete
  Hall B Solenoid – 94%
Key Performance Parameter Runs – 100%

## Slide 4: Hall C SHMS Magnets All Delivered
D: 31-OCT-2016
Q1: 14-JAN-2015
HB: 6-MAR-2015
Q2: 6-OCT-2016
Q3: 6-DEC-2016
Dipole Rigging
2-NOV-2016
Dipole CCR

## Slide 5: Hall C 12GeV Detectors All Installed
Noble-Gas Cerenkov (NGC)
Drift Chambers
S1XY Hodoscope
Heavy-Gas Cerenkov (HGC)
S2XY Hodoscope
Shower Counter
(within wall)
Pre-Shower Counter

## Slide 6
Hall C KPP Run
HB
Q1
Q3
Q2
D
March 7–10, 2017
Beam
  ~ 5 mA CW
Target
  BeO, Carbon

## Slide 7
Hall C : Detector Performance
Tracking / Event Display
Two perspectives on the same event shown in Hall C event display.
  Red track generated by Wire Chamber data only
  Visual confirmation that the other detector elements along the track do indeed see the same particle
4. Figures demonstrating charged-particle tracks from position-sensitive detectors.
Preshower
S1x
S1y
S2x
S2y
Wire Chambers
Shower
Run 488, Event 16

## Slide 8
Hall C KPP Demonstrated
Detector running for 8 hours recording data from all subsystems.
Screenshots of beam status and/or accelerator e-log entries demonstrating electron beam current and energy.
Data showing relative timing of trigger, tracking, and particle identification in detector subsystems.
Figures demonstrating charged-particle tracks from position-sensitive detectors.
Particle identification plots using signals from calorimetry and Cerenkov detectors.
Accepted by DOE March 14 2017
Detector operational: events recorded with a > 2nA electron beam at > 6 GeV beam energy (3 pass).
KPP Demonstration Criteria:

## Slide 9: Hall B Torus at Full Current 11/4/2016
Installation completed in May 2016
Power tests reached 3770A

## Slide 10
Hall B KPP Configuration
Beamline
CTOF and SVT
Forward Carriage
Tagger Shielding

## Slide 11: Hall B : Reconstructed Particle Trajectories
Target #1
Target #2
<s>=1.2 cm
Two 0.5 mm 12C wires mounted 2.1 cm apart along beamline (Vz)

## Slide 12: HALL B KPP Demonstrated
KPP Demonstration Criteria:
1. Detector running for 8 hours recording data from all subsystems.
2. Screenshots of beam status and/or accelerator e-logs entries demonstrating electron beam current, beam energy, and beam profiles.
3. Plots showing relative timing of calorimetry, time-of-flight, and Cerenkov detectors.
4. Event displays showing correlated particle hits in the forward detectors.
5. Plots of particle trajectories showing target position.
6. Particle identification plots using signals from calorimetry and Cerenkov detectors.
Accepted by DOE February 7 2017
Detector operational: events recorded with a > 2nA electron beam at > 6 GeV beam energy (3 pass).

## Slide 13: DOE OPA Review May 10-11, 2017
Major “annual” review of 12 GeV Project
From the Report of the Review:
  The Installation of all detectors and detector subsystems is complete. Satisfactory operation of all detectors in Halls B, C, and D is confirmed.
  All CD-4b Key Performance Parameters (KPPs) are complete.
  Installation, cool-down, and power-up of all magnets in Halls B, C, and D, with the exception of the Hall B solenoid magnet, is complete. All delivered magnets are operating satisfactorily.
  The Hall B solenoid magnet assembly is continuing at the vendor site.
  The project team completed all activities necessary to support installation, cool-down, and power-up of the Hall B solenoid magnet when it arrives from the vendor.
  However, continued schedule delays with the solenoid magnet vendor have affected schedule contingency to the point that project completion by September 30, 2017 remains uncertain.

## Slide 14: Solenoid Radiation Shield Installed 6/1/2017

## Slide 15: High Level Visitors 6/7/2017

## Slide 16: MultiLayer Insulation Installed 6/9/2017

## Slide 17: Outer Vacuum Cryostat Ends Installed 6/12/2017

## Slide 18: June 2017 Solenoid Cryostat Welding Party

## Slide 19: Solenoid Ready to Ship 6/23/2017

## Slide 20: Loading and Unloading
June 27 2017
ETI
Hall B
ETI
Hall B
6/26/2017
6/28/2017
6/27/2017
6/27/2017

## Slide 21: Solenoid Infrastructure at JLab - Ready
Solenoid Service Tower & U-tubes – Complete
Solenoid I&C Construction – Complete
Solenoid Hall B Infrastructure – Complete
He Vaporizer
Solenoid Stand
Instrumentation and Controls Installed
U-tube
SST Installed
Magnet Power Supply

## Slide 22: Work at JLab after Solenoid Arrival
Arrival Checks
  Receiving inspection (vacuum, electrical, instrument), place on stand
  Remove shipping restraints, survey
Cryogenics SST Attachment
  Place SST, weld SST cryostat bottom plate to solenoid, add lower thermal shield plate, splice power leads, complete piping, add radiation shield and MLI, close cryostat, attach vacuum pumping system
I&C Attachment/Setup
  Add final internal sensors to SST, hook up all cables, hook up main Magnet Power Supply, test all I&C items
Cryogenic Operation Setup
  Leak / Pressure / Reverse Leak checks, add U-tubes, circulate Helium
Pump-down
Cool-down – mid-August, one month
Power test

## Slide 23: Summary
All 12 GeV Project Scope is complete except Solenoid
All 12 GeV Project KPPs Demonstrated
Solenoid Installation in Hall B underway
Physics Division ERRs were held for Solenoid Cool-Down (July 6) and Power-up (July 7)
Plan to complete Solenoid Commissioning by September 30

## Slide 24: Appendix

## Slide 25: Key Activities: Path to CD-4B
  Level 2 Milestones (PEP)
Number | Milestone Description | Baseline | Projected | Actual | Status
2-12 | Hall D Equipment Installation Completed | Sep-14 |  | Oct-14 | CD-4B
2-13 | Hall D Beam Commissioning Completed | Dec-14 |  | Dec-14 | CD-4B
2-27 | Hall C Q1 Magnet Delivered | Oct-14 |  | Jan-15 | CD-4B
2-28 | Hall C HB Magnet Delivered | Mar-15 |  | Mar-15 | CD-4B
2-34 | Hall B Torus Cold Mass Delivered | Apr-15 |  | Apr-15 | CD-4B
2-38 | Conventional Facilities Complete | Dec-15 |  | Nov-15 | CD-4B
2-29 | Hall C Dipole Magnet Delivered | Dec-15 |  | Nov-16 | CD-4B
2-30 | Hall C Q2 Magnet Delivered | Dec-15 |  | Oct-16 | CD-4B
2-31 | Hall C Q3 Magnet Delivered | Mar-16 |  | Nov-16 | CD-4B
2-35 | Hall B Solenoid Cryostated Coil Delivered | Mar-16 |  | Jun-17 | CD-4B
2-32 | Hall C Equipment Installation Complete | Jul-16 |  | Feb-17 | CD-4B
2-33 | Hall C Beam Commissioning Complete | Aug-16 |  | Mar-17 | CD-4B
2-36 | Hall B Equipment Installation Complete | Oct-16 | Sept-17 |  | CD-4B
2-37 | Hall B Beam Commissioning Complete | Dec-16 |  | Feb-17 | CD-4B

## Slide 26
#3: Detector Performance
3. Data showing relative timing of trigger, tracking, and particle identification in detector subsystems.
Time [ns]
PreShower Left Side Timing
HGC Timing
PMT Number
PMT Number
PMT Number
Time [ns]
Time [ns]
Time [ns]
Time [ns]
NGC Timing
Shower Timing
PreShower Right Timing
HGC, NGC Timing
  Horizontal axis is PMT #
Shower Timing
  Horizontal axis is PMT #
Pre-shower Timing
  Horizontal axis is PMT #
PMT Number
PMT Number

## Slide 27
#3: Detector Performance
Wire Drift Chambers
  2 wire drift chambers provide tracks for charged particles
    6 wire planes per chamber
Figure shows time distribution histograms of particles passing by the wires in all 6 planes
  All planes have similar timing structure, minimal background
  All planes have similar counts indicating equal detection efficiencies
3. Data showing relative timing of trigger, tracking, and particle identification in detector subsystems.
Timing relative to Trigger [ns]
Wire Drift Chamber Timing

## Slide 28
Electrons
Hall C : Particle ID
Preshower Energy (arb. units)
NGC Signal (arb. units)
Pions
Preshower Energy (arb. units)
HGC Signal (arb. units)
5. Particle identification plots using signals from calorimetry and Cerenkov detectors.
HGC vs PSh
NGC vs PSh
arb. = arbitrary