## Slide 1: SBS Construction Status
Mark Jones

## Slide 2: Overview
SBS Project focused on equipment for three form factor experiments.
SBS Project Closeout in June 2017.
In “Transition to Operation”, monitoring the SBS Dependencies
SBS weekly meetings. Minutes and talks are available.
SBS Collaboration meeting on Feb 23-24, 2018.
GMN experiment passed its ERR last year.

## Slide 3: Overview of SBS Program
 | Apparatus | Experiment
Projects |  | 
WBS 1 SBSBAS | SBS Magnet with platform and power supply, beamline upgrades. Hall LCW and power upgrades | GEn, GMn , GEp
WBS 2 SBSNFF | Coordinate Detector HCAL trigger Detector frames, Electronics Hut, Lead shielding | GEn, GMn , GEp
WBS 3 SBSPFF | Rear GEM tracker | GEp
SBS dependencies |  | 
 | Front Tracker GEMS | GEn, GMn , GEp
 | Polarized 3He target | GEn
 | Gas Cherenkov (GRINCH) in BigBite | GEn, GMn
 | Hadron Calorimeter (HCAL) | GEn, GMn , GEp
 | Electron calorimeter (ECAL) | GEp
Existing Hall A equipment |  | 
 | BigBite Magnet and Platform , Scintillator Array BigBite PreShower /Shower calorimeter and HRS-Right | GEn, GMn
 | LD2 and LH2 cryotarget | GMn , GEp

## Slide 4: Experimental Layout

## Slide 5: GMN Experimental Layout
Bigbite

## Slide 6: GMN Experimental Layout

## Slide 7: GEp Experimental Layout
Ecal here

## Slide 8: GEp Experimental Layout

## Slide 9: WBS 1 Completed Jan 22, 2016
Target chamber snout
Power Supply
Two plastic analyzers
Saddle coil
Modified 48D48 magnet with racetrack coils.

## Slide 10: WBS 1 Completed Jan 22, 2016
Upstream
Downstream
Corrector magnets
Counterweight on floor plates
Beam pipe
Front clamp

## Slide 11: WBS2 Completed Jan 23rd 2017
Iron shielding
GEM frames and support
Beamline support
Three of the six CDET modules
CDet frame

## Slide 12: WBS3 Completed Feb 1st 2017
Forty modules built!
Ready and waiting to be shipped to JLab cleanroom
Four modules arranged as one chamber
Electronics is being used in X-ray source setup and separate cosmic ray setup

## Slide 13: Transition from construction to commissioning
Work in TestLab (except for GRINCH).

## Slide 14: Transition from construction to commissioning
But in Dec 2017, BigBite moved to ESB with pit stop in Testlab HiBay.

## Slide 15: Updated BigBite Detector Package
Shower
Grinch
GEMs
Pre-shower
Hodoscope
GEM
Approved Frame Modifications

## Slide 16: BigBite Status
Frame in TestLab High Bay.
Modification drawings complete and reviewed with Walter and Jessie.
Walter Kellner & crew will do modifications
New Hodoscope plane built by Glasgow is at JLab
Summer 2018 full integration of BigBite detectors

## Slide 17: Front GEM Tracker
The Italian group has come multiple times to JLab in 2017 to prepare the chambers.

## Slide 18: Front GEM Tracker
Three spare GEM modules under construction in Catania.

## Slide 19: HCal
All modules were constructed by May 2017

## Slide 20: HCal
Need to be assembled into groups of
6x12 modules for final stacking

## Slide 21: Hcal

## Slide 22: HCal

## Slide 23: HCal

## Slide 24: Polarized helium target
Goal is 60cm long cell with metal endcap.

## Slide 25: Polarized target work at UVa
Stage-1
30cm convection target cell
Polarization = 65%
Apparatus to measure k0, needed for polarimetry
Signal to noise in water signal 1-2 orders order magnitude better than previously achieved at UVa

## Slide 26: Polarized Helium target at UVa

## Slide 27: Polarized target design/engineering
Soft-iron box
Beam dump
Incoming beam
BigBite
SBS magnet
Laser optics
Dual optical pumping
Oven with mirrors
Close up view of target oven and 60cm target

## Slide 28: ECal Supermodule
Desired temperature profile is 2250C to 1850C from front to back of leadglass with a drop to 500C at end of light guide.
Close up of cooling region

## Slide 29: ECal Oven Enclosure
Thermal Insulation
Rear Light tight box
Commercial Foam-Glass blocks used as thermal insulation for top, bottom and sides.
Panels attach to frame with light tight gasket around edges of panel

## Slide 30: ECal status
Supermodules parts have start to arrive in December.
Drawings of oven frame and associated parts will be completed by mid February.
Procurement of oven frame by NCCU will follow.