## BCR Form
LCLS-II |  | Baseline Change Request (BCR) |  |  |  | BCR No. |  | LEVEL
[6 empty] | CS-060 |  | 3
ORIGINATOR: | Ed Daly |  | PHONE: | 757-269-7721 |  | DATE: | 2017-08-17
CHANGE TITLE: | LERF as Additional CM Testing Facility | [9 empty] | RQD: A BCR Title title
BCR JUSTIFICATION: | [9 empty] | LCLS.CryoMod-011, LCLS.Cryomod-029
| The current plan is to test cryomodules at each partner lab with no planned re-test. Each lab has one test facility which can accommodate one cryomodule's testing at a time. This BCR adds scope for an additional testing facility at JLAB to allow for more testing cycles and to address potential cryomodule delivery delays associated with unplanned test facility downtime, unplanned re-testing of reworked CMs, and supply chain delays associated with cavity deliveries. | [9 empty] | RQD: The justification needs to clearly state the scope change/adds/removes etc.
COM Types effected by this BCR:
Control Account / Description |  |  | Thru FY 2015 | FY 2016 | FY 2017 | FY 2018 | FY 2019 | FY 2020 | FY 2021 | TOTAL
Current Baseline |  |  | 3649892.8343 | 2693910.0701 | 891609.5321 | 1367374.5203 | 0 | 0 | 0 | 8602786.9568
1.04.06.15 Infrastructure |  |  | 3649892.8343 | 2693910.0701 | 891609.5321 | 1367374.5203 | 0 | 0
Proposed Baseline |  |  | 3649892.8343 | 2693910.0701 | 1002155.2662 | 3883703.2845 | 669391.8997 | 360307.2553 | 0 | 12259360.6101
1.04.06.15 Infrastructure |  |  | 3649892.8343 | 2693910.0701 | 1002155.2662 | 3883703.2845 | 669391.8997 | 360307.2553
Total Increase / (Decrease) to Baseline |  |  | 0 | 0 | 110545.7341 | 2516328.7642 | 669391.8997 | 360307.2553 | 0 | 3656573.6533
Total Increase / (Decrease) to Contingency | [9 empty] | -3656573.6533
Total TPC Change | [9 empty] | 0
WBS/WBS/Milestone Dictionary or Level 1-3 Milestones (any change to Milestone Dates or WBS/Milestone Dictionary):
No milestones will be affected. The WBS dictionary will be changed | [10 empty] | RQD: Please make sure you address Milestone/WBS Dictionary if changes are required
SCHEDULE (any impact on schedule. critical path(s) and adjoining systems?):
No impact to schedule or adjoinimg systems. This BCR adds activities for the described effort. | [10 empty] | RQD: Please indicate if you added new activities/resources as part of BCR and/or what changes were made to the schedule. Unless it was a coding change BCR, then there is no impact to schedule. Another thing to address would be changes to float values
TECHNICAL (any impact on KPP, GRD, PRD Parameters and system capabilities?):
No impact to KPP, GRD, PRD Parameters and system capabilities. | [10 empty] | RQD: Please indicate any technical changes
INTEGRATION (any impact on associated and adjoining systems?)
No impact on associated and adjoining systems. | [10 empty] | RQD: This section should address if this BCR other CA's outside of this BCR's scope and if all impacted CAMs/SMs are aware of this change
Impact of NOT Approving or Delaying Approval of this Request (Alternatives considered and options available):
Third Cryomodule test stand would not be available to mitigate schedule risk | [10 empty] | RQD: If alternatives were considered, please make sure these are addressed here.
Approval Authorizations
|  |  |  | NAME |  | SIGNATURE |  |  | DATE
LEVEL 1
Director, Office of Science | [5 empty] | N/A
LEVEL 2
DOE Federal Project Director /Deputy Federal Project Director |  |  |  | H. Lee/H. Joma |  | N/A
LEVEL 3
Project Director |  |  |  | J.Galayda
LEVEL 4
System Manager
Project Management |  |  |  | M.Reichanadter |  | N/A
Electron Systems |  |  |  | J. Chan |  | N/A
Photon Systems |  |  |  | M. Rowen |  | N/A
Cryo Systems |  |  |  | M.Ross
Conventional Facilities |  |  |  | B. Law |  | N/A
OPC |  |  |  | D.Schultz |  | N/A
CAM
Compliance
Project Controls |  |  |  | J.Chaffin
Finance |  |  |  | J. Cardoso
ES&H
Others:
The approval of this BCR serves as the authorization for work to proceed on the scope identified on this BCR.
OPC
R&D
Preps
Spares
PED
TEC
LLP
Budget/Scope Addition
Budget/Scope Reduction
Budget Transfer
Schedule/Milestone Change
Other
Risk Mitigation -

## Spend by FY
LCLS II Spend Plan by FY at CA Level (impacted CA's only)
Control Account |  | Thru FY 2015 | FY 2016 | FY 2017 | FY 2018 | FY 2019 | FY 2020 | Total
1.04.06.15 Infrastructure
| BCWS | 3649892.8343 | 2693910.0701 | 891609.5321 | 1367374.5203 | 0 | 0 | 8602786.9568
| BCR_IMPA | 3649892.8343 | 2693910.0701 | 1002155.2662 | 3883703.2845 | 669391.8997 | 360307.2553 | 12259360.6101 | 3656573.6533
Grand Total
| BCWS | 3649892.8343 | 2693910.0701 | 891609.5321 | 1367374.5203 | 0 | 0 | 8602786.9568
| BCR_IMPA | 3649892.8343 | 2693910.0701 | 1002155.2662 | 3883703.2845 | 669391.8997 | 360307.2553 | 12259360.6101 | 3656573.6533
[7 empty] | Change to MR: | 3656573.6533
Increase/ (Decrease) to Baseline |  | 0 | 0 | 110545.7341 | 2516328.7642 | 669391.8997 | 360307.2553 | 3656573.6533

## Spend by Month
LCLS II Spend Plan by Month at CA Level (impacted CA's only)
Control Account | Cost Set | 2014-11-30 | 2014-12-31 | 2015-01-31 | 2015-02-28 | 2015-03-31 | 2015-04-30 | 2015-05-31 | 2015-06-30 | 2015-07-31 | 2015-08-31 | 2015-09-30 | 2015-10-31 | 2015-11-30 | 2015-12-31 | 2016-01-31 | 2016-02-29 | 2016-03-31 | 2016-04-30 | 2016-05-31 | 2016-06-30 | 2016-07-31 | 2016-08-31 | 2016-09-30 | 2016-10-31 | 2016-11-30 | 2016-12-31 | 2017-01-31 | 2017-02-28 | 2017-03-31 | 2017-04-30 | 2017-05-31 | 2017-06-30 | 2017-07-31 | 2017-08-31 | 2017-09-30 | 2017-10-31 | 2017-11-30 | 2017-12-31 | 2018-01-31 | 2018-02-28 | 2018-03-31 | 2018-04-30 | 2018-05-31 | 2018-06-30 | 2018-07-31 | 2018-08-31 | 2018-09-30 | 2018-10-31 | 2018-11-30 | 2018-12-31 | 2019-01-31 | 2019-02-28 | 2019-03-31 | 2019-04-30 | 2019-05-31 | 2019-06-30 | 2019-07-31 | 2019-08-31 | 2019-09-30 | 2019-10-31 | 2019-11-30 | 2019-12-31 | 2020-01-31 | Grand Total
1.04.06.15 Infrastructure
| BCWS | 868446.05 | 91026.31 | 119016.9808 | 196650.7307 | 143866.516 | 457209.3178 | 194533.9938 | 398943.405 | 978052.0661 | 170766.2873 | 31381.177 | 45874.0969 | 150471.4459 | 120090.9686 | 23792.0856 | 479245.6642 | 290153.9698 | 1125195.5846 | 74635.4684 | 144941.9649 | 68637.2652 | 165920.4515 | 4951.1045 | 683783.3934 | 22933.4057 | 9321.3198 | 0 | 0 | 30417.5 | 51223.1573 | 51789.033 | 36729.8561 | 5411.8667 | 0 | 0 | 774.5076 | 916.6976 | 845.83 | 1208.3285 | 117960.4285 | 1329.1614 | 1268.745 | 1329.1614 | 1268.745 | 1153262.8757 | 69477.2711 | 17732.7685 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8602786.9569
| BCR_IMPA | 868446.05 | 91026.31 | 119016.9808 | 196650.7307 | 143866.516 | 457209.3178 | 194533.9938 | 398943.405 | 978052.0661 | 170766.2873 | 31381.177 | 45874.0969 | 150471.4459 | 120090.9686 | 23792.0856 | 479245.6642 | 290153.9698 | 1125195.5846 | 74635.4684 | 144941.9649 | 68637.2652 | 165920.4515 | 4951.1045 | 683783.3934 | 22933.4057 | 9321.3198 | 0 | 0 | 30417.5 | 51223.1573 | 51789.033 | 36729.8561 | 5411.8667 | 86538.4758 | 24007.2583 | 107587.0686 | 40843.3374 | 106056.8788 | 617041.3577 | 1002503.8291 | 175898.5386 | 74535.2343 | 5330.3073 | 3893.715 | 1324008.2274 | 291894.0556 | 134110.7346 | 37380.1279 | 4768.5266 | 3337.9686 | 100420.4072 | 80912.2095 | 25114.9797 | 47013.9396 | 106810.4995 | 55362.6735 | 24107.1683 | 92171.6583 | 91991.741 | 79374.6739 | 172840.7412 | 79790.1243 | 28301.716 | 12259360.6102
Grand Total
| BCWS | 868446.05 | 91026.31 | 119016.9808 | 196650.7307 | 143866.516 | 457209.3178 | 194533.9938 | 398943.405 | 978052.0661 | 170766.2873 | 31381.177 | 45874.0969 | 150471.4459 | 120090.9686 | 23792.0856 | 479245.6642 | 290153.9698 | 1125195.5846 | 74635.4684 | 144941.9649 | 68637.2652 | 165920.4515 | 4951.1045 | 683783.3934 | 22933.4057 | 9321.3198 | 0 | 0 | 30417.5 | 51223.1573 | 51789.033 | 36729.8561 | 5411.8667 | 0 | 0 | 774.5076 | 916.6976 | 845.83 | 1208.3285 | 117960.4285 | 1329.1614 | 1268.745 | 1329.1614 | 1268.745 | 1153262.8757 | 69477.2711 | 17732.7685 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8602786.9569
| BCR_IMPA | 868446.05 | 91026.31 | 119016.9808 | 196650.7307 | 143866.516 | 457209.3178 | 194533.9938 | 398943.405 | 978052.0661 | 170766.2873 | 31381.177 | 45874.0969 | 150471.4459 | 120090.9686 | 23792.0856 | 479245.6642 | 290153.9698 | 1125195.5846 | 74635.4684 | 144941.9649 | 68637.2652 | 165920.4515 | 4951.1045 | 683783.3934 | 22933.4057 | 9321.3198 | 0 | 0 | 30417.5 | 51223.1573 | 51789.033 | 36729.8561 | 5411.8667 | 86538.4758 | 24007.2583 | 107587.0686 | 40843.3374 | 106056.8788 | 617041.3577 | 1002503.8291 | 175898.5386 | 74535.2343 | 5330.3073 | 3893.715 | 1324008.2274 | 291894.0556 | 134110.7346 | 37380.1279 | 4768.5266 | 3337.9686 | 100420.4072 | 80912.2095 | 25114.9797 | 47013.9396 | 106810.4995 | 55362.6735 | 24107.1683 | 92171.6583 | 91991.741 | 79374.6739 | 172840.7412 | 79790.1243 | 28301.716 | 12259360.6102
Increase/ (Decrease) to Baseline |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 86538.4758 | 24007.2583 | 106812.561 | 39926.6398 | 105211.0488 | 615833.0292 | 884543.4006 | 174569.3772 | 73266.4893 | 4001.1459 | 2624.97 | 170745.3517 | 222416.7845 | 116377.9661 | 37380.1279 | 4768.5266 | 3337.9686 | 100420.4072 | 80912.2095 | 25114.9797 | 47013.9396 | 106810.4995 | 55362.6735 | 24107.1683 | 92171.6583 | 91991.741 | 79374.6739 | 172840.7412 | 79790.1243 | 28301.716 | 3656573.6533