## Sheet1
Cryoplant Commissioning Documentation Matrix
Gas Management System
|  | Operating and Maintenance Manual | Commissioning Readiness Checks |  | Power ON Procedure | Operational Procedures* | Acceptance
|  | (From Vendor for Large Items) | Engineering - Aspect Chekclist | Installation - Aspect | (Checks/ LOTO)
1 | MCC's | Vendor | JLab | SLAC | SLAC | SLAC | Vendor
2 | Main Compressor System (Interconnects) | NA | JLab | SLAC | NA | Jlab with mods | Jlab
2.1 | LP Compressor Skids | Vendor | JLab | SLAC | Jlab with mods | Jlab with mods | Vendor w Jlab tailoring
2.2 | MP Compressor Skids | Vendor | JLab | SLAC | Jlab with mods | Jlab with mods | Vendor w Jlab tailoring
2.3 | HP Compressor Skids | Vendor | JLab | SLAC | Jlab with mods | Jlab with mods | Vendor w Jlab tailoring
3 | Oil Removal System | NA | JLab | SLAC | Vendor thru Jlab | Vendor thru Jlab | Jlab
4 | Gas Analyzer | Vendor | JLab | SLAC | Vendor | Jlab with mods | Jlab | Error in Counting
5 | Cooling Water System for Warm Compressors | SLAC | JLab | SLAC | SLAC | SLAC | Jlab | Total | SLAC | JLAB | Vendor
6 | Cooling Water for Turbines & CC | Vendor | JLab | SLAC | Jlab with mods | Jlab with mods | Jlab | 49 | 13 | 27 | 9
7 | Instrument Air System (compressor, dryer, receiver) | Vendor | JLab | SLAC | SLAC | SLAC | Jlab
Utility System
8 | Oil Processor Skid | Vendor | JLab | Vendor | Vendor | Vendor | Jlab
9 | UPS Systems | SLAC | SLAC | SLAC | SLAC | SLAC | Jlab
10 | Emergency Generator | SLAC | SLAC | SLAC | SLAC | SLAC | Jlab
11 | Helium Gas Storage | Vendor | JLab | Vendor | Jlab new for initial operations | Jlab new for initial operations | Jlab
12 | Helium Gas Distribution | Vendor | JLab | Vendor |  |  | Jlab
13 | Helium Recovery System | Vendor | JLab | Vendor | Jlab new for initial operations | Jlab new for initial operations | Jlab
14 | Purifier | Vendor | JLab | Vendor | Vendor | Vendor | Jlab
15 | Recovery Compressor | Vendor | JLab | SLAC | Jlab with mods | Jlab with mods | Jlab
16 | Interface Box | Vendor | JLab | SLAC | Jlab new | Jlab new | Jlab
17 | Instrument Air Distribution | See Instr Air Above | JLab | See Instr Air Above | See Instr Air Above | See Instr Air Above | See above
18 | LN2/GN2 Distribution | Vendor | JLab | SLAC | SLAC | SLAC | NA | Error in Counting
19 | LN2 Dewar | Vendor | JLab | Vendor | Vendor tailored by Jlab | Vendor tailored by Jlab | Jlab | Total | SLAC | JLAB | Vendor
20 | Guard Vacuum System | Vendor | JLab | SLAC | Jlab with mods | Jlab with mods | Jlab | 76 | 25 | 30 | 21
21 | He Gas Delivery | SLAC | SLAC | SLAC | SLAC | SLAC | SLAC
22 | LN2 Delivery | SLAC | SLAC | SLAC | SLAC | SLAC | SLAC
4.5 K Cold Box
23 | 4.5 K Cold Box | Vendor |  | Vendor | Vendor w Jlab tailoring | Vendor w Jlab tailoring | Jlab | Error in Counting
23.1 | Turbines | Vendor |  | Vendor | Vendor w Jlab tailoring | Vendor w Jlab tailoring | Jlab | Total | SLAC | JLAB | Vendor
24 | LHe Dewar | Vendor |  | SLAC | Jlab new | Jlab new | Jlab | 15 | 0 | 10 | 5
2 K Cold Box | [7 empty] | Error in Counting
25 | 2 K Cold Box | Vendor |  | SLAC | Vendor with Jlab mods | Jlab with mods | Jlab | Total | SLAC | JLAB | Vendor
25.1 | CC1 to CC6 | Vendor |  | Vendor | Vendor | Vendor | Jlab | 10 | 0 | 5 | 5
|  | In-Work | [5 empty] | Error in Counting
|  | Complete | [5 empty] | Total | SLAC | JLAB | Vendor
| * | Under Review | [5 empty] | 150 | 38 | 72 | 40
Notes:
All Vendor supplied data will be checked
Pressure systems maintenance activities are assumed to be SLAC responsibilities for specification of intervals of inspection and testing.
The assumption is that the Operational Procedure is the Training Document.
Documentation for follow-on training of new SLAC staff is the responsibility of SLAC
Note on H9: Author: Referring to 79120-S002, this is Vendor provided document
Note on H10: Author: Referring to 79120-S002, this is Vendor provided document
Note on H11: Author: Referring to 79120-S002, this is Vendor provided document