## CP1
CP1 Commissioning Plan - Overarching Schedule | [61 empty] | SLAC Plan
|  | Timeline | 2019 | [50 empty] | 2020 | [7 empty] | 2019-01-01 | 6
|  |  | 2019-01-14 |  |  | 2019-02-01 |  |  |  | 2019-03-01 |  |  |  | 2019-04-01 |  |  |  | 2019-05-01 |  |  |  |  | 2019-06-01 |  |  |  | 2019-07-01 |  |  |  |  | 2019-08-01 |  |  |  | 2019-09-01 |  |  |  | 2019-10-01 |  |  |  |  | 2019-11-01 |  |  |  | 2019-12-01 |  |  |  |  | 2020-01-01 |  |  |  |  | 2020-02-01 |  |  | 2019-03-01 | 7
Mains | Sub-Systems | Resource | W1 | W2 | W3 | W4 | W5 | W6 | W7 | W8 | W9 | W10 | W11 | W12 | W13 | W14 | W15 | W16 | W17 | W18 | W19 | W20 | W21 | W22 | W23 | W24 | W25 | W26 | W27 | W28 | W29 | W30 | W31 | W32 | W33 | W34 | W35 | W36 | W37 | W38 | W39 | W40 | W41 | W42 | W43 | W44 | W45 | W46 | W47 | W48 | W49 | W50 | W51 | W52 | W53 | W54 | W55 | W56 | W57 |  |  | 2019-06-01 | 8
Pre-comm |  | S1 | [59 empty] | 2019-08-01 | 9
Aux Comm | [7 empty] | W1 | W2 | W3 | W4 | W5 | W6 | W7 | W8 | W9 | W10 | W11 | W12 | W13 |  | Auxiliaries Acceptance | [39 empty] | 2020-06-01 | 13
He Comp | [13 empty] | W1 | W2 | W3 | W4 | W5 | W6 | W7 | W8 | W9 | W10 | W11 | W12 | W13 | W14 | W15 | W16 | W17 | W18 | W19 | W20 |  | Helium Compression Acceptance
4 K CB | [28 empty] | W1 | W2 | W3 | W4 | W5 | W6 | W7 | W8 | W9 | W10 | W11 | W12 | W13 | W14 | W15 | W16 | W17 | W18 |  | 4.5 K Acceptance
2 K CB | [48 empty] | W1 | W2 | W3 | W4 | W5 | W6 | W7 | W8 | W9 | W10 | W11 |  | 2.0 K Cold Box Acceptance
| Resources | Weeks | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 53 | 54 | 55 | 56 | 57 | 58
|  | Coordinations | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
|  | S1 | 1 | 2 | 3 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 3 | 2 | 1
|  | S2 | [5 empty] | 2 | 2 | 2 | 2 | [5 empty] | 2 | 2 | 2 | 2 | 2 | 2 | 2 |  | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 |  |  |  |  | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 |  |  |  |  | 2 | 2 | 2 | 2 | 2 | 2 | 2
|  | S3 | [5 empty] | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 |  | 2 |  |  | 2 | 2 |  | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | [5 empty] | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 |  |  |  |  | 2 | 2 | 2 | 2 | 2 | 2 | 2
|  | S4 | [11 empty] | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 |  |  |  | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 |  |  | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 |  | 2 | 2 | 2 |  | 2 | 2 | 2 | 2 | 2 | 2 | 2
|  | S5 | 33: 2; 34: 2; 35: 2; 36: 2; 37: 2; 38: 2; 39: 2; 40: 2; 41: 2; 42: 2; 43: 2; 44: 2; 45: 2; W3 49: 2; W4 50: 2; W5 51: 2; W6 52: 2; W7 53: 2; W8 54: 2; W9 55: 2; W10 56: 2; W11 57: 2
SME | bar: 37 to 44; W5 51 to W11 57
VENDOR | bar: 21 to 22; 38 to 44; W7 53 to W11 57
Installation | bar: 23; 46
|  | Total | 3 | 4 | 5 | 6 | 6 | 10 | 10 | 10 | 10 | 8 | 8 | 10 | 10 | 10 | 12 | 12 | 10 | 12 | 10 | 10 | 12 | 10 | 10 | 10 | 10 | 10 | 12 | 12 | 12 | 12 | 12 | 10 | 10 | 10 | 8 | 7 | 13 | 12 | 11 | 11 | 11 | 11 | 11 | 11 | 10 | 6 | 4 | 4 | 6 | 4 | 11 | 11 | 11 | 11 | 11 | 11 | 11
|  |  | S1 |  |  |  | S2 | S3 | S4 | S5
Ops | bar: 5 to 8
Tech | bar: 1 to 8
|  | Lead | 1: 2
|  | ME | 1: 3
EE | bar: 1
|  | MT | 1: 4
|  | ET | 1: 4
SME | bar: 1
Vendor | bar: 1
Installation | bar: 1
|  | Total | 1: 14

## CP1 + CP2
CP Commissioning Plan - Resource Loaded Schedule
|  |  | Timeline | 2019 | [50 empty] | 2020
|  |  |  | 2019-01-14 |  |  | 2019-02-01 |  |  |  | 2019-03-01 |  |  |  | 2019-04-01 |  |  |  | 2019-05-01 |  |  |  |  | 2019-06-01 |  |  |  | 2019-07-01 |  |  |  |  | 2019-08-01 |  |  |  | 2019-09-01 |  |  |  | 2019-10-01 |  |  |  |  | 2019-11-01 |  |  |  | 2019-12-01 |  |  |  |  | 2020-01-01 |  |  |  |  | 2020-02-01 |  |  |  | 2020-03-01 |  |  |  | 2020-04-01 |  |  |  |  | 2020-05-01 |  |  |  | 2020-06-01
Mains |  | Sub-Systems | Resource | W1 | W2 | W3 | W4 | W5 | W6 | W7 | W8 | W9 | W10 | W11 | W12 | W13 | W14 | W15 | W16 | W17 | W18 | W19 | W20 | W21 | W22 | W23 | W24 | W25 | W26 | W27 | W28 | W29 | W30 | W31 | W32 | W33 | W34 | W35 | W36 | W37 | W38 | W39 | W40 | W41 | W42 | W43 | W44 | W45 | W46 | W47 | W48 | W49 | W50 | W51 | W52 | W53 | W54 | W55 | W56 | W57
Pre-COMM - Facility |  | Electrical Checks | S1 | A1 | A2 | A3 | A4 | A5 | A6 | A7 | B1 | B2 | B3 | B3 | B4 | B5 | B5 | B6 | B7 | C1 | C2 | C3 | C4 | C5 | C5 | C5 | C6 | C6 | C6 | C7 | C8 | D1 | D2 | D3 | D4 | D6 | D7 | D8
|  | Instrumentation & Control Checks | S1 |  | A1 | A2 | A3 | A4 | A5 | A6 | A7 | B1 | B2 | B3 | B3 | B4 | B5 | B5 | B6 | B7 | C1 | C2 | C3 | C4 | C5 | C5 | C5 | C6 | C6 | C6 | C7 | C8 | D1 | D2 | D3 | D4 | D6 | D7 | D8
|  | Mechanical Checks | S1 |  |  | A1 | A2 | A3 | A4 | A5 | A6 | A7 | B1 | B2 | B3 | B3 | B4 | B5 | B5 | B6 | B7 | C1 | C2 | C3 | C4 | C5 | C5 | C5 | C6 | C6 | C6 | C7 | C8 | D1 | D2 | D3 | D4 | D6 | D7 | D8
|  | System Clean-up + Leak Checks | S1 |  |  |  | A1 | A2 | A3 | A4 | A5 | A6 | A7 | B1 | B2 | B3 | B3 | B4 | B5 | B5 | B6 | B7 | C1 | C2 | C3 | C4 | C5 | C5 | C5 | C6 | C6 | C6 | C7 | C8 | D1 | D2 | D3 | D4 | D6 | D7 | D8
[9 empty] | W1 | W2 | W3 | W4 | W5 | W6 | W7 | W8 | W9 | W10 | W11 | W12 | W13
A. Auxiliaries COMM | A1 | Nitrogen System (Tank + Distri) | S2 | [19 empty] | Auxiliaries Acceptance | bar: A5 A4 A3 W1 to B1 A7 A6 W4
| A2 | Air Compressor | S3 | [32 empty] | Helium Compression Acceptance | [41 empty] | SLAC Plan | bar: A5 A4 A3 W1
| A3 | Cooling Water System (79621-0000) | S3 | [45 empty] | 4.5 K Acceptance | [28 empty] | 2019-01-01 | 7 | 5 | bar: A6 A5 A4 W2
| A4 | Recovery Compressor | S3 | [51 empty] | 2.0 K Cold Box Acceptance | [22 empty] | 2019-03-01 | 8 | 14 | 6 | bar: A7 A6 A5 W3 to B1 A7 A6 W4
| A5 | Gas Analyzers | S3 | [74 empty] | 2019-06-01 | 9 | 16 | 7 | bar: B2 B1 A7 W5
| A6 | Helium Purifier | S3 | [74 empty] | 2019-08-01 | 10 | 18 | 8 | bar: B3 B2 B1 W6 to B6 B5 B5 W11
| A7 | Helium Gas Storage Tank | S2 +S3 | [74 empty] | 2019-10-01 | 11 | 11 | 0 | bar: B5 B5 B4 W10 to C1 B7 B6 W13
[15 empty] | W1 | W2 | W3 | W4 | W5 | W6 | W7 | W8 | W9 | W10 | W11 | W12 | W13 | W14 | W15 | W16 | W17 | W18 | W19 | W20 | [43 empty] | 2019-12-01 | 12 | 12 | 0
B. Helium Compression | B1 | Adsorbers | S4 | [74 empty] | 2020-03-01 | 12 | 12 | 0 | bar: W1 to S3 W12
| B2 | Oil Processor | S2 | [74 empty] | 2020-06-01 | 13 | 11 | -2 | bar: S3 W7 to S3 W10
| B3 | Motor Control Center | S3 + V | [74 empty] | 2020-12-01 | 13 | 11 | -2 | bar: S3 W10 to S3 W11
| B4 | Filling of Oil & Helium | S2 + I/V | bar: S3 W12
| B5 | Helium Compressor | S2+S3 | [11 empty] | S3 W13: S2 + S3 | [44 empty] | S1 and S6 |  |  |  | S2 | S3 | S4 | S5
| B6 | Oil Removal System | S2+S3 | [11 empty] | S3 W17: S2 + S3 | [43 empty] | Ops |  |  |  |  | ME | ME | ME | EE
| B7 | Oil Management System | S2+S3 | [11 empty] | S3 W19: S2 + S3 | [43 empty] | Tech | ET | ET | MT | MT | MT | ET | MT | ET
[30 empty] | W1 | W2 | W3 | W4 | W5 | W6 | W7 | W8 | W9 | W10 | W11 | W12 | W13 | W14 | W15 | W16 | W17 | W18 | [31 empty] | ET | ET | MT | MT | ET | MT | MT
C. 4.5 K Cold Box | C1 | Adsorbers | S4 | [74 empty] | On-Call | [8 empty] | 3 | bar: W1 to S2 + S3 W6
| C2 | Secondary Cooling Water Loop | S2 | [74 empty] | Installation | bar: S2 + S3 W6
| C3 | Insulation Vacuum System | S4 | [74 empty] | Vendor | bar: S2 + S3 W7 to S2 + S3 W8
| C4 | Helium Filling and Cleanup | S5 | [74 empty] | JLAB | [9 empty] | 3 | bar: S2 + S3 W7 to S2 + S3 W10
| C5 | UCB - Heat Exchangers | S2+S3+ S4 +S5 | [26 empty] | S2 + S3 W11: S2+S3+S4+S5 | [30 empty] | Total
| C6 | LCB - Heat Exchangers & Turbines | S2+S3+ S4 +S5 | [26 empty] | S2 + S3 W11: S2+S3+S4+S5
| C7 | Liquid Helium Dewar - 10 kL | S2+S3+ S4 +S5 | [26 empty] | S2 + S3 W11: S2+S3+S4+S5
| C8 | Test Heaters & Performance Test | S2+S3+ S4 +S5 | [26 empty] | S2 + S3 W14: S2+S3+S4+S5 | [30 empty] | Lead | 2
| C9 | Warmup and U-Tube Operation | S2+S3+S4+S5+I | [44 empty] | S2+S3+S4+S5+I | [29 empty] | ME | 3
[50 empty] | W1 | W2 | W3 | W4 | W5 | W6 | W7 | W8 | W9 | W10 | W11 | W12 | W13 | W14 | W15 | W16 | W17 | W18 | [10 empty] | EE | 1
D. 2.0 K Cold Box + Interface | D1 | Helium Filling and Cleanup | S4 | [74 empty] | MT | 8 | bar: W1 to W2
| D2 | Test Heater | S5 | [74 empty] | ET | 7 | bar: W3
| D3 | Insulation Vacuum System | S4 | [74 empty] | SME | Y | bar: W3 to W4
| D4 | Guard Vacuum | S5 | [74 empty] | Vendor | Y | bar: W4
| D5 | Cooldown to 4.5 K | S2+S3+ S4 +S5 | [46 empty] | W12: S2+S3+S4+S5 | [10 empty] | Installation | Y
| D6 | Magnetic Bearing Tuning | S2+S3+ S4 +S5 | [46 empty] | W14: S2+S3+S4+S5 | [10 empty] | Total | 21
| D7 | Cold Compressor + 2 K CB | S2+S3+ S4 +S5 | [46 empty] | W16: S2+S3+S4+S5
| D8 | Interface - CAN A | S2+S3+ S4 +S5 | [46 empty] | W18: S2+S3+S4+S5
|  | Resources | Weeks | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 53 | 54 | 55 | 56 | 57 | 58 | 59 | 60 | 61 | 62 | 63 | 64
|  |  | Coordinations | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | [7 empty] | 2 | 2 | 2 | 2 | 2 | 2 | 2
|  |  | S1 | 1: 1; 2: 2; 3: 3; 4: 4; 5: 4; 6: 4; 7: 4; 8: 4; 9: 4; 10: 4; 11: 4; 12: 4; 13: 4; 14: 4; 15: 4; 16: 4; 17: 4; 18: 4; 19: 4; 20: 4; 21: 4; 22: 4; 23: 4; 24: 4; 25: 4; 26: 4; 27: 4; 28: 4; 29: 4; 30: 4; 31: 4; 32: 4; 33: 4; 34: 4; 35: 4; 36: 3; 37: 2; 38: 1
|  |  | S2 | 6: 2; 7: 2; 8: 2; 9: 2; 15: 2; 16: 2; 17: 2; 18: 2; 19: 2; 20: 2; 21: 2; 23: 2; 24: 2; 25: 2; 26: 2; 27: 2; 28: 2; 29: 2; 30: 2; 31: 2; 32: 2; 37: 2; 38: 2; 39: 2; 40: 2; 41: 2; 42: 2; 43: 2; 44: 2; 45: 2; 46: 2; 58: 2; 59: 2; 60: 2; 61: 2; 62: 2; 63: 2; S2+S3+S4+S5 64: 2
|  |  | S3 | [5 empty] | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 |  | 2 |  |  | 2 | 2 |  | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | [5 empty] | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | [11 empty] | 2 | 2 | 2 | 2 | 2 | 2 | 2
|  |  | S4 | [11 empty] | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 |  |  |  | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 |  |  | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 |  | 2 | 1 | 1 | [8 empty] | 2 | 2 | 2 | 2 | 2 | 2 | 2
|  |  | S5 | 33: 2; 34: 2; 35: 2; 36: 2; 37: 2; 38: 2; 39: 2; 40: 2; 41: 2; 42: 2; 43: 2; 44: 2; 45: 2; 49: 1; 50: 1; 58: 2; 59: 2; 60: 2; 61: 2; 62: 2; 63: 2; S2+S3+S4+S5 64: 2
SME | bar: 37 to 44; 58 to S2+S3+S4+S5 64
VENDOR | bar: 21 to 22; 38 to 44; 60 to S2+S3+S4+S5 64
Installation | bar: 23; 46
|  |  | CP1 Total | 3 | 4 | 5 | 6 | 6 | 10 | 10 | 10 | 10 | 8 | 8 | 10 | 10 | 10 | 12 | 12 | 10 | 12 | 10 | 10 | 12 | 10 | 10 | 10 | 10 | 10 | 12 | 12 | 12 | 12 | 12 | 10 | 10 | 10 | 8 | 7 | 13 | 12 | 11 | 11 | 11 | 11 | 11 | 11 | 10 | 6 | 4 | 3 | 4 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11 | 11 | 11 | 11 | 11 | 11 | 11
Timeline in Weeks
|  |  | Resource |  |  |  |  | W1 | W2 | W3 | W4 | W5 | W6 | W7 | W8 | W9 | W10 | W11 | W12 | W13 | W14 | W15 | W16 | W17 | W18 | W19 | W20 | W21 | W22 | W23 | W24 | W25 | W26 | W27 | W28 | W29 | W30 | W31 | W32 | W33 | W34 | W35 | W36 | W37 | W38 | W39 | W40 | W41 | W42 | W43 | W44 | W45 | W46 | W47 | W48 | W49 | W50 | W51
Pre-COMM - Facility |  | Electrical Checks | S6 |  |  |  |  | A1 | A2 | A3 | A4 | A5 | B1 | B2 | B2 | B3 | B4 | B4 | B5 | C1 | C2 | C3 | C4 | C5 | C5 | C5 | C6 | C6 | C6 | C7 | C8 | D1 | D2 | D3 | D4 | D6 | D7 | D8
|  | Instrumentation & Control Checks | S6 | [5 empty] | A1 | A2 | A3 | A4 | A5 | B1 | B2 | B2 | B3 | B4 | B4 | B5 | C1 | C2 | C3 | C4 | C5 | C5 | C5 | C6 | C6 | C6 | C7 | C8 | D1 | D2 | D3 | D4 | D6 | D7 | D8
|  | Mechanical Checks | S6 | [6 empty] | A1 | A2 | A3 | A4 | A5 | B1 | B2 | B2 | B3 | B4 | B4 | B5 | C1 | C2 | C3 | C4 | C5 | C5 | C5 | C6 | C6 | C6 | C7 | C8 | D1 | D2 | D3 | D4 | D6 | D7 | D8
|  | System Clean-up + Leak Checks | S6 | [7 empty] | A1 | A2 | A3 | A4 | A5 | B1 | B2 | B2 | B3 | B4 | B4 | B5 | C1 | C2 | C3 | C4 | C5 | C5 | C5 | C6 | C6 | C6 | C7 | C8 | D1 | D2 | D3 | D4 | D6 | D7 | D8
[13 empty] | W1 | W2 | W3 | W4 | W5
A. Auxiliaries COMM | A1 | Nitrogen System (Tank) | S2 |  |  |  |  | W6: S2; W12: Auxiliaries Acceptance
| A2 | Air Compressor | S3 |  |  |  |  | W6: S3; W27: Helium Compression Acceptance
| A3 | Cooling Water System (79621-0000) | S3 |  |  |  |  | W7: S3; W46: 4.5 K Acceptance
| A4 | Gas Analyzers | S3 | bar: W8
| A5 | Helium Gas Storage Tank | S3 |  |  |  |  | W9: S3; W47: 2.0 K Cold Box Acceptance
[16 empty] | W1 | W2 | W3 | W4 | W5 | W6 | W7 | W8 | W9 | W10 | W11 | W12 | W13 | W14 | W15 | W16 | W17 | W18 | W19 | W20
B. Helium Compression | B1 | Adsorbers | S4 | bar: S3 W1 to S3 W12
| B2 | Motor Control Center | S3 | bar: S3 W10 to S3 W11
| B3 | Filling of Oil & Helium | S2+I/V | bar: S3 W12
| B4 | Helium Compressor | S2+S3 | [12 empty] | S3 W17: S2+S3
| B5 | Oil Removal System | S2+S3 | [32 empty] | S2+S3
[35 empty] | W1 | W2 | W3 | W4 | W5 | W6 | W7 | W8 | W9 | W10 | W11 | W12 | W13 | W14 | W15 | W16 | W17 | W18
C. 4.5 K Cold Box | C1 | Adsorbers | S4 | bar: W1 to S2+S3 W6
| C2 | Secondary Cooling Water Loop | S2 | bar: S2+S3 W6
| C3 | Insulation Vacuum System | S2 | bar: S2+S3 W7 to S2+S3 W8
| C4 | Helium Filling and Cleanup | S3 | bar: S2+S3 W7 to S2+S3 W10
| C5 | UCB - Heat Exchangers | S2+S3+S4+S5 | [31 empty] | S2+S3 W17: S2+S3+S4+S5
| C6 | LCB - Heat Exchangers & Turbines | S2+S3+S4+S5 | [31 empty] | S2+S3 W17: S2+S3+S4+S5
| C7 | Liquid Helium Dewar - 10 kL | S2+S3+S4+S5 | [31 empty] | S2+S3 W17: S2+S3+S4+S5
| C8 | Test Heaters & Performance Test | S2+S3+S4+S5 | [50 empty] | S2+S3+S4+S5
| C9 | Warmup and U-Tube Operation | S2+S3+S4+S5+I | [55 empty] | S2+S3+S4+S5+I
[61 empty] | W1 | W2 | W3 | W4 | W5 | W6 | W7 | W8 | W9 | W10 | W11
D. 2.0 K Cold Box + Interface | D1 | Helium Filling and Cleanup | S2 | bar: W1 to W2
| D2 | Test Heater | S3 | bar: W3
| D3 | Insulation Vacuum System | S2 | bar: W3 to W4
| D4 | Guard Vacuum | S3 | bar: W4
| D5 | Cooldown to 4.5 K | S2+S3+S4+S5 | [57 empty] | W9: S2+S3+S4+S5
| D6 | Magnetic Bearing Tuning | S2+S3+S4+S5 | [57 empty] | W11: S2+S3+S4+S5
| D7 | Cold Compressor + 2 K CB | S2+S3+S4+S5 | [69 empty] | S2+S3+S4+S5
| D8 | Interface - CAN A | S2+S3+S4+S5 | [71 empty] | S2+S3+S4+S5
|  | Resources | Weeks |  |  |  |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 53 | 54 | 55 | 56 | 57 | 58 | 59 | 60 | 61 | 62 | 63 | 64 | 65 | 66 | 67 | 68 | 69 | 70
|  |  | Coordinations |  |  |  |  | 47: 2; 48: 2; 49: 2; 50: 2; 51: 2; 52: 2; 53: 2; 62: 2; 63: 2; 64: 2; 65: 2; 66: 2; 67: 2; S2+S3+S4+S5 68: 2
|  |  | S1 |  |  |  |  | 1: 1; 2: 2; 3: 3; 4: 4; 5: 4; 6: 4; 7: 4; 8: 4; 9: 4; 10: 4; 11: 4; 12: 4; 13: 4; 14: 4; 15: 4; 16: 4; 17: 4; 18: 4; 19: 4; 20: 4; 21: 4; 22: 4; 23: 4; 24: 4; 25: 4; 26: 4; 27: 4; 28: 4; 29: 4; 30: 4; 31: 4; 32: 3; 33: 2; 34: 1
|  |  | S2 |  |  |  |  | 6: 1; 7: 1; 8: 1; 9: 1; 20: 1; 25: 1; 26: 1; 27: 1; 28: 1; 29: 1; 30: 1; 31: 1; 32: 1; 33: 1; 34: 1; 35: 1; 44: 2; 45: 2; 46: 2; 47: 2; 48: 2; 49: 2; 50: 2; 51: 2; 52: 2; 53: 2; 54: 1; 55: 1; 56: 1; 57: 1; 62: 2; 63: 2; 64: 2; 65: 2; 66: 2; 67: 2; S2+S3+S4+S5 68: 2
|  |  | S3 |  |  |  |  | 6: 1; 7: 1; 8: 1; 9: 1; 10: 1; 18: 1; 19: 1; 25: 1; 26: 1; 27: 1; 28: 1; 29: 1; 30: 1; 31: 1; 32: 1; 34: 1; 35: 1; 36: 1; 37: 1; 44: 2; 45: 2; 46: 2; 47: 2; 48: 2; 49: 2; 50: 2; 51: 2; 52: 2; 53: 2; 56: 1; 57: 1; 62: 2; 63: 2; 64: 2; 65: 2; 66: 2; 67: 2; S2+S3+S4+S5 68: 2
|  |  | S4 |  |  |  |  | 9: 1; 10: 1; 11: 1; 12: 1; 13: 1; 14: 1; 15: 1; 16: 1; 17: 1; 18: 1; 19: 1; 28: 1; 29: 1; 30: 1; 31: 1; 32: 1; 33: 1; 44: 2; 45: 2; 46: 2; 47: 2; 48: 2; 49: 2; 50: 2; 51: 2; 52: 2; 53: 2; 62: 2; 63: 2; 64: 2; 65: 2; 66: 2; 67: 2; S2+S3+S4+S5 68: 2
|  |  | S5 |  |  |  |  | 44: 2; 45: 2; 46: 2; 47: 2; 48: 2; 49: 2; 50: 2; 51: 2; 52: 2; 53: 2; 62: 2; 63: 2; 64: 2; 65: 2; 66: 2; 67: 2; S2+S3+S4+S5 68: 2
SME | bar: 44 to 53; 62 to S2+S3+S4+S5 68
VENDOR | bar: 18 to 19; 45 to 51; 64 to S2+S3+S4+S5 68
Installation | bar: 20; 53
|  |  | CP2 Total |  |  |  |  | 1 | 2 | 3 | 4 | 4 | 6 | 6 | 6 | 7 | 6 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 6 | 6 | 5 | 4 | 4 | 4 | 4 | 6 | 6 | 6 | 7 | 7 | 7 | 7 | 6 | 4 | 3 | 2 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 9 | 9 | 9 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 1 | 1 | 2 | 2 | 0 | 0 | 0 | 0 | 11 | 11 | 11 | 11 | 11 | 11 | 11
|  | CP1 & CP2 Total | CP1 + CP2 | 3 | 4 | 5 | 6 | 7 | 12 | 13 | 14 | 14 | 14 | 14 | 16 | 17 | 16 | 17 | 17 | 15 | 17 | 15 | 15 | 17 | 16 | 16 | 15 | 14 | 14 | 16 | 16 | 18 | 18 | 18 | 17 | 17 | 17 | 15 | 13 | 17 | 15 | 13 | 12 | 12 | 11 | 11 | 11 | 10 | 6 | 4 | 12 | 13 | 12 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 12 | 12 | 13 | 13 | 11 | 11 | 11 | 0 | 11 | 11 | 11 | 11 | 11 | 11 | 11
[6 empty] | Jan |  | 3: Feb; 7: Mar; 11: Apr; 16: May; 20: Jun; 25: Jul; 29: Aug; 33: Sep; 38: Oct; 42: Nov; 47: Dec; 52: Jan; 56: Feb; 60: Mar; 65: Apr
[6 empty] | 5 |  | 3: 13; 7: 14; 11: 17; 16: 15; 20: 15; 25: 18; 29: 17; 33: 17; 38: 11; 42: 6; 47: 11; 52: 11; 56: 13; 60: 11; 65: 11
|  |  |  | S1 and S6 |  |  |  | 1: S2; 2: S3; 3: S4; 4: S5
Ops | bar: 1 to 4
|  |  | Tech | ET | ET | MT | MT | bar: 1 to 4
|  |  |  | ET | ET | MT | MT | bar: 1 to 3
|  |  | On-Call |  |  |  |  | 5: 3
Installation
Vendor
|  |  | JLAB |  |  |  |  | 6: 3
Total
|  |  | Lead | 2
|  |  | ME | 3
|  |  | EE | 1
|  |  | MT | 8
|  |  | ET | 7
|  |  | SME | Y
|  |  | Vendor | Y
|  |  | Installation | Y
|  |  | Total | 21

## CP2
CP2 Commissioning Plan - Overarching Schedule
Timeline in Weeks
|  | Resource | W1 | W2 | W3 | W4 | W5 | W6 | W7 | W8 | W9 | W10 | W11 | W12 | W13 | W14 | W15 | W16 | W17 | W18 | W19 | W20 | W21 | W22 | W23 | W24 | W25 | W26 | W27 | W28 | W29 | W30 | W31 | W32 | W33 | W34 | W35 | W36 | W37 | W38 | W39 | W40 | W41 | W42 | W43 | W44 | W45 | W46 | W47 | W48 | W49 | W50 | W51
Pre-Comm | Electrical Checks | S1
Aux Comm |  |  | Timeline in Weeks W6: W1; Timeline in Weeks W7: W2; Timeline in Weeks W8: W3; Timeline in Weeks W9: W4; Timeline in Weeks W10: W5; Timeline in Weeks W12: Auxiliaries Acceptance
He Comp | [7 empty] | W1 | W2 | W3 | W4 | W5 | W6 | W7 | W8 | W9 | W10 | W11 | W12 | W13 | W14 | W15 | W16 | W17 | W18 | W19 | W20 |  | Helium Compression Acceptance
4 K CB | [22 empty] | W1 | W2 | W3 | W4 | W5 | W6 | W7 | W8 | W9 | W10 | W11 | W12 | W13 | W14 | W15 | W16 | W17 | W18 |  | 4.5 K Acceptance
2 K CB | [42 empty] | W1 | W2 | W3 | W4 | W5 | W6 | W7 | W8 | W9 | W10 | W11 | 2.0 K Cold Box Acceptance
|  | Weeks | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51
|  | Coordinations | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
|  | S1 | 1 | 2 | 3 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 3 | 2 | 1
|  | S2 | 6: 2; 7: 2; 8: 2; 9: 2; 17: 2; 18: 2; 19: 2; 20: 2; 21: 2; 22: 2; 23: 2; 24: 2; 25: 2; 26: 2; 31: 2; 32: 2; 33: 2; 34: 2; 35: 2; 36: 2; 37: 2; 38: 2; 39: 2; 40: 2; W5 45: 2; W6 46: 2; W11 51: 2
|  | S3 | 6: 2; 7: 2; 8: 2; 9: 2; 10: 2; 15: 2; 16: 2; 18: 2; 19: 2; 20: 2; 21: 2; 22: 2; 23: 2; 24: 2; 25: 2; 31: 2; 32: 2; 33: 2; 34: 2; 35: 2; 36: 2; 37: 2; 38: 2; 39: 2; 40: 2; W5 45: 2; W6 46: 2; W11 51: 2
|  | S4 | [5 empty] | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 |  |  |  | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
|  | S5 | 27: 2; 28: 2; 29: 2; 30: 2; 31: 2; 32: 2; 33: 2; 34: 2; 35: 2; 36: 2; 37: 2; 38: 2; 39: 2; 40: 2; W3 43: 2; W4 44: 2; W5 45: 2; W6 46: 2; W7 47: 2; W8 48: 2; W9 49: 2; W10 50: 2; W11 51: 2
SME | bar: 31 to 38; W5 45 to W11 51
VENDOR | bar: 15 to 16; 32 to 38; W7 47 to W11 51
Installation | bar: 17; 40
|  | Total | 3 | 4 | 5 | 6 | 6 | 12 | 12 | 12 | 12 | 10 | 8 | 8 | 8 | 8 | 10 | 10 | 10 | 10 | 10 | 10 | 12 | 12 | 12 | 12 | 12 | 10 | 10 | 10 | 10 | 10 | 14 | 13 | 12 | 11 | 10 | 10 | 11 | 11 | 10 | 10 | 4 | 4 | 6 | 6 | 11 | 11 | 7 | 7 | 7 | 7 | 11
|  |  | S1 | S2 | S3 | S4 | S5
|  | Ops | 1: 0; 2: 1; 3: 1; 4: 1; 5: 1
|  | Tech | 1: 4; 2: 1; 3: 1; 4: 1; 5: 1