## Slide 1: SNS PPU CRYOMODULE FDR
Kurt Macha
Cryomodule Assembly Plan
This talk will be mostly tooling focused
Other talks cover more in depth assembly processes

## Slide 2: Outline
Four major workstations
  Work station #1 Clean Room Assembly (earlier talk by K. Wilson)
  Work station #2
    Cold Mass Assembly
    Thermal Shield/Space Frame Assembly
    Alignment
    Insertion of cold mass into the vacuum tank
  Work Station #3 Cryomodule Final assembly
    End can assembly
    Top hat assembly
  Work station #4
    Test cave thermal cycle and checkout
Tooling is at PDR status, will progress over the next few months toward final design. Will show current status of tooling.
Majority of the assembly plan is based on the original SNS CM build
  The end can assembly will be different due to the new CM design.

## Slide 3: Recommendations and Comments
R7 | Develop conceptual designs for cleanroom and assembly tooling. | CLOSED | This has been done and will be presented at the FDR. [Clean Room and Cryomodule Assembly talk]
C11 | Consider CAD demonstration of cleanroom-to-spaceframe tooling interfaces. | CLOSED | This has been done and will be presented at the FDR. [Cryomodule assembly talk]

## Slide 4: Cryomodule assembly floor layout
Work Station #2
Vacuum vessel
assembly
Work Station #3
End Can assembly
to the vacuum vessel
Work station #4
Thermal cycle
testing and checkout
Work station #1
Clean room
Assembly

## Slide 5: Cavity string transfer from the clean room
The cavity string assembly will be transferred from the clean room to a fixed high bay rail for further assembly.
An ion pump will be used to maintain vacuum and monitor pressure through out the assembly process.
  The ion pump weight will be supported to the end lollipop carriage.
Ion pump support
Cavity string as transferred
from clean room
Recommendation #7

## Slide 6: Work station #2
Cold mass assembly will be assembled using the same tooling as the original SNS build
The ion pump support from the lollipop will be transferred to the spaceframe for insertion into the vacuum vessel
Alignment using the one arm fixtures (Same process as original build)
Ion pump support
Space frame tooling
Lollipops as used for
first SNS build, ready for
removal at this stage of assembly
Recommendation #7 and Comment #11

## Slide 7: Work station #2
The original vacuum tank support will be used
A minor interference causing a modification for mounting (Left)
Repositioning the support with a new mounting bracket will easily resolve the interference (Right)
Tooling removed as CM is rolled into vessel
Comment #11

## Slide 8: Work station #2
Align the spaceframe in the center of the vacuum vessel
  Investigating differential screws for fine adjustment (Talked about in earlier talk)
Install and secure all lockdowns
Crane the vacuum vessel assembly to the next work center, install saddles and set the assembly on concrete blocks for proper work height
Center BL Flange
To Vacuum Vessel
Flange

## Slide 9: Work Station #3
The cryomodule shell sub-assembly will be staged on blocks for appropriate work height.
The end cans will be mounted on tooling that is installed on rail carts for easy maneuverability.
Clear access for top hat assembly
Recommendation #7

## Slide 10: Work station #3
Simple jig used to
locate cart in relation
to the shell
The end can rail cart rails are set perpendicular to the vacuum vessel for in and out adjustment. (Use Jig)
Three point adjustment for setting of height and plumb.
Support fixture allows fine swivel adjustment.
We have a draft assembly procedure. Tooling was designed around this plan.
Rotatable flanges
Mounting block
New rail cart
design
Recommendation #7

## Slide 11: Work station #3
Existing rail
cart
Same adjustment
Fixture design used for both End Cans
Same assembly process used for both end cans
Recommendation #7

## Slide 12: Work station #3
Return
End Can
Supply
End Can
Install 2k, 4k, coupler and shield piping.
Leak test 2k, 4k, coupler and shield piping
Install end cap thermal shield, Mu shielding and MLI.
Install the VV end plates
Close up the top hat areas

## Slide 13: Work station #3 Warm to cold beamline assembly
Install the final beam line sections using portable clean room work spaces
Extra precautions to ensure reduced particulate.
  Slow pump and slow backfills will be done using improved equipment and procedures

## Slide 14: Work Station #3
Close all vacuum shell ports
  Parallel plate reliefs, blank flanges, burst disk, instrumentation ports, pump gate valve and vacuum monitoring manifold.
  Pump and leak test vacuum shell
  Testing of internal piping
Burst disk
Parallel plate relief
Access port
blank flange
Pump out valve
Instrumentation
port
Gauge manifold

## Slide 15: Work station #4
Cryomodule test cave will be used for thermal shock testing
Instrumentation checkout
Existing U-tube pipes will need modification to accommodate the new end can design
Cryomodule rolling carts need modification due to new end can designs.

## Slide 16: Summary
macha@jlab.org
Kurt Macha
Many of the same assembly processes to the first SNS build
Work station 3 resulting in the most difference due to end can design.
  New assembly processes
  New tooling for end can assembly
Extra care will be taken to support the temporary Ion pump weight during assembly
Work station 4
  Cryomodule rolling cart will require modifications
  U-tube modifications