## StatusReport
Status Report
For Fiscal Year 2019 Period 8
PROJ: FMESR2
PROJ ID: 000001.12.03.002.006
B&R: Facilities
PROJ NAME: ESR2 Planning & Concept
PROJ MANAGER: Rusty Sprouse
Period of Performance: 11/1/18-
Exclude machine shop project
**Budgets on this page have not been finalized and are based on the AWP planning to date.
| CURRENT | TOTAL | OPEN | PENDING | FY19 | **AWP BUDGET | FY18 | TOTAL | REMAINING | TOTAL
| PERIOD | YTD | PO | (Credit | SPENDING |  | COMMITS | BUDGET | BUDGET | CTD
| INCURRED | INCURRED | COMMITS | Cards, PR, |  |  |  | (47% OF DIRECT BUDGET SPENT) |  | INCURRED
Stock,
Travel)*
LABOR
Direct Labor (5739) | 31096 | 150703 | 0 | 0 | 150703 | 527819 | 0 | 527819 | 377116 | 150703
Statutory Fringe ( 9.100%) | 2830 | 13714 | 0 | 0 | 13714 |  |  | 0 | -13714 | 13714
Fringe Benefits (51.400%) | 15983 | 77461 | 0 | 0 | 77461 |  |  | 0 | -77461 | 77461
TOTAL LABOR | 49909 | 241878 | 0 | 0 | 241878 | 527819 |  | 527819 | 285941 | 241878
EXPENSES
Sply, Matl, Equip, Bldg (5743) | 0 | 0 | 4500 | 0 | 4500 | 0 | 0 | 0 | -4500 | 0
TOTAL EXPENSES | 0 | 0 | 4500 | 0 | 4500 | 0 | 0 | 0 | -4500 | 0
TOTAL DIRECT | 49909 | 241878 | 4500 | 0 | 246378 | 527819 | 0 | 527819 | 281441 | 241878
OVERHEAD
Pool 25: MAT HANDLG ( 5.730%) | 0 | 0 | 258 | 0 | 258 |  |  | 0 | -258 | 0
TOTAL WITH OVERHEAD | 49909 | 241878 | 4758 | 0 | 246636 |  |  | 527819 | 281183 | 241878
LABOR ADJUSTMENTS | [7 empty] | 0
NONLABOR ADJUSTMENTS | [7 empty] | 0
DIRECT BUDGET WITH ADJUSTMENTS | [7 empty] | 527819
*NOTE:
Pending numbers for this report are generated nightly. Drill down numbers are real-time.