## Sheet1
ESR2 P&ID Status
DRAWING NUMBER | DRAWING NAME | DESIGNER INITIALS | READY FOR CHECKING | OUT FOR SIGNATURES | HISTORY | RELEASED IN DOC CONTROL | MODEL PART# NOT CREATED | MODEL PART# CREATED BUT NOT READY | MODEL PART# CREATED & READY | DRAWING READY FOR CHECKING | DRAWING IN CHECKING | DRAWING RELEASED IN DOC CONTROL
74020-0001 | CRYOGENICS SYSTEM BLOCK DIAGRAM | C. Butler | 100% | YES | NEW | NO
74120-0001 | MAIN COMPRESSOR SYSTEM FLOW DIAGRAM | C. Butler | 100% | YES | NEW | NO
74120-0002 | FINAL OIL REMOVAL P & I DIAGRAM | C. Butler | 100% | YES | NEW | NO
74220-0001 | MAIN COLD BOX (MCB) P& I DIAGRAM | C. Butler | 100% | YES | NEW | NO
74320-0001 | TRANSFER LINE (EST2) FLOW DIAGRAM | C. Butler | 85% | YES | NEW | NO
74520-0000 | RECOVERY SYSTEM P & I DIAGRAM | C. Butler | 90% | YES | NEW | NO
74520-0001 | PURIFIER SYSTEM P & I DIAGRAM | C. Butler | 90% | YES | NEW | NO
74520-0002 | RECOVERY COMPRESSOR C5 P & I DIAGRAM | C. Butler | 100% | APPROVED | NEW | REV -
74520-0003 | RECOVERY COMPRESSOR C6 P & I DIAGRAM | C. Butler | 100% | APPROVED | NEW | REV -
74622-0001 | COOLING WATER P & I DIAGRAM | C. Butler | 100% | APPROVED | NEW | REV -
74622-0002 | SECONDARY TURBINE COOLING WATER P & I DIAGRAM | C. Butler | 100% | YES | NEW | NO
74623-0001 | INSTRUMENT AIR SYSTEM P & I DIAGRAM | C. Butler | 100% | APPROVED | NEW | REV -
74720-0000 | ESR2 LN2/GN2 DISTRIBUTION P & I DIAGRAM | C. Butler | 100% | APPROVED | NEW | REV -
74720-0001 | He GAS STORAGE DISTRIBUTION P & I DIAGRAM | C. Butler | 100% | APPROVED | NEW | REV -
74720-0002 | He GAS STORAGE DEWARS P & I DIAGRAM | C. Butler | 100% | APPROVED | NEW | REV -
EXISTING VENDOR P&IDS REVISED SUCH TO INTERFACE WITH ESR2 SYSTEMS
SC1-0-11-001 | SSCL 1ST STAGE COMPRESSOR P & I DIAGRAM | C. Butler | 100% | APPROVED | REVISION | REV 6
SC1-0-13-001 | SSCL 2ND STAGE COMPRESSOR P & I DIAGRAM | C. Butler | 100% | APPROVED | REVISION | REV 6
SC1-0-17-001 | SSCL COLD BOX CARBON BED ADSORBER REGEN P & I DIAGRAM | C. Butler | 100% | APPROVED | REVISION | REV 6
EXISTING ESR1 P&IDS REVISED SUCH TO INTERFACE WITH ESR2 SYSTEMS
71400-1000 | CHL LN2 DISTRIBUTION SYSTEM FLOW DIAGRAM | C. Butler | 90% | OPEN | REVISION | REV C
71700-0027 | CHL FLOW SCHEMATIC LIQUID NITROGEN STORAGE DEWAR | C. Butler | 90% | OPEN | REVISION | REV D
74100-0016 | ESR1 FINAL OIL REMOVAL FLOW DIAGRAM | C. Butler | 100% | APPROVED | REVISION | REV B
74200-0111 | ESR1 WARM He GAS INTERFACE TO HALLS (EWG) FLOW DIAGRAM | C. Butler | 100% | OPEN | REVISION | REV E
74400-0010 | ESR HALL 'A' INTERFACE FLOW DIAGRAM | C. Butler | 100% | OPEN | REVISION | REV K
74400-0011 | ESR HALL 'B' INTERFACE FLOW DIAGRAM | C. Butler | 100% | OPEN | REVISION | REV S
74400-0012 | ESR HALL 'C' INTERFACE FLOW DIAGRAM | C. Butler | 100% | OPEN | REVISION | REV N
74400-0009 | ESR1 GAS MANAGEMENT FLOW DIAGRAM | C. Butler | 100% | OPEN | REVISION | REV P
74400-0013 | ESR VALVE BOX FLOW DIAGRAM | C. Butler | 100% | OPEN | REVISION | REV S
74600-0100 | ESR1 COOLING WATER FLOW DIAGRAM | C. Butler | 100% | APPROVED | REVISION | REV D
74700-0004 | ESR 10,000L He DEWAR FLOW DIAGRAM | C. Butler | 100% | APPROVED | REVISION | REV F
New drawings: | 15
Vendor drawings: | 3
JLab dwg revisions: | 11
Total dwgs | 29