## Slide 1: SBS Engineering Status
Robin Wines
August 2019

## Slide 2: Kinematics of SBS
SBS Program is defined by three experiments, each with multiple configurations of equipment. Each configuration has been modeled and the required layout of the Hall has been determined.

## Slide 3: GEp
HRS-L
HRS-R
ECAL
Cable Carts
HCAL
SBS
E-HUT

## Slide 4: GEn
CDET
HCAL
BB
SBS
HRS-R
HRS-L

## Slide 5: GMn
SBS and HCal
BB
E-HUT

## Slide 6: SBS status- main components complete and in storage
Scattering Chamber & Vacuum Snout-in storage
Front Field Clamp-in storage
Corrector Magnets-in storage
48D48 Magnet-in storage
Counterweight Support Structure-in storage
Exit Beam Pipe-parts in storage
Rear Field Clamp-in storage
GEM frames-parts in storage
Plastic Analyzers-in storage

## Slide 7: Beamline Support
Kinematics of experiments require 4 beamline configurations. Developed tower & overhead support to accommodate all configurations.
Tower fabricated and in storage.
Main tower
Existing beam line
SBS beam line
Radiation shielding & supports in storage.
Corrector
Corrector
Vertical supports in fabrication.
Tower extension in storage

## Slide 8: Beamline Shielding
Conical beam pipe, correctors and shielding pieces are in storage.
Assembly drawings complete.
Trial assembly completed, remaining assembly parts being purchased.

## Slide 9: ECAL
Front frame has been delivered.
Design of back frame near completion- needs access doors and support feet.
Modifying existing platform- needs design of support feet and lifting frame

## Slide 10: CDET
Have CDet frame
Added hardware design to mount detector modules to frame
Added modifications to the frame for the addition of the post racks that house the cables
Added strain relief bars for the cables
Need to determine if width of frame is sufficient for access of the panels

## Slide 11: HCAL & CDET Support/ Access Platform
HCAL is being assembled
Access platform in procurement
Support platform in procurement

## Slide 12: BigBite
BigBite detector frame modifications are defined to include GEMs and GRINCH.
Modifications have been completed.
New BB electronics frame is complete.

## Slide 13: Polarized 3He Target

## Slide 14: Polarized 3He Target
Design completed. Continue on drawings and procurements.
  Oven material delivered
  Be window telescoping beampipe delivered
  Be window flange delivered
  Cell glue fixture delivered
  Alignment cartridge delivered
  Telescoping exit beampipe weldment delivered
  Magnetic shielding assembly in storage delivered
  Platform drawings 95% complete.
  Target system drawings 75% complete.

## Slide 15: Utilities
Electronics Huts – Main hut to be located on beam left side of Hall. Two GEM electronics huts to be relocated as needed with use of BB, SBS detectors and GEn-RP detectors. All materials in storage.
Power Supplies- SBS dipole power supply in-house. Corrector power supplies in-house.
LCW- Upgrades to LCW system starting September 2019.

## Slide 16: SUMMARY
Items remaining :
- Drawings & modifications of Ecal/ CDet support platform
- ECal back frame and assembly drawings
- Complete CDet hardware and frame modifications
- Beamline assembly hardware procurement
- Review of SBS detector frame
- Procuring assembly parts & hardware (beamline flanges, tie
rods, stand-offs, cylinder cart, floor plates)
FY19-FY20 Schedule & Manpower
- With present staff, need 12 calendar weeks to complete

## Slide 17: GEn polarimeter Layout
BB
HCAL
SBS
BR
BL
Polarimeters

## Slide 18: Kinematics of GEn-RP