## Sheet1
Isotope Program Risk Registry
Risk | Consequence level | Probability | Unmitigated Risk | Mitigation | Mitigated Risk
Water cooling stops | EL | M | 1 | Flow and temperature measurements on each circuit | N
Thermocouples change calibration due to radiation | EL | M | 1 | Reduntant thermal measurement on two circuits | N
Instrumentation is damaged by radiation | L | M | 2 | Radiation shielding surrounds radiator and target No instrumentation inside the shielding hutch | N
Ozone production in the air gap | L | H | 3 | Nitrogen flowing through the air gap Ozone monitoring on the exit air plenum No entry to the vault during cool down period would allow ozone to be removed from vault | N
Crucible cracks | EL | L | ! | High surface tension of Gallium would keep it contained in the crucible | N
Crucible breaks apart so Gallium can leave the crucible (1) | L | L | 1 | Gallium is kept on copper baseplate by secondary containment | N
Crucible breaks apart so Gallium can leave the crucible (2) | L | L | 1 | Gamma ray absorption by rear push plate would increase temperature of the cooling water Excess temperature is interlocked to prevent LERF beam operation. | N
Crucible is dropped during removal | L | M | 2 | Practice with empty crucible | 1
Transfer to VCU goes wrong | EL | M | 1 | Use point-to-point transfer JLab staff follow truck to ensure correct delivery | N
Transport container is opened incorrectly | L | M | 2 | Carry out dry runs with VCU RSO participation JLab staff will be present for initial deliveries | N