Isotope Production R&D at Jefferson Lab’s High-Power Electron Accelerators

Request for Initial Packet of Information:

Project Control Milestones for the project duration. These should be more technical in nature. Provide at least one milestone per quarter consisting of the following:

See attached list of milestones. There is no critical path, as there is sufficient float.

Project Expenditures

- Labor and Hardware Costs

Costs starting from beginning project to the completion of project, separated into four sections.  Each of these categories should further be broken into labor and hardware, for a total of eight categories.

|  | Projected labor expenditures (a) | Projected hardware expenditures (b) |
| --- | --- | --- |
| Design | $179000 |  |
| Procurement | $30800 | $15000 |
| Construction | $62600 | $4000 |
| Operation | $103700 |  |

The total of columns (a) and (b) should equal the total project cost.

- List major hardware procurements.

| Item | Critical Path (Y/N) | Estimated Cost | Projected Procurement Date |
| --- | --- | --- | --- |
| Beamline components | Y | $2.5k | 11/2018 |
| Viewer flags | N | $1.5k | 2/2019 |
| Isotope stock | N | $7k | 3/2019 |
| 50 kW target assembly | Y | $11.5k | 8/2019 |
| Shipping container | Y | $2k | 3/2019 |

- Budget breakdown

Tracking of expenditures: Your project should be organized into major activities.  The first column is the WBS item or activity ID number.  The second column is a brief description of the item/activity.  The third column is the baseline total cost of the item/activity, including contingency.  The fourth column shows current "costed and committed" numbers.  The fifth column is a current "estimate to complete" and then an "estimated total cost.”  “Estimated total cost” is the sum of “costed and committed” and “estimate to complete.”

|  | Item/Activity | Baseline Total Cost | Costed & Committed | Estimate To Complete | Estimated Total Cost |
| --- | --- | --- | --- | --- | --- |
| WBS or ID # |  |  |  |  |  |
|  |  | (AY$) | (AY$) | (AY$) | (AY$) |
| 1 | Beam transport installation | $66.6k | $25.4k | $41.2 | $66.6k |
| 2 | 50 kW target design | $197.1k | $21k | $176.1k | 197.1k |
| 3 | Operations | $103.7k | $0k | $103.7k | $103.7k |
| Totals: |  | $367.4 K | $46.4 | $321k | $367.4k |

Project Schedule

- Copy of Project Schedule (attached).

- Starts and Stops. Complete this table and note forecast dates.

|  | Baseline Start Date mo/year | Baseline Completion Date mo/year |
| --- | --- | --- |
| Design | October 2018 | August 2019 |
| Procurement | October 2018 | March 2019 |
| Fabrication | March 2019 | November 2019 |
| Operation | June 2019 | May 2020 |

Summary of concerns/issues at project initiation

None