## Sheet1
Recommendations | Response | Cross Walk to Slides or Background Documents
Planning
è There was very little formal planning | Planning has been difficult given the low priority of the Isotope program, but work has been planned at the scheduled LERF meetings on Wednesday mornings at 11 am
è Informal planning occurred at 7:45 AM prior to the 8 AM Program Deputy meeting | This has not been necessary during the construction phase
è If the planning meetings occurred after the 8 AM PD meeting, there would have been more input to the experiment. | These meetings will be scheduled for the days preceding the irradiations
è Even with this short time to execute, proper procedures were followed: the DOE site office was made aware of the experiment and the experiment was cleared by Oak Ridge Office. A number of individuals contributed to obtaining the needed permissions. | All the proper procedures have been followed to obtain the needed permissions. Patty Hunt and Steve Neilson from the DOE Site Office have visited the vault to see the Isotope preparations.
è Is it worth investigating and creating a library of potential experiments, planned and prioritized for opportunistic running? | Outside the scope of the Isotope Program
Review Process
è There was a formal review | The ERR is a formal review. Engineering reviews of specific topics were organized to allow a cognizant expert to spend enough time with the designs to cover all the technical details. The hutch design, radiation shielding and target movement were evaluated by Tim Whitlatch. Pressure vessel code compliance was evaluated by Matt Marchlik. Earthquake compliance was evaluated by Tom Renzo. | https://www.jlab.org/indico/event/341/
è The mix of reviewers was good. It included representatives from Physics Division, Operations, Engineering and Radcon. | The ERR has a similar mix of representatives
è The recommendations from the reviewers were specific and helpful | The recommendations of Tim Whitlach, Matt Marchlik and Tom Renzo were extremely helpful, and all suggestions were incorporated. | Talk by Joe Gubeli
https://www.jlab.org/indico/event/341/material/3/18.pdf
https://www.jlab.org/indico/event/341/material/3/19.pdf
è Suggestions of the review committee were followed | We will follow the recommendations of the ERR Committee
è There was an SCMB review | According to Bob May, an SCMB Review is not required for irradiations up to 5 kW. If there is follow-on funding for higher power irradiations, an SCMB Review will be required
è Safety of CEBAF machine was thoroughly reviewed | The ERR will review the safety of the LERF machine
è Experiment was reviewed less thoroughly than the safety of the machine | The ERR will also focus on the experiment
è No Experimental Readiness Review (ERR) occurred | ERR has been scheduled prior to the first irradiation
è Threshold size of experiment for the ERR needs to be determined. One suggestion was any ATLis plan that goes beyond base equipment may warrant an ERR | Outside the scope of the Isotope Program
è Another suggestion is to conduct a Technical Advisory Committee (TAC) type review | Outside the scope of the Isotope Program
è A recommendation is to find the process in place at BNL for small experiments of this type. | Outside the scope of the Isotope Program
è for opportunistic running? | Outside the scope of the Isotope Program
Risk Assessment
è There was no formal risk assessment | There have been ATLis entries for all LERF beam operations, which contain Task Hazard Analyses. There is an ESAD and an RSAD, both of which contain formal risk analyses. | Risk Registry Link
è The risk assessment, even if informal, paid much attention to machine and personnel safety | Much attention has been paid to machine and personnel safety in addition to the formal documentation, e.g. ALARA considerations for removing the irradiated target | ESAD link
è Experiment would have benefited from developing a risk matrix, consequences and mitigations | Risks are addressed in LSAD | Risk Registry Link
è Should the reviewers be charged with raising questions regarding risks? | Outside the scope of the Isotope Program, however I expect the ERR Reviewers will ask about risk
è The experimenters might have responded well to reviewers but might not have been diligent in heeding input from outsiders | The experimenters have listened to all helpful suggestions
Skills Mix
è The right skills were brought into the experiment | The team consists of people who are multi-talented. It is regrettable that the low priority of the isotope Program has prevented others from actively participating - particularly in Engineering.
è Operational Support was good | The Accelerator Operations Department took responsibility for resuscitation of the LERF. Operational support has been excellent with an assigned Operations Coordinator (Shawn Frierson) and with MCC operators participating in all beam operations.
è Beam set up at 4K including calibration of newly installed diagnostic equipment with the existing equipment in the beam line went very well | Beam set-up of the resuscitated LERF was slow, interrupted by hardware failures
è Experiment installation, alignment without and with beam had the right people to execute and was successful | The right people were assigned; the Isotope program frequently had to wait for these experts to become available due to the low priority of the Isotope Program
è Temporary Operational Safety Procedure (TOSPs) and Task Hazard Analysis (THA) were done by safety professional | All TOSPs and THAs were reviewed by Ops personnel and Safety professionals
è Radcon and Industrial hygiene personnel were included in the retrieval, packaging and shipment of the irradiated sample | Support from RadCon has been outstanding. Keith Welch has been integrated into the Team from the beginning and has led the evaluation of the hutch shielding requirements, and the retrieval, packaging and shipping of the irradiated sample
è ATLis containing the test plan was being revised during the experiment. Suggestion is to have a person who is well acquainted with generating ATLis (such as an operator) participate in developing the test plan | ATLis have been prepared
è Having regular meetings after the 8 AM PD meeting would have brought in more expert help. | In the installation and resuscitation phases, there were regular meetings in the LERF Break Room. Regular meetings after the 8 AM PD meeting will be held in the days prior to the first irradiation.
Safety
è RWP, TOSP and THA were reviewed prior to the experiment | This has been done in addition to the ESAD and RSAD | Link to ESAD
Link to RSAD
è SCMB has reviewed the safety of the experiment | Operation up to 5 kW does not need an SCMB Review
è No personnel were hurt | All efforts will be made to ensure that no-one is hurt in the isotope experiments, including our collaborators offsite.
è Target retrieval was rehearsed | Target retrieval will be rehearsed
è The gallium in the BN crucible should have been grounded (BN is an electrical insulator) | Crucible now has a graphite plug that acts as a grounding conductor | Overview talk by Andrew Hutton (Slide20)
è Some instrumentation near the target area sustained radiation damage. Dose rate calculation should be part of experiment planning | There is no sensitive instrumentation within the hutch. The hutch shielding has been designed to reduce radiation in the LERF vault to levels that will not affect instrumentation (this is more stringent than is required at the ANL Isotope Irradiation Facility, which members of the Isotope Team visited to learn about their program). | Talk by Keith Welch (Slide 5)
è Shipment should include appropriate labels | Shipment will have all appropriate labels
è The shipment should include the activity and dose rate document | Shipment will include the activity and dose rate documentation
è Dry run of un-irradiated gallium to VCU’s RSO would have helped prevent the spill at VCU | Two dry runs have already taken place, and included several members of the VCU Radiation Control Group.
è Clear instructions to the VCU’s Radiation Safety Officer on opening the container should have been included in the package. Should include VCU’s RSO in future shipment process | Clear instructions have been prepared, provided to VCU in advance, discussed with the VCU RadCon personnel, and a copy be will placed in the transport container. VCU's RSO has been involved in the two dry runs. | https://www.jlab.org/indico/event/341/material/3/38.pdf
è Should acquire a DOT Type A container for shipment | A DOT Type A transport container has been purchased as well as two lead "pigs" that were custom made for the transport container. | Lessons Learned talk by Andrew Hutton (Slide 19) and talk by Keith Welch (Slide 13)
Should assume that the person opening the package knows nothing about what's in it, and that they will assume they can open any openable container in the package unless there are instructions telling them otherwise. | The instructions are clear, and additional labels have been placed on the "pig" to state clearly that the "pig" should be delivered unopened to the hot cell in Jamal Zweit's laboratory. | Overview talk by Andrew Hutton (Slide 34)
Documentation
è There were check lists for installation and target retrieval process | Check lists exist
è The documentation was mostly complete with the exception of formal risk analysis | Formal risk analysis has been prepared | Risk Analysis
è No Engineering drawings of the experiment were drawn | Engineering drawings were prepared by Joe Gubeli. Support from Engineering would have been appreciated. | Talk by Joe Gubeli (Slides 4-, 8-12, 17)
è ATLis entries were being updated the day of the experiment. This should have occurred earlier | ATLis entries have been prepared in advance for all resuscitation runs and will be prepared in advance for target irradiations
è Responses from reviewers could use more time | Enough time will be left for responses.
è ATLis author needs to have better knowledge of operations | An MCC Operator (Shawn Frierson) and Matt Bickley reviewed the operations plan before the ATLis entries were written
è Documentation should be such that a different group of experimenters can successfully stage the experiment | Documentation is good, but active participation in the first experiments would help future experimenters
è A mailing list of people to notify all concerned with any change of plans would be useful | This will be created