## Slide 1: BigBite Calorimeter status
Arun Tadepalli – Jefferson Lab

## Slide 2: Contents
General introduction to the detector
Current status of shower and preshower
Before moving to the hall…
After the move and before day 1
Summary

## Slide 3: BigBite Workforce
Name | Location | Position | Role | FTE | Comments
Arun Tadepalli | JLab | Postdoc | Contact | >75% | onsite
Bogdan Wojtsekhowski | JLab | Staff | Detector |  | onsite
Mark Jones | JLab | Staff | DAQ, trigger | 20% | onsite
Eric Fuchey | UConn | Postdoc | Software/as needed | 15% | remote
Provakar Datta | UConn | Grad Student | WAPP trigger | More? | onsite
Bhesha Devkota | Miss. State. Univ | Grad student | Installation & Misc | 40% | onsite
Will Tireman | Northern. Mich. Univ | Prof. | HV calibration using cosmics | < 5% | remote
Gary Penman | Univ of Glasgow | Grad student | Software | 40 – 50% | remote
COULD BE YOU! | Anywhere | Alert | Very important! |  | onsite/remote

## Slide 4: General detector capabilities
Purpose
  Trigger (for all experiments other than GEp)
  Determination of energy
  PID
  Starting point of track reconstruction and time determination
General principles
  Collect Cherenkov light from relativistically charged particles including primaries and secondary e+/e- shower in electromagnetic cascades
  Long axis of preshower perpendicular to e- or pion
  Long axis of shower parallel to e- or pion
https://drive.google.com/drive/folders/1wp-CWXj9u6otH6OU8Wz1OW3F3scEEEc7?usp=sharing

## Slide 5: Trigger diagram
Charged particle
Trigger concept:
PS + SH > Adjustable threshold
preshower
shower
*will be updated after including WAPP trigger
5
26 row x 2 col blocks
9 x 9 x 30 cm rad hard lead glass blocks
27 row x 7 col
8.5 x 8.5 x 37 cm lead glass blocks

## Slide 6
Shower stacking with more efficient blocks and mu-metal plates
Replaced (previously adjusted) top layers of inefficient shower blocks with good preshower blocks
The HV bases for the shower have been installed
Inside the shower

## Slide 7
Red = signal from 5.6 top layer
Yellow = signal from 4.6 which is from the replaced PMT
It works!
Bogdan applying UV curing light to cure the epoxy
SBS docid#72

## Slide 8
Preshower stacking completed

## Slide 9
Cabling work completed

## Slide 10: AT TEDF…
Cabling (signal and HV) - all cables and connectors intact – completed
Repaired broken modules in place – completed
Light leak checks (shining flash light and checking for current on pico-ammeter) - completed
Signals on individual channels - completed
Looking at pedestals with HV off - completed
Looking at the amplitude shape of the signals with HV on – completed (general noise issues pertains)
Attaching the cosmic counter and setting up the FastBus trigger – completed
Also set up the trigger using the sum of different layers in the shower and preshower – completed
Checking the shape of amplitude distribution – completed
Taking data using different HV settings for shower and preshower – completed
Alpha studies for shower and preshower completed – completed
Adjusting the gain and offset seen on amplifier summer modules – completed
Checking individual channels on the discriminator – completed
For more information see BigBite calorimeter status weekly meeting updates on Sep 14th 2020, Nov 9th 2020, Jan 11th 2021

## Slide 11: At tedf…
Adding a copy of the trigger to get WAPP pion threshold (Provakar’s work) – in progress
Attaching new discriminators with tweakable discriminator thresholds – in progress
Remotely monitorable thresholds – need to think about this

## Slide 12: From the DAQ side
FastBus connected and fully operational with cosmic trigger – completed
Upgrade to CODA3 – completed (thanks to Bryan Moffit, Alex Camsonne and Ben Raydo!)
Connecting preshower to FADC channels – completed
  Raw data with 16 channels looks ok. Need to coordinate efforts with HCAL people on FADC software for BBCAL
Connecting shower to FADC channels – to do
  LEMO to BNC FADC cable making in progress (120/272 finished by DSG).
  There are plans (by Alex) to acquire the FADCs ahead of time and return after the shipment arrives in June – We strongly advocate for this!
No TDCs being used currently
Until more FADCs for the shower arrive, all calibrations will continue with the FastBus

## Slide 13: From the software side
As mentioned before, software exists to looks at:
  Raw hits
  Pedestals
  Analysis code to monitor ADC spectra
  HV adjustment
  Cosmic event display (to do)
  Cosmic calibrations (Will Tireman’s talk)

## Slide 14: Detector equipment
Detector stack
  Shower and preshower
Cable system
  52 signal cables for preshower and 189 signal cables with spares for shower
  52 HV cables for preshower and 189 HV cables with spares for shower
Power supplies = 2
  Adequate number of HV cards with 4 spares
Blue electronics racks = 1
  Discriminator modules
  Amplifier summer modules
  Trigger (lower and upper threshold copies)
BigBite weldment
  DAQ (FastBus or VME), cosmic trigger
  4 FADC at hand (12 ordered for shower)
  LEMO to BNC (64 ready for preshower, 120/252 being prepared by DSG, +16 spare)

## Slide 15: Sequence of Moving equipment to the hall
Detector stack
  After Shower & preshower fully uncabled
Signal cables from HCAL
  HCAL will be moved first hence we have to give (up) the signal cables. HCAL TDC cables will have been freed for BigBite by then.
Front end blue rack + preshower & shower signal cables conduit
  All cables are in conduit (easy to control and transport)
HV cables in a basket
  Limitation is that they are underneath the signal cables which will be moved for HCAL folks so it should be ok
BigBite weldment that carries DAQ, patch panels, FADC cables and cosmic trigger

## Slide 16: Moving cables to the hall…
Preshower and shower front end signal cables can be taken with this rack
Unplug shower and preshower cables and put in basket
Unplug HV cables and put in basket below

## Slide 17: Floor plan in hall a
What we really need is someone to tell us, “Hey, this is where you can layout your cables”

## Slide 18: Timeline of bigbite tasks (as per jessie’s gantt chart)
Decabling shower preshower
May 17th
Jun 1st
Jul 2nd
Aug 1st
GMn run group
Jessie and co. tests in the pivot area to put bigbite at an angle
Moving HCAL cables,
Moving BigBite weldment
Moving front end blue rack
HV cables to Hall A
Start attaching cables
Plan ahead due to COVID restrictions
Software for beam conditions (see next slide)
Moving BigBite to Hall A
Attach cosmic trigger
Check pedestals and ADC spectra with cosmics in the Hall
EVERYTHING SHOULD BE READY!
2 weeks
2 weeks

## Slide 19: after move and before day 1…
Make sure that:
  All connections are tested
  Amplitude and time distributions are seen for all the channels on FADC or Fastbus
  Online monitoring setup to see the counting rates, cosmic tracks and event display in individual blocks on a 27 x 7 and 26 x 2 grids
  Trigger has been tested out and the thresholds are tweaked
  HV display should be simple for shifters (green or red) and alert experts if needed
  All observations are properly documented in the logbook!

## Slide 20: Day 1
Will have to monitor all the quantities mentioned in the previous slides under beam conditions
Plan for calibrations under beam conditions
  For E02-013 (GEn), calibrations were done using elastics on H2 data for electrons and pions (Seamus Riordan’s thesis).
  Should we do this again? Need to discuss with BigBite group
  Andrew pointed us to Freddy Obrecht’s thesis where the procedure is outlined in detail

## Slide 21: Documentation/safety
Documentation
  BigBite how to – Eric Fuchey (needs to be updated)
  Making a cosmic trigger using FastBus (https://sbs.jlab.org/cgi-bin/DocDB/private/ShowDocument?docid=74)
  THA (Task Hazard analysis) – to do
Safety
  Ladder safety (to do)
  COVID restrictions (to do)
  Procedure to replace a PMT (https://sbs.jlab.org/cgi-bin/DocDB/private/ShowDocument?docid=72)
How-to for shift workers
  Instructions on DAQ operation, monitoring ADC spectra etc will have to be written. The person who will do these tasks will write the documentation for shifters. Will have to be written for shifters but not worried at this point

## Slide 22: summary
Current status of the shower and preshower from detector, software, and DAQ viewpoint
New people have joined and are enthusiastic about hardware experience and interested in contributing to analysis tasks.
Some preliminary thoughts on what to anticipate while moving detectors, cables, weldments, front end racks and calibrations were presented to invoke discussions
Need to communicate and coordinate effectively while following safety and COVID protocols
Exciting times ahead!!

## Slide 23: SPECIAL Thanks TO
Many people who helped cable up the detector
  Ashley Yoon, Abby Hellman, Maria Satnik
  Eric Fuchey
  Doug Higinbotham
Chuck Long for all continued help
DAQ debugging – Alex Camsonne, Bryan Moffit & Ben Raydo
DSG – Mindy Leffel and Marc McMullan for help with cables
Calibration software support – Will Tireman
Hall A staff and engineers