## NP Log
[13 empty] | as of: 21 Nov 13 | [9 empty] | CHANGE IN CONTINGENCY AND MANAGEMENT RESERVE | [23 empty] | CHANGE IN CONTINGENCY AND MANAGEMENT RESERVE
FY13 NP Change Request Log | [16 empty] | ESCALATED VALUES | [23 empty] | DIRECT VALUES
12 GeV Upgrade
[39 empty] | AY$ | [23 empty] | AY$
|  |  | CR | Date | Date |  | CCB | Contingency | Mgmt Reserve | Impact |  | Approval | Implementation |  |  |  | 1.0 |  | 1.1 |  | 1.2 |  | 1.3 |  | 1.4 |  | 1.5 |  | 1.6 |  | 1.7 |  | 1.8 |  | 1.9 |  | 1.1 |  | Total |  | 1.0 |  | 1.1 |  | 1.2 |  | 1.3 |  | 1.4 |  | 1.5 |  | 1.6 |  | 1.7 |  | 1.8 |  | 1.9 |  | 1.1 |  | Total
CR # | Class | WBS # | Title | Submitted | Required | Originator | Concur | (Burd. CY$K) | (Burd. CY$K) | Assessment | Status | Date | Cost Book | Cost Mgt | P6 | WAD | Cont. | MR | Cont. | MR | Cont. | MR | Cont. | MR | Cont. | MR | Cont. | MR | Cont. | MR | Cont. | MR | Cont. | MR | Cont. | MR | Cont. | MR | Cont. | MR | Cont. | MR | Cont. | MR | Cont. | MR | Cont. | MR | Cont. | MR | Cont. | MR | Cont. | MR | Cont. | MR | Cont. | MR | Cont. | MR | Cont. | MR | Cont. | MR
14-001 | 3 | 1. | Admin CR to Update Costbook to Reflect FY13 Actuals and Commitments; Escalate Costbook, P6 and Cost Manager to FY14$ | 2013-10-10 | 2013-10-31 | V. James | Yes |  |  | Complete | Approved | 2013-10-31 | vaj/11-8-13, Scenario 1179 | vaj/11-8-13 | BL14-001 October 13 Progress |  |  | 0 |  | 0 |  | 0 |  | 3.151 |  | 13.86 |  | 4.107 |  | 0.456 |  | 0.661 |  | -38.378 | [5 empty] | -16.143 |  | 0 |  | 0 |  | 0 |  | -56.012 |  | -648.409 |  | -139.141 |  | -61.453 |  | -28.778 |  | -311.486 | [5 empty] | -1245.279
[15 empty] | Totals |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3.151 | 0 | 13.86 | 0 | 4.107 | 0 | 0.456 | 0 | 0.661 | 0 | -38.378 | 0 | 0 | 0 | 0 | 0 | -16.143 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -56.012 | 0 | -648.409 | 0 | -139.141 | 0 | -61.453 | 0 | -28.778 | 0 | -311.486 | 0 | 0 | 0 | 0 | 0 | -1245.279
13-XXX | Link to CR Document
Construction
[12 empty] | Cont. | MR | Total | CD-2 |  | 11 | 0 | 527 | 0 | 1813 | 0 | 64888 | 0 | [8 empty] | 4612 | 0 |  | 0 |  | 0
[11 empty] | TEC | 15215.9866 | 302.7408 | 15518.7275 | FY08 Changes |  | 0 | 43.5 | -458.054 | 65.165 | -113.9916 | 232.072 | -6.912 | 1657.96 | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0
[11 empty] | OPC | 4385.3088 | 461.266 | 4846.5748 | FY09 Changes |  | 0 | 0 | -42 | -108.179 | -1126.7641 | 117.1147 | -2548.5511 | -1635.3578 | [8 empty] | -265.5316 | 0 | 0 | 0 | 0 | 0
[11 empty] | TPC | 19601.2955 | 764.0068 | 20365.3023 | FY10 Changes |  | 0 | 0 | -36 | 0 | -921 | 6.672 | -16177.9228 | 3040.5451 | [8 empty] | -540.6391 | 0 | 0 | -3644.0716 | -140 | -484
[15 empty] | FY11 Changes |  | 0 | 0 | 0 | 0 | 0 | 0 | -16344.2752 | -755.5233 | [8 empty] | -1199.6082 | 0 | 0 | 0 | 0 | 0
[15 empty] | FY12 Changes |  | 0 | 0 | 0 | 0 | 0 | 0 | -2127.1867 | -859.0079 | -8978.7022 | -2122.6473 | -1247.8793 | -529.227 | -661 | -170.4308 | 0 | 1036.3875 | -2417.0389 | 0.124 | 0 | 0 | 0 | 0
[13 empty] | Claus contingency file thru CR14-001 | 20364.8874 | FY13 Changes |  | 0 | 0 | 0 | 0 | 0 | 0 | 15032.001 | 763.096 | -19711.7084 | -580.6143 | 3713.162 | 69.775 | 0.616 | 0.023 | -264.899 | 9.669 | 4194.1807 | 499.034 | 0 | 0 | 0 | 0
[13 empty] | cross check | 0.41487 | FY14 Changes |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3.151 | 0 | 13.86 | 0 | 4.107 | 0 | 0.456 | 0 | 0.661 | 0 | -38.378 | 0 | 0 | 0 | 0
[15 empty] | Current |  | 11 | 43.5 | -9.054 | -43.014 | -348.7556 | 355.8587 | 42715.1532 | 2214.863 | -28690.4106 | -2689.4016 | 2465.2827 | -455.345 | -660.384 | -169.9518 | -264.899 | 1046.7175 | 4383.3628 | 460.78 | 0 | -3644.0716 | -140 | -484
Green indicates implementation status
Note on Q15: Kelly Krug: $123k included in CD-21 contingency is FY08 PED funding that will not arrive until FY09…causing a delta in the 4-way balance of contingency.
Note on P21: vjames: Paste from ugly green

## BAC-Oblig Data
12 GeV Cost/Schedule Status Report | [11 empty] | 2013-10-31
| Cumulative to Date ($K) | [8 empty] | Independent | Contin.
| Budgeted Cost |  | Actual Cost |  |  |  |  | Budget At | Estimate At | Estimate At | & MR
| Work | Work | Work | Variance |  | Performance Indices |  | Complete | Completion | Completion | % | % Complete
WBS | Scheduled | Performed | Performed | Schedule | Cost | SPI | CPI | ($K) | ($K) | ($K) | ($/ETCob)
1.2 PED | 20993.4238 | 20993.4239 | 20993.4238 | 8.97e-05 | 7.79e-05 | 1 | 1 | 20993.4238 | 20993.4239 | 20993.4237 |  | 100%
1.3 Construction Accelerator Systems | 100694.8168 | 100464.759 | 100422.3439 | -230.0578 | 42.4151 | 0.99772 | 1.0004 | 103729.2499 | 103726.1761 | 103685.4566 |  | 96.85%
1.4 Construction Upgrade Halls A, B & C | 56013.4446 | 56571.2561 | 57057.3795 | 557.8115 | -486.1234 | 1.01 | 0.99148 | 90757.3007 | 90744.2067 | 91537.1887 |  | 62.33%
1.4.1 Construction Upgrade Hall A | 667.749 | 657.0925 | 680.7981 | -10.6565 | -23.7056 | 0.98404 | 0.96518 | 667.749 | 667.5519 | 691.8391 |  | 98.4%
1.4.2 Construction Upgrade Hall B | 37024.0724 | 37262.0964 | 37600.7087 | 238.024 | -338.6124 | 1.0064 | 0.99099 | 59803.0974 | 59796.4789 | 60346.547 |  | 62.31%
1.4.3 Construction Upgrade Hall C | 18321.6233 | 18652.0673 | 18775.8727 | 330.444 | -123.8054 | 1.018 | 0.99341 | 30286.4543 | 30280.1759 | 30487.4843 |  | 61.59%
1.5 Construction Hall D | 34734.8486 | 34894.1776 | 35037.7182 | 159.329 | -143.5407 | 1.0046 | 0.9959 | 40007.7263 | 40003.2461 | 40172.3021 |  | 87.22%
1.6 Construction Conventional Facilities | 28273.0334 | 28278.6413 | 28239.9239 | 5.6079 | 38.7174 | 1.0002 | 1.0014 | 30347.3495 | 30344.4694 | 30305.7997 |  | 93.18%
1.7 Construction Project Management | 8225.7857 | 8225.7675 | 8241.8153 | -0.018152 | -16.0478 | 1 | 0.99805 | 9171.2804 | 9170.6689 | 9189.1728 |  | 89.69%
12 GeV Total Estimated Base Cost | 248935.3528 | 249428.0254 | 249992.6046 | 492.6726 | -564.5792 | 1.002 | 0.99774 | 295006.3306 | 294982.191 | 295883.3437 |  | 84.55%
|  |  |  | Management Reserve |  |  |  |  | 302 | 302 | 0.9051%
|  |  |  | IEAC Projected Variance |  |  |  |  | -0.19105 | -23901.3437 | -0.0005725%
|  |  |  | DOE Held Contingency |  |  |  |  | 15216 | 15216 | 45.6%
|  |  |  | 12 GeV Total Estimated Cost |  |  |  |  | 310500 | 287500
1.0 ACD/CDR | 3445.0642 | 3445.0642 | 3445.0643 | 0 | -2.72e-05 | 1 | 1 | 3445.0642 | 3445.0642 | 3445.0643 |  | 100%
1.1 R&D | 7051.5426 | 7051.5426 | 7051.5426 | 9.7e-06 | 1.39e-05 | 1 | 1 | 7051.5426 | 7051.5427 | 7051.5426 |  | 100%
1.8 Construction Pre-Ops | 2377.9475 | 2197.445 | 2332.3016 | -180.5025 | -134.8566 | 0.92409 | 0.94218 | 12117.6672 | 12156.3147 | 12117.6672 |  | 18.13%
12 GeV Total Other Project Base Cost | 12874.5544 | 12694.0518 | 12828.9085 | -180.5025 | -134.8566 | 0.98598 | 0.98949 | 22614.274 | 22652.9216 | 22614.274 |  | 56.13%
|  |  |  | Management Reserve |  |  |  |  | 461 | 461 | 4.647%
|  |  |  | IEAC Projected Variance |  |  |  |  | 0.078449 | -4961.274 | 0.0007909%
|  |  |  | DOE Held Contingency |  |  |  |  | 4386 | 4386 | 44.22%
|  |  |  | 12 GeV Other Project Cost |  |  |  |  | 27500 | 22500
12 GeV Total Project Cost | 261809.9071 | 262122.0772 | 262821.5131 | 312.1701 | -699.4359 | 1.0012 | 0.99734 | 317620.6047 | 338000 | 310000 | 47.05% | 82.53%
[10 empty] | Contingency | 45.28%
[10 empty] | Mgmt Reserve | 1.763%
[10 empty] | Contingency + Mgmt Reserve on Actual Costs | 36.69%
[10 empty] | Contingency Based on Actual Costs | 35.32%
Monthly EVMS Data | BCWS | BCWP | ACWP | [6 empty] | Mgmt Reserve Based on Actual Costs | 1.375%
12 GeV Total Estimated Cost | 3337.7503 | 3022.7911 | 3120.0958
12 GeV Other Project Cost | 294.8543 | 165.8156 | 162.5836 | [6 empty] | Contingency and MR % calculation includes out-year phased contracts: | 968.8
12 GeV Total Project Cost | 3632.6045 | 3188.6067 | 3282.6793 | [7 empty] | Contingency and MR % calculation includes contract vendor notifications.
Assigned ~ $1.25M Mgmt Reserve for Civil contracts.
Non-DOE | BCWS | BCWP | ACWP | Sv | Cv | SPI | CPI | BAC | EAC | IEAC | Cont/MR % | % Complete
1.09 Work for Others | 8912.6312 | 8855.9849 | 8845.3773 | -56.6463 | 10.6075 | 0.99364 | 1.0012 | 8912.6312 | 8912.5166 | 8901.9558 | 154.4% | 99.36%
1.10 Non-DOE | 624 | 624 | N/A | 0 |  | 1 |  | 624 | 0 |  |  | 100%
Note on I3: Kelly Krug: Cost Mgmt BAC (Fully Burden/Esc)
Note on J3: Kelly Krug: Costbook (Burd/Esc) Raw Data from imr in columns P-W.
Note on M4: Kelly Krug: BCWP/"BCWS @ completion"
Note on J13: Kelly Krug: Based on CR Log.
Note on L13: Kelly Krug: MR/ETCob
Note on J15: Kelly Krug: Based on CR Log.
Note on K19: Kelly Krug: IEAC calculated only on WBS level 2s that are currently active. Therefore, formula is is not in 1.8.
Note on J21: Kelly Krug: Based on CR Log.
Note on J23: Kelly Krug: Based on CR Log.
Note on B32: Kelly Krug: Monthly S, P, A are 0 until Pre-Ops.
Note on C32: Kelly Krug: Monthly S, P, A are 0 until Pre-Ops.
Note on D32: Kelly Krug: Monthly S, P, A are 0 until Pre-Ops.
Note on B36: Kelly Krug: Change column each month to read from CTD.
Note on C36: Kelly Krug: Change column each month to read from CTD.
Note on D36: Kelly Krug: Change column each month to read from CTD.
Note on B37: Kelly Krug: Change column each month to read from CTD.
Note on C37: Kelly Krug: Change column each month to read from CTD.
Note on D37: Kelly Krug: Change column each month to read from CTD.