## Slide 1: CEBAF Operations Overview
Eduard Pozdeyev,
Director of Accelerator Operations
2024 JLAAC Review

## Slide 2: Outline
Introduction
Status of Accelerator Operations
Sources of beam downtime and performance limitations
CEBAF Performance Plan
Accelerator Improvement Projects (AIPs) and R&D portfolio
Operations staffing
Accelerator Operations risks
Summary
This presentation answers charge questions 1 and 3

## Slide 3: CEBAF Accelerator
SRF, recirculating, 5.5 pass, 12 GeV Linac
Beam power up to 900 kW
Total recirculated beam current in the linac up to 450 uA
CEBAF can provide beam up to 4 Halls simultaneously
Beam can be extracted to a specific Hall at any selected pass
  e.g., Hall A can operate at pass 4, Hall B can operate at pass 5, and Hall C can operate at pass 3
1.1 GeV linac
C100 (new) CMs
C20 (old) CMs
1.1 GeV linac
C100 (new) CMs
C20 (old) CMs
Experimental Halls A,B, C
2.2-11 GeV after 1-5 passes
Experimental Hall D
12 GeV after 5.5 passes
Injector
5 magnetic
Arcs

## Slide 4: Alignment with Lab’s Mission and Long-Range Plan (LRP)
Operate CEBAF for Nuclear Physics for >30 week/yr. for >1800 users
Support upcoming 12 GeV experimental program (MOLLER, SoLID, K-Long)
Adapted from S. Henderson’s
all-hands presentation 07/2023
LRP Recommendation 1: Capitalize on the extraordinary opportunities for scientific discovery made possible by the substantial and sustained investments. Continue effective operation of national user facilities, including CEBAF at TJNAF

## Slide 5: Scope of Accelerator Operations
Operations of CEBAF Accelerator, Real Time Support and Repair (RSR)
  MCC (control room operator) group
  Software/EPICS controls group
  Labor and material required to operate and maintain CEBAF accelerator systems, e.g., RF, magnets, instrumentation. It can include some development.
    Scope and budget are planned by system owners yearly in collaboration with Operations.
  Does not include power and other utilities
  FY2024 Budget $18.8M, labor 121 FTE, material $2.24M
CEBAF Performance Plan
  CPP Reliability, critical spares, obsolescence. FY2024 Budget is $2.76M.
  CPP Energy Reach (cryomodule upgrade and refurbishment). Budget is in SRF-Ops.
AIPs
  $1.05M/year
  Budget presently is not in Accelerator Operations

## Slide 6: Program Requirements and Performance Limitations
Operational time (weeks/year) is determined by DOE. Goal is 33-34 weeks/year.
DOE metric for reliability is 80%
  Scheduled program includes 100% margin (1 experiment day mapped to 2 calendar days)
Beam energy:
  CEBAF is operated at 11.5 GeV (after 5.5 pass) in FY2024. 12 GeV requested in FY2025.
  Many experiments, including MOLLER, can trade energy for reduced RF fault rate
Beam power and intensity:
  CEBAF 12 GeV upgrade performance optimized for up to 1 MW, 450 uA recirculated current
  CEBAF is operated at <800 kW. Beam power of 1.1 MW requested in FY2025
  Some experiments do not require maximum energy allowing for program optimization
Accelerator performance limitations (presently):
  Accelerator systems ~850 kW Klystron performance below spec
  Operational Envelope 1.1 MW Determined by the dump cooling system
  Environmental Assessment: 2 MW

## Slide 7: FY24 and FY25 Operations
FY24 Run
34 weeks of beam operations, ~31 weeks physics
Three Halls: A (2-5), B (3-5), C (3-5)
E = 11.5 GeV (1047 MeV/linac), P = 900 kW
FY25 Run
33 weeks of beam operations, ~31 weeks physics
Four Halls: A (3-5) , B (1-5), C (3-5), D (5.5)
E = 12 GeV (1100 MeV/linac), P = 1.1 MW
  Increasing CEBAF energy reach will be critical

## Slide 8: CEBAF Beam Power For 5 Last Years
CEBAF typically operates at <800 kW
Power is lower in FY2024 run due to
  Hall A shutdown from Nov to Apr
  Hall C reduced power requirements
Runs above 800 kW (e.g., in 2022) were difficult due to frequent RF trips

## Slide 9: Status of CEBAF Beam Operations: Beam Availability
Average beam availability for this run (08/26/2023 – now) is 80%
DOE metric is 80%
Data shows average
beam availability over a week
ending on the shown date
CEBAF Gun Failure
80% - This Run Average
72% - Previous Run Average
Safety Interlock
Systems Failure

## Slide 10: Beam Availability and Reliability, This Run (08/26/2023 – now)

## Slide 11: Main Sources of Downtime
RF failures are consistently the largest contribution to downtime, >30%
  Klystron HV PS and control boards
  High power components (transformers, breakers, etc.)
  Cooling
Beam transport consistently is a high contribution, ~15%-25%
  Beam losses due to optics and orbit drifts
  Unscheduled tuning to reduce beam losses
Other noticeable contributions to downtime
  Magnet cooling channels clogging
  Power supply failures
  Facilities: LCW, HVAC
  Gun is a single point failure. Although mostly reliable, it’s failure causes significant downtime.

## Slide 12: Accelerator Performance Limitations
SRF
  C100 cavity gradient degradation.
    Contamination due to degrading Viton seals, field emission, and high radiation
    Possibly, dark current due to field emission
  Loss of cryomodules and cavities to vacuum leaks and other events.
  Cavity faults caused by microphonics and other effects.
RF
  RF station power lags performance requirement
Outdated and inadequate accelerator systems, including data acquisition and post-mortem capabilities, limit understanding of the machine and application of advanced techniques such as AI/ML
  LLRF, earlier, analog versions are still prevalent at CEBAF
  BPMs, slow DAQ (most), no buffering for postmortem processing
  BLMs, slow DAQ
  (No) Global timing system, no synchronization between different systems
See slide 25

## Slide 13: CEBAF Performance Plan (CPP)
Established in 2017 with goal of achieving 12 GeV in 5.5 passes with good reliability.
Reliability Project, manager: Randy Michaud
  Critical Spares
  Klystrons
  Obsolescence
  Optimal Weeks Hardware
Energy Reach Project, manager: Tony Reilly
  C75 program
  C100 refurbishment program
  Plasma processing
CPP funding vs FY. The total is $60.1M.

## Slide 14: CPP Reliability
Critical Spares, No scope in FY24.
Klystrons
  Supply chain crisis increased service cost by 60%. Supplier business has a new owner.
  We evaluate an alternative supplier to mitigate risk
  FY24 plan: 10 rebuilds and 10 new klystrons
Obsolescence
  SSG – 5 items @ $79K: ODH UPSs ordered for SAD24.
  DC – 4 items @ $515K : New DC PM coming up to speed on CPP plans.
  I&C – 3 items @ $360K: VME Crates awaiting PO, 15 units for SAD24
  RF – 5 items @ $666K : Work planning for Sep SSA install SAD24.
  ACE – 2 items @ $60K: UPS/Line Switches ordered.
Optimal Weeks, No scope in FY24.

## Slide 15: CPP Energy Reach
Scope
  C75 program
  C100 refurbishment program
  Plasma processing
Cryomodules refurbished and installed at CEBAF to date: C75 x 2, C100 x 4, C50 x 1, 7-cell P1 x 1
Four cryomodules in south linac were plasma processed in situ.
 | Cryomodules Installed | Cryomodules Removed
FY23 | C100, C100 | C100
FY24 | C100, C75, C75 | F100, C20, C20
FY25 | C100, C75 | C100, C20
FY26 | C100, C75 | C100, C20
FY27 | C100, C75 | C100, C20
FY28 | C100, C75 | C100, C20
FY29 | C100, C75 | C100, C20
FY30 | C100, C75 | C100, C20
Cryomodule Installation Plan
T. Reilly

## Slide 16: CEBAF Energy Reach Projection
now
- measured
- projected for FY25 run
T. Reilly
Jay adds: TN-24-001 has energy reach history 2016-2024

## Slide 17: Successful In-Situ Plasma Processing Of CEBAF CMs
Four cryomodules, 2L22 - 2L25 (all cavities), were plasma-processed in the tunnel during last SAD
Path Forward
  Process 3 to 4 C100 and C75 cryomodules during accelerator shutdowns.
  Extend plasma processing to C75 cavities.
T. Powers

## Slide 18: In-Situ Plasma Processing Increased Gradient by 2.7 MV/m
Field emission free operation was improved by 59.1 MeV (24%).
An average improvement of 2.7 MV/m.
5 cavities were field emission free after processing.
Average Increase
is 2.7 MV/m
Success of plasma processing supports more aggressive curve for CEBAF energy reach
T. Powers

## Slide 19: All-Metal Gate Valves
Contamination of CEBAF linac causes degradation of cavity performance, requires cryomodule refurbishment, plasma processing.
One of contamination sources was attributed to radiation damage of elastomer (Viton) seals around C100 and C75 CMs
  Viton seals can reach its lifetime in a single run
All-metal gate valves are a viable alternative
All-metal valves are used in SRF accelerators: X-FEL, LCLS-II, PIP-II (future)
Risk – production of metallic particulates
  Some gate valves cycle a dozen times a run, some not at all
We are considering installing all-metal gate valves in CEBAF next shutdown. Exact scope of installation is under discussion (3 to 7 CMs).
We solicit comments on viability of this approach from JLAAC

## Slide 20: Probing CEBAF Performance Limits
High intensity run in 10/2023 to identify CEBAF intensity limitations.
Performance is limited by available RF power. C100 CM klystrons are underperforming.
  Need at least 10 kW for 1.1 MW
  Klystrons specified at 13 kW max and 11 kW linear regime
Maximum achieved power
850 kW (395 uA)
Measured RF Klystron Power Distribution
Need 10 kW RF for 1.1 MW beam power.
Klystrons are specified at 13 kW max and 11 kW linear.
Beam power as function of time

## Slide 21: Optimization of QL of C100 Cryomodules
C100 cavities were designed with QL of 3e7 in anticipation of high operating field and low microphonics
Reality:
  Microphonics is higher than specified
  Operating field is lower than expected
Impact:
  C100 cavities trip due to insufficient RF power with high beam current and high microphonics
  Difficult to control narrow-bandwidth C100 cavities
Mitigation: QL of C100 cavities was reduced to optimal 1.5-1.7e7 during this SAD
Impact to be tested during this and next runs
Average Klystron power
available at cavities
QL before adjustment
QL after
adjustment
Required RF power as function of QL
100 MV/CM and 40 Hz detuning
Measured QL of C100 cavities before and after adjustment
Design QL=3e7
Adjustment goal
QL=1.5e7 – 1.7e7

## Slide 22: Improving Understanding of Beam Losses
CEBAF employs original 30-year-old analog BLM system to detect beam losses
  System adequately protects the machine but is not well suited for understanding or optimization of beam losses
  PMT voltage settings are likely too conservative
Near-term approach
  Procured 8 ion chambers with fast DAQs and installed them at the location of highest losses (see figure)
  Ion chambers are used to study beam losses and cross-calibrate existing BLMs
Long-term approach: Conduct a mini-workshop with subject matter experts to develop path forward with the upgrade of the BLM system
Frequency of MPS fast trips pulled by BLMs
60% of all trips are caused by four BLMs
Beam losses are responsible for ~27%
of all downtime.

## Slide 23: Injector Upgrade Completed
The injector upgrade reduces helicity correlated asymmetry for the Parity Quality program (MOLLER) and improves beam quality for high charge/bunch beam (K-Long).
Scope
  Increased gun voltage from 130 to 180 keV.
  Upgraded Wien filters.
  Solenoids with a larger aperture.
  New SRF Booster cryomodule with reduced deflection and coupling.
Injector is used successfully for this beam run.
Increased beam energy improved beam stability significantly.
Beam tests to quantify beam Parity Quality and fully evaluate the injector are on-going
180 kV photogun
booster
New injector and Booster CM
In the CEBAF tunnel
Beam in the injector

## Slide 24: Accelerator Improvement Projects (AIPs)
Challenges
  Cost-Of-Living funding does not allow acquisition of critical systems before FY30.
  Incremental production and installation spread over multiple years is costly and inefficient.
LLRF, BPMs, BLMs, and Timing together provide complementary, synchronized data.
Focused funding and construction of these systems will provide maximum benefit for CEBAF Operations.
 | Total cost | Past Years | FY22 | FY23 | FY24 | FY25 | FY26 | FY27 | FY28 | FY29
LLRF Digital Upgrades | 3,739 | 1,789 | 660 | 266 | 905 | 40 | 40 | 40 |  | 
Next Gen BPM Upgrade | 4,580 |  |  |  | 190 | 1,088 | 1,122 | 1,157 | 1,023 | 
Global Timing System | 1,480 |  |  |  |  |  |  |  | 210 | 1,270
Beam Loss Monitoring System | TBD |  |  |  |  |  |  |  |  | 
TOTAL ( = Funding) | 9799+ |  | 1,052 | 1,063 | 1,095 | 1,128 | 1,162 | 1,197 | 1,233 | 1,270
See next slide

## Slide 25: Benefits Of Advancing LLRF, BPM, BLM, and Timing System
LLRF Upgrade
  Provides advanced functionality for field control and diagnostics capabilities.
  Upgrade in progress. Installation to proceed until 2027.
Next Generation BPMs
  Addresses obsolescence. Provides new functionality: high bandwidth DAQ, buffering, interface to global timing system, suitable for capturing fast transients.
  Porotype construction in progress. Plan to install by 2028.
BLM System Upgrade
  Provides new functionality (faster DAQ, buffering, interface to timing system). Total loss monitors can extend area coverage.
Global Timing System
  Synchronizes instrumentation and allows correlating their response to beam events
These systems will benefit CEBAF the most if they are treated as parts of an integrated system, complementing each other.
Advanced functionality and global timing will provide insight into machine behavior and allow us to use modern tools such as ML/AI.
We ask JLAAC to comment on this concept and usefulness of advancing procurement of these systems.
LLRF v3
New gen. BPM prototype
Global timing system concept
N. Rider

## Slide 26: Next Generation CEBAF High Power RF
Klystron has been a reliable RF source at CEBAF for almost 30 years
Industry is changing
  Design experience is aging out.
  Solid State became much more prevalent in the last 10 years.
Cost of Klystrons surpassed cost of Solid-State Amplifiers.
It becomes difficult to find klystron vendors.
Aging CEBAF HP RF system is the main source of downtime: HV PS, Transformers, Klystron control electronics.
We need to think about next generation RF solution for CEBAF
Chart: 8 kW Klystron Tube Costs (does not include HV PS)
| 2000 | 2001 | 2002 | 2012 | 2018 | 2019 | 2020 | 2023
 | 18364 | 19084 | 19575 | 33516 | 50000 | 50000 | 51200 | 85000
$10/Watt

## Slide 27: Next Generation CEBAF High Power RF: Alternatives
Solid State Amplifiers (SSA)
Solid State Amplifiers are widely accepted technology that matured over last 20 years.
Viable alternative to tubes between 100 MHz – 2 GHz.
SSA efficiency > 40% for class A/B…more for class F.
SSA is technology of choice for LCLS-II, FRIB, PIP-II.
Status: requirements for CEBAF 8 kW SSA developed. Ready to contact vendors to get proposals for one CEBAF cryomodule. Project will be funded as AIP.
Magnetrons
Promise of high-efficiency, high power, and, possibly, lower cost.
Widely used technology for industrial applications but not accelerators.
R&D is conducted to demonstrate required phase and amplitude stability and address short lifetime.
  75 kW, 915 MHz AMTek magnetron funded by DOE Accelerator Stewardship award
  SBIR with Muons, Inc. for 1497 MHz magnetron
One zone at CEBAF (design)
We request and will appreciate comments from JLAAC
H. Wang

## Slide 28: Portfolio of R&D and SBIR-Funded Projects
Three AI/ML DOE funded projects (FOA-LAB-20-2261)
  Automate identification of unstable SRF cavities.
  C100 Cavity Fault Prediction.
  CEBAF cavity field emission management using neutron detectors and surrogate models (ML)
    Reduce field emission, increase lifetime of components
He flowmeter (SBIR, Hyperboloid LLC)
  Allows for fast and accurate measurement of cavity heat and Q0
1497 MHz Magnetron RF source (SBIR, Muon Inc)
  Demonstrate feasibility of magnetron as alternative, efficient RF source for CEBAF
Detection of anomalies in cavity field
First L-Band tube at
Richardson Electronics
Helium Mass
Flow Monitor​
C. Tennant
D. Turner
M. Spata

## Slide 29: Accelerator Operations Staffing
Personnel of operator group increased to 25, bringing Ops staffing to adequate level.
  7 new operators hired with a loss of 2 operators over the last year.
Operability deputy hired to focus on improving reliability and failure analysis
Competition for technical expertise with EIC and other projects is a concern
  Projects will compete for expert knowledge (e.g., SRF/RF/LLRF) required to support CEBAF

## Slide 30: CEBAF Operations Risks And Their Mitigation
Top risks
  Loss of experienced personnel supporting CEBAF Operations
  Aging linac systems and infrastructure affect CEBAF performance and increase rate of component failures to unacceptable level (e.g., loss of CMs, RF failures, CF failures)
  Changing market conditions and industry can cause obsolescence of accelerator components and/or increase cost of maintenance
  Energy reach fails to meet goals
  Funding after CPP ends is insufficient to maintain CEBAF performance and reliability
CPP and AIPs are examples of Risk Mitigation
  We will benefit from pulling AIPs ahead and combining them to take full advantage of provided capabilities
Formal risk registry exists for CPP. No formal risk registry for Operations exists yet. We plan to develop it.

## Slide 31: Summary
CEBAF usefully delivers beam to experimental halls in support of DOE NP mission.
Beam run is in progress. Average reliability for the current run is 80%.
We are actively addressing sources of downtime and performance limitations and managing future risks.
CEBAF Performance Plan and AIPs are used to improve performance of the machine, improve reliability, and address risks.
Looking forward to another successful year of delivering beam to NP users.

## Slide 32: Thank You!

## Slide 33: Current Priorities of CEBAF Operations
Deliver beam (up) to four halls for nuclear physics program safely and reliably, meeting program’s requirements
Execute CEBAF Performance Plan to extend CEBAF energy reach up to 12 GeV after 5.5 passes with margin.
Increase beam availability, reduce unscheduled downtime and frequency of trips
Improve hardware reliability through acquisition of critical components and spares. Address hardware obsolescence
Enhance CEBAF capabilities through AIPs, upgrades, and R&D
Prepare for upcoming experiments
Maintain strong operations team capable of meeting operational challenges

## Slide 34: Machine Studies And Operator Training
Machine Studies
Systematic beam studies to improve performance of the machine, understand performance limitations, and conduct R&D for future experiments are conducted bi-weekly (1 shift) and when opportunity presents itself
Beam studies are managed by CASA in coordination with Ops and other departments
Study plans are approved, prioritized, and scheduled at a weekly BTEAM meeting
Operator Training
Senior crew chiefs conduct hands-on operator training of junior operators on a live machine when either opportunity presents or during machine studies
These sessions provide unique opportunity to train young operators
Junior operators execute beam tuning procedures and operate hardware
Y. Roblin
D. Turner

## Slide 35: FY23 Scheduled Accelerator Downtime (SAD) Completed
New injector will reduce helicity correlated asymmetries for MOLLER.
Installed cryomodules and plasma processing increased the energy reach.
Upgrade of Personnel Safety System in South Linac. Certification once per year is considered.

## Slide 36: CEBAF Accelerator
1.1 GeV Linac
5 Magnetic Arcs
Halls A, B, C
Injector
Hall D