## Slide 1: LD2413 Development of µRWELL-PICOSEC Detectors FY24 Q2 meeting
Kondo Gnanvo
JLab Radiation Detectors & Imaging Group (RD & I Group)
Wenze Xi, Jack McKisson, Brian Kross, Akash Pandey
Seung Joon Lee (pro bono)
JLab - RD & I Group

## Slide 2
FY2413 µRWELL-PICOSEC – Q2 Progress & status
Single-channel µRWELL-PICOSEC protos
  Telescope stand completed and on its way to CERN 
  All parts of µRWELL-PICOSEC protos in hand 
  Housing for 4 × single-channel protos 
  MCP-PMT & 3 × GEM trackers for timing & tracking 
  4 × CIVIDEC fast amplifier  + Oscilloscope DAQ (CERN)
µRWELL-PICOSEC telescope
MCP-PMT stand
Housing for single channel proto
Motorized linear stage & manual vertical jack
GEM
Outer board PCB
µRWELL-PCB
Cathode-spacer
Cerenkov crystal
Alu housing
Different elements of the single-channel µRWELL-PICOSEC prototypes
CIVIDEC pre-amplifier
Ready for two-weeks test beam starting next week (04 / 10 / 2024) @ CERN

## Slide 3
100-pad reference MM-PICOSEC
Alu housing for 100-pad PICOSEC
10-channels custom preamplifier boards
64-channels SAMPIC Digitizer
100-pad outer PCB board
FY2413 µRWELL-PICOSEC – Q2 Progress & status
100-pads (10 cm × 10 cm) µRWELL-PICOSEC & MM-PICOSEC protos
Both 100-pad µRWELL-PICOSEC & MM-PICOSEC PCBs in hand 
Mechanical housing & Cerenkov crystal for 2 chambers 
Fabrication of two 100-pads outer PCB – ongoing
7 × 10-ch custom-made multi-channel pre-amplifiers for the readout 
Procurement of 64-ch Fast digitizer (SAMPIC) – ongoing
Preliminary test beam in April (04/10/2024) with borrowed electronics 
Final test in beam in end June 2024 with all 100 channels read out
  Use the same telescope stand (with minor accommodations) – ongoing

## Slide 4
FY2413 µRWELL-PICOSEC – Q2 Budget
Budget profile for the first six months of FY24
Projected spending profile for FY24
FY24 spending trend
In good shape with respect to the projected spending profile so far:
Fabrication of PICOSEC telescope & prototypes for April beam test
In-house multi-channel readout based on LMH6881 chip + CAEN picoTDC DAQ to be evaluated in beam in June 2024
Completion of test stand in EEL126 : Q3 & Q4
Variances anticipated:
  The spending trend exceed a little bit the projected profile
  Most procurement of FY24 already placed in the first two quarters
    No concerns about over spending for FY24
Final optimization 100-pad µRWELL-PICOSEC prototypes
  Studies of spatial resolution with capacitive-sharing
Investigating new materials for photocathodes is unlikely to be completed this year
Ongoing difficulties with setting up JLab team account at CERN is affecting several aspects of our LDRD program:
  Purchase of SRS crate for PICOSEC telescope GEM trackers
  Need but small expenses during test beam activities at CERN

## Slide 5
backup

## Slide 6
FY2413 µRWELL-PICOSEC – Q2 Progress & status
Pad readout geometry
Plain Cu electrode
Hash pattern Cu electrode
Contact
GND
Prototype | Shape | P (µm) | OD (µm) | ID (µm)
RD-T150-P80-D60 | round | 80 | 60 | 40
μRWELL#9 | round | 100 | 80 | 60
μRWELL#5 | round | 120 | 100 | 80
SQ-T150-P120-D100 | square | 120 | 100 | 80
Optimization of single-channel µRWELL-PICOSEC prototypes
New µRWELL hole geometries: 3 main approaches under investigation
  Minimize pitch to outer diameter ratio  reduce e-field effect
  Increase hole density  Increase gain capability
  Standard round holes vs. square holes  mimic MM mesh pattern
Plain solid pad vs. hash pattern pad
  Minimize detector capacitance  improve S/N