## Slide 1: PRad/X17 Collaboration Major Achievements for the past one year
Significantly increased the collaboration membership, (Patrick/Dipangkar)
more work needs to be done on this part.
fADC250 -based DAQ electronics is on site (in most part) and tested at JLab (talk by Chris)
H2 gas flow target is reassembled, updated, mostly tested, (talk by Xiangdong )
tests with He is planned in the next few weeks.
GEM detectors are in progress (with some delays but not yet critical) (talk by Nilanga)
An alternative DAQ readout system for GEM detectors had been proposed and successfully tested providing 25 kHz DAQ rate (talk by Nilanga)
HyCal PbWO4 crystal part has been repaired and tested. (talk by Aruni/Erik)
HyCal is ~95% ready for the experiment
A good progress on the HyCal chiller and interlock part (by Eugene)
need more work on this part

## Slide 2: PRad/X17 Collaboration Major Achievements for the past one year
Trigger algorithm is developed and being implemented (talk by Chao)
Good progress on Entire DAQ configuration part (Sergey/Chao)
nnn

## Slide 3: Collaboration Tasks for the Next 2 Years
  Construct and test all beamline elements by September 2025
  including scattering chamber with the window
  Reassemble and test the HyCal Transporter. From Sept. to Dec. 2025
  Complete HyCal work with cosmic rays and LMS,
  prepare for the beamline installation and cosmic ray tests in September 2025.
    test all signal and HV cables;
    test and repair all CAEN HV channels;
    test the new chiller;
    test the new interlock system.
  Complete gas flow target tests, ready for the beamline installation
  and tests in September 2025
  Remove the gas flow target from beamline, install X17 beamline by Dec. 2025
  Construct and test GEM detectors (4 detectors for 2 plains), ready for installation and cosmic ray tests in September 2025
    Integrate GEM new readout with DAQ;

## Slide 4: Collaboration Tasks for the Next 2 Years
  Construct and test veto scintillators, assemble in the target chamber and test. Ready to install in November 2025
  and then after the X17 experiment. In April 2026
  Install new fADC-based DAQ electronics before February 2025. Full tests from August 2025.
  Further develop full package of online control and monitoring programs. Dec. 2025
  To be ready for online draft data analysis during the experiments. January 2026
  Execute both X17 and PRad-II experiments, accumulate high quality and large statistics experimental data sets. Feb. July 2026
  Complete work on Radiative Corrections August 2026
  Start the data analysis work for both experiments