## Slide 1: Tentative Beam Time Schedule for 2026
February 02, 2026 X17 4.4 GeV
March 23, 2026 X17 2.2 GeV
April 23, 2026 end of X17 run 2.2 GeV
May 01, 2026 PRad-II 2.1 GeV
May 30, 2026 Prad-II 0.7 GeV
June 13, 2026 PRad-II 1.4 GeV
July 20, 2026 PRad-II 1.4 GeV the end

## Slide 2: Short Beamline Installation and Testing Plan (from September to December 2025)
Install all beamline elements in Hall B beam line Starts from September 2025
  Photon tagger radiators
  Hallo collimator before the tagger magnet
  Collimator box with three collimators (~6, 12, 24 mm) just after the Tagger magnet
  Beam pipe from collimator to target
  H2 gas flow target installed (see next bullet)
  Scattering chamber installed with its small window
  Beamline elements after HyCal
Install the H2 Gas Flow target with its all service parts (discussions)
Install new scintillators with their moving mechanism. Test the motion system
Install HyCal on its stand (table)
Install GEM detectors on front of HyCal
  connect all HyCal and GEM cables, HV and signal cables
  Install new Chiller
  Connect cables for new scintillators
Beam exit part on the vacuum window is closed with a temporary film
Engineering survey of ALL beamline elements and detectors (scintillatore, GEMs, HyCal)
Start testing the vacuum system
Test Gas Flow target FULLY (vacuum, gas, pressure, movements, etc.)
Start cosmic ray tests for GEMs, HyCal and new Scintillators

## Slide 3: Short Beamline Installation and Testing Plan (Cont.) (from September to December 2025)
Remove Gas Flow Target from the beamline, locate it next to that area Nov./Dec. 2025
Install X17 target (beam pipes, harp ladder, target films)
Remove temporary film on front of the Vacuum Window
Install new He-gas flow plastic pipe through GEMs and HyCal
Test the vacuum system
Continue cosmic ray tests for all detectors (scintillators, GEMs, HyCal)
Do these tests before January ~10, 2026

## Slide 4: PreRun Period (January 2026)
Remove the new plastic pipe from GEMs and HyCal Starts from January ~10, 2026
  Temporary thin film on the exit part of the vacuum Window
Remove GEM assembly off from HyCal, locate next to that area (taking cosmic ray data)
Install HyCal on the Transporter
Check all precision motions with on-line software
HyCal is still at chilled temperature
Check the vacuum system
Check the motion systems for all radiators, collimators, harps, etc.
Experimental setup is Ready for X17 experiment with a Photon beam End of January 2026

## Slide 5: Photon Beam Tuning for HyCal Gain Equalizing and Calibration
Photon Beam Tuning (~1 day):
  HyCal on the Transporter and off the beam line;
  Target cell off the beam line;
  Tagger radiator off, collimators off;
  Tagger magnet on.
establish a good electron beam (Ee = 4.4 GeV, Ie = 5 nA) on the tagger dump;
take electron harp scans 2C21A and 2C24A,
check the position, widths and peak to tails ratio;
study beam halo by setting the harp wire in the tail region and ramping beam current up to 100 nA;
lower beam current to 0.1 nA
insert radiator 10-5 r. l.;
check tagger counter scalars;
setup MOR logic for equalizing trigger T5-counter only;
etc.
Start HyCal gain equalizing process with photon beam

## Slide 6: HyCal Gain Equalizing
HyCal Gain Equalizing and Trigger Checkout (~2-3 shifts):
  HyCal temperature is already at T=17o and kept stable for few days;
  new collimator before tagger magnet is off;
  collimator after the Tagger is in, 6 mm (1/4”);
  X17 targe off the beam;
  HyCal is out of the beam;
  establish photon beam with Ie ~ 0.2 nA, Ee = 4.4 GeV;
  photon beam is off;
  set HyCal in “Bottom Right” PbWO4 position;
  trigger is from MOR T5, establish a good timing with HyCal readout (?);
  adjust the trigger delay if necessary;
  set the gain value: E=2 GeV to ADC=4000 channel;
  start the gain equalizing process: scan to each module’s center, show the anode ADC distribution on computer screen, by changing the HV set anode ADC=4000 channel (with ~ 5% precision), save the HV;
  repeat for all HyCal PbWO4 modules.
Run HyCal for 3-4 hours with the final HV, start HyCal gain equalizing process with photon beam

## Slide 7: HyCal Gain Calibration
HyCal Gain Calibration (2-3 shifts)
  HyCal is running with preset HV unchanged for ~ 3 hours after the “Gain Equalizing” process;
  the beam and the beam line are the same as in “Gain Equalizing”;
  MOR trigger: Three ranges of T- and E-counters: upper few, middle few and down few (for linearity check);
  DAQ without “sparsification”;
  start from the “Top Left” PbWO4 position with a continuous motion (~1 min/module) “illuminate” all modules, store the data with HyCal’s X,Y positions from EPICS;
  stop the HyCal motion by the end of each row, make new DAQ run with pedestals and LMS (? Needs discussion), store the files;
  run on-line calibration programs for calibration constants, store the data.
Configuration change to X17 running configuration with HyCal on the cart.

## Slide 8: Configuration Change to X17 Run Condition
Configuration change to X17 running configuration with HyCal on the cart.
  move HyCal back to running cart;
  install GEMs back on HyCal;
  install plastic pipe through GEMs and HyCal again;
  establish good vacuum;
  HyCal and GEM engineering survey to beam center (~2 shifts ?)

## Slide 9: Preparation and Run X17 Experiment
Preparation for the X17 Experiment
  tagger radiator off;
  upstream collimator off;
  downstream collimator (after Tagger magnet) in, 12 mm diameter (0.5”);
  set DAQ trigger: 3 clusters in HyCal with Eclust > 30-50 MeV AND Etotal > 0.7xEbeam (correct these numbers with new MC simulations to optimize the trigger);
  request electron beam Ee =4.4 GeV, Ie = 5 nA;
  insert the 1 m Tungsten target;
  take data and measure the trigger rate;
  insert upper collimator with 0.5” diameter, take date and DAQ rate;
  optimize the upper collimator diameter;
  gradually increase the beam intensity to reach the 25 kHz DAQ rate;
  take data;
  The sequence and duration of “empty target” runs needs to be discuss separately.
  What is the gain from “empty target” runs in X17 experiment and how much we need to
  take them?

## Slide 10: X17 Experiment: Change of Energy (if needed, maybe not a bud idea)
If decided, change to Ee = 2.2 GeV, and run as before.
  beam is off;
  all collimators are in, as before;
  target is off;
  request electron beam Ee =2.2 GeV, Ie = 5 nA;
  insert the 1 m Tungsten target in;
  set DAQ trigger: 3 clusters in HyCal with Eclust > 30 MeV AND Etotal > 0.7xEbeam (correct these numbers with new MC simulations to optimize the trigger);
  take data and measure the trigger rate;
  gradually increase beam intensity to reach the 25 kHz DAQ rate.
  take data with the same “empty target” sequesnce as before.

## Slide 11: Configuration Change to PRad-II Experiment (Ee is 2.1 GeV)
Preparation for PRad-II experiment.
  beam is off;
  remove X17 pipes with target harp;
  uninstall GEMs with plastic vacuum pipe from HyCal;
  have a saved HyCal HV values on disk;
  turn off HyCal HV;
  keep the Chiller running;
  remove the large tungsten “absorber/collimator”;
  insert the smaller “absorber/collimator”. Repair optical fibers:
  close the HyCal front door;
  set the same HV values on HyCal;
  reinstall GEMs on HyCal;
  reinstall the plastic vacuum pipe;
  change the FADC jumpers to x2 more sensitive position
Parallel to upper work install the H2 Gas Flow Target.
Establish good vacuum.

## Slide 12: Hydrogen Gas Flow Target Recommissioning with Beam
Target Commissioning (2 shifts)
  target cell off the beam line, no gas flow in the cell and chamber;
  beam collimators in “off” position;
  set threshold energy for the HyCal trigger to E ~ 0.5 Ee (needs to be optimized);
  request electron beam (E = 2.1 GeV, I = 1 nA);
  take harp scans 2C21A, 2C24A and 2H01, check position and widths, establish a good electron beam and fix the beam line parameters;
  record HyCal trigger rate with no cell and no gas flow take one short DAQ run (record HyCal and GEM information);
  electron beam off; insert the target cell in the beamline, still empty, ask for beam;
  target cell is empty (no gas flow into the cell and chamber);
  record HyCal trigger rate, take one short DAQ run (record all information);
  gas flow in the cell (Pcell = 6 torr, Pcham = 5 mtorr);
  record HyCal trigger rate, take one short DAQ run (record all information);
  move the cell on X-axis by +/- 3 mm with 0.2 mm steps and take HyCal rate;
  move the cell on Y-axis by +/-3 mm with 0.2 mm steps and take HyCal rate;
  change the cell angles and record the HyCal rate, get optimal cell position and direction;
  center the cell in the beam based on those measurements;
  no gas flow into the cell and chamber, record HyCal rate;
  gas flow into the cell (Pcell = 6 torr, Pcham = 5 mtorr);
  record HyCal trigger rate, take one short DAQ run (record all information);

## Slide 13: H2 Gas Flow Target Recommissioning with Beam (Cont.)
Selecting optimal “Collimator” combination.
  beam energy is Ee = 2.1 GeV;
  set HyCal trigger: Etotal > 0.5xEbeam;
  insert the downstream collimator (after tagger): 12 mm (0.5”) (check from PRad run);
  sequentially insert different collimators in upstream collimator and select the optimum
  trigger rate condition.

## Slide 14: PRad-II Data Taking
Data taking with Ee = 0.7 GeV (5 days, check this number)
  beam intensity: Ie ~ 10 nA;
  collimator in (as defined in 11 a, b);
  set HyCal trigger: Etotal > 0.5xEbeam
  DAQ is ready, all slow control readout is ready;
  target cell in with maximum density (2.x1017 H/cm3);
  take data for 2 days, record all information on disk and on tape;
  no gas in the cell, take data for 0.5 day (empty target run);
  gas in the cell, run for 2 days (same as in (e));
  no gas in the cell, take data for 0.5 day (empty target run);
Data taking with Ee = 2.1 GeV (4 days, check this number)
  intensity: : Ie ~ 10 nA;
  collimator in (with the diameter defined in 11 a and b;
  set HyCal trigger: Etotal > 0.5xEbeam,
  DAQ is ready, all slow control readout is ready;
  target cell in with maximum density (~2.x1017 H/cm3);
  take data for ~2 days, record all information on disk and on tape;
  no gas in the cell, take data for 0.5 day (empty target run);
  gas in the cell, run for ~1.0 day (same as in (e);
  no gas in the cell, take data for 0.5 day (empty target run).

## Slide 15: PRad-II Data Taking
Data taking with Ee = 1.4 GeV (4.5 days, check this number)
  intensity: : Ie ~ 10 nA;
  collimator in (with the diameter defined in 11 a and b;
  set HyCal trigger: Etotal > 0.5xEbeam
  DAQ is ready, all slow control readout is ready;
  target cell in with maximum density (2.x1017 H/cm3);
  take data for 2 days, record all information on disk and on tape;
  no gas in the cell, take data for 0.5 day (empty target run);
  gas in the cell, run for 1.0 day (same as in (e);
  no gas in the cell, take data for 0.5 day (empty target run).