## Slide 1: FM&L SAM Projects
Facilities, Management & Logistics
FY25-26 SAM Project List
Sep 2025

## Slide 2: FML Construction Projects
Road Repairs: RFP amended to add additional areas of repair; due mid-Aug. Construction is tentatively scheduled between Sep 8 – Oct 3, project scheduled to complete Q1 FY26
LERF Duct Repair: Repair of underground HVAC ducting. Work will start in Sep; completion date dependent on evaluation of failure and lead time on materials needed to repair or replace
Cooling Tower Drives Replacement: Scope includes replacement of 10 existing fan drivetrains in cooling tower cells (3 at CUP, 5 at N/S Access, and 1 at CTF and CHL). Work scheduled for completion by Oct
Hall C Electrical Modifications: Phase 1 – Replace feeder cable, conduit, and pull box from top of Hall C down to switchboard 96-SWBD-ESC. Contract award scheduled for Sep. Targeting Nov timeframe for work
Building 36 HVAC for Magnet Refurbishment Bay: New air conditioning system and ducting to provide space cooling. Contract award scheduled for Sep with an estimated completion Q3 FY26
2

## Slide 3: FML Construction Projects
N & S Access Cooling: Scope includes ductwork modifications to improve circulation of existing cooling. Contract awarded, material submittals approved. Work to start and finish in Sep
LERF and Test Lab Guardrails: LERF guardrail installation scheduled for Sep. Test Lab guardrails completion estimated for Q1 FY26
87 HVAC Controls Replacement: Replacement of existing “end of life” BAS controls with new JCI controls. Work starting in Sep and scheduled to finish in Q1 FY26
Site Electrical Metering: Install remaining 24 meters on the accelerator site. (Service Buildings and End Stations) Work scheduled to be completed during this SAM. Close coordination with Operations, subcontractor and FM&L will be required
3

## Slide 4: CEBAF Water Intrusion Repairs and Modifications
Includes crack repair, replacement of water collection and pumping stations and electrical circuit installation
Leak Repair
  RFP for leak repairs issued. Work to be executed during this SAM
Electrical
  Upgrade electrical with permanent wiring (remove extension cords) in support of 17 water collection pump stations. Work to be executed by BOA subcontractor during this SAM
Mechanical
  Replace 10 water collection and pumping stations with permanent engineered solutions during this SAM
  Remaining 7 stations will be refurbished until they can be replaced during the next SAM in FY26
4

## Slide 5: Inspection and PMs
Electrical Inspections:
  FY25 SAM work focused in Halls A/B/C using both JSA staff and contractors
  8 SWBDs (3 Hall A, 3 Hall B, 2 Hall C)
  ~120 Panel Boards (less than 400 A) throughout Halls A/B/C
PMs
  Electrical:
    5 yr SWBD cleaning in Halls A/B/C IAW ESH 6230 T5
    CEBAF and LERF: Perform annual 1 yr external inspections
  Mechanical:
    Multiple PMs throughout the accelerator and support facilities. Masterlist and ATLis approval managed with Accelerator Operations