## Slide 1: HYPER-NUCLEAR DESIGN STATUS Jamie Shiflett Hall C Lead Engineer shiflett@jlab.org (757) 269-6944 Feb 12, 2026
HYPER-NUCLEAR

## Slide 2: HALL C
Nansemond Pre Cast Concrete – Radiation Shielding
  P.O. 25-D1718-0 - Deliverables late Sept-Oct 2026
    62 WALL BLOCKS
    18 MEDIUM BLOCKS
Cabling with Bill Henry
  Cable routing
PCS
  Metrology Survey Complete and data compared with drawings.
Power Supply Unit Procurement
  Qty 3 Purchase Requisition(441768) on hold
  Qty 1 Still needs PR submittal.
  DELIVER HKS PSU TO TEST LAB FOR MOLLER TESTING
LCW
  Preliminary Schematic Produced
  Establish preliminary Bill of Materials
SCHEDULES
FUTURE TASKS
HYPER-NUCLEAR

## Slide 3
HYPER NUCLEAR – LAYOUT(TOP VIEW)
BEAM LINE
ENGE
HES
High Energy Spectrometer
HKS
High resolution Kaon Spectrometer
PCS

## Slide 4
HYPER NUCLEAR – LAYOUT (TOP VIEW)
BEAM LINE
ENGE
HES
HKS
SHMS
HMS

## Slide 5
CAD
150
110
125
CDet
NPS
BigBITE
LOCATION

## Slide 6
HYPER NUCLEAR – CABLE ROUTING
CABLE TRAY LAYOUT FROM SUPER HMS(YELLOW)

## Slide 7
HYPER NUCLEAR – CABLE ROUTING
CABLE TRAY LAYOUT FROM SUPER HMS(YELLOW)
HKS
HES

## Slide 8
PCS MAGNETS
SURVEY MONUMENTS INSTALLED
MOUNTING INTERFACE CONFIRMED

## Slide 9
HYPER NUCLEAR – POWER SUPPLY UNITS PROCUREMENT
Magnet | Current (with overhead for MOL) (A) | Voltage (V) | Magnet DC Power kW | Magnet LCW (L/min) | Inductance (H) | Magnet LCW pressure (MPa) | Magnet resistance (not including leads) | PSU – New or existing | PSU Water Flow (L/min) 0.6LPM/kW | PSU DC Power (kW) | Regulation (PPM)
HES E Dipole | 1,000 | 220 | 220 | 95 | 0.820 | 0.5 | 0.181/pole | Existing HES PSU | 45 | 220 | 
HES E Q1 | 800 | 110 | 88 | 41 | 0.054 | 0.5 | 0.111 | Existing BB | 28 | 90 | 
HES E Q2 | 800 | 110 | 88 | 41.4 | 0.056 | 0.5 | 0.109 | Left Q1 Hall A | 48 | 90 | 
HKS Dipole | 1,140 | 165 | 188 | 135.1 | 1.95 | 0.67 | 0.145 | Existing HKS PSU | 45 | 190 | 
HKS Q1 | 875 | 160 | 140 | 49.6 | No data Use HKS Q2 | 0.36 | 0.181 | Existing Compton PSU | 43 | 140 | 
PCS (k) | 1,700 | 106 | 180 | 100 | 2.0 (from vendor report) | 0.16 | 0.06 | Existing SBB | 50 | 186 | 10
PCS (k) corr | 1,000 | 97 | 97 | 100 | 2.0 (from vendor report) | 0.16 | 0.01 | Existing NPS PSU | 32 | 97 | 10
Corrector magnet | 150A |  |  | Air cooled |  | NA |  | Existing (NPS) | NA |  | 

## Slide 10
HYPER NUCLEAR – POWER SUPPLY UNITS PROCUREMENT
Magnet | Current (with overhead for MOL) (A) | Voltage (V) | Magnet DC Power kW | Magnet LCW (L/min) | Inductance (H) | Magnet LCW pressure (MPa) | Magnet resistance (not including leads) | PSU – New or existing | PSU Water Flow (L/min) 0.6LPM/kW | PSU DC Power (kW) | Regulation (PPM)
PCS (e’) | 1,800 | 130 | 180 | 100 | 2.0 (from vendor report) | 100 | 0.06 | PR 441768 ON HOLD | 112 | 186 | 10
PCS(e’) corr | 1,100 | 120 | 97 | 100 | 2.0 (from vendor report) | 100 | 0.1 | PR 441768 ON HOLD | 58 | 97 | 10
HKS Q2 | 500 | 60 | 28 | 17.3 | 0.36 | 0.38 | 0.119 | PR 441768 ON HOLD | 15 | 25 | 10
ENGE | 331 | 50 | 100 | 50 | 1.59 | 1.0 |  | IN PROCESS | 11 | 17 | 10
Sub Totals (both sheets) |  |  | 1,406 | 829.4 |  |  |  |  | 487 128 GPM | 1,338 | 
WAITING FOR BUDGET OFFICE APPROVAL(All other signatures obtained)*

## Slide 11
HYPER NUCLEAR – PSU/LCW LOCATION
PSU LOCATION
(BLUE)
LCW FROM HMS SIDE OF HALL

## Slide 12
PRELIMINARY LCW SCHEMATIC

## Slide 13
HYPER NUCLEAR – SCHEDULE

## Slide 14
HYPER NUCLEAR – SCHEDULE

## Slide 15
HYPER NUCLEAR – SCHEDULE

## Slide 16
HYPER NUCLEAR – SCHEDULE

## Slide 17
FUTURE TASKS
TIMELINE TO CHECKOUT EXISTING POWER SUPPLIES
TESTING OF PCS MAGNETS
VACUUM BEAMLINE
ASSEMBLY PROCEDURES AND PTW GENERATION
MANPOWER EXPECTATIONS
  DESIGNER on loan from Hall A