## Slide 1: Hypernuclear Target Design, Schedule and Cost
David Meekins
12 February 2026

## Slide 2: Design Status
Currently in very early stages of the design
  Coarsely adapting the PREX/CREX target system to HKS needs
  This includes the cryogenic fluid transfer subsystem
Only solid targets no gas cells
Enge location is challenging to chamber design and adds spacial constraints.
Preliminary thermal analyses show concept at least workable for 3 spectrometer operation for all solid targets at the proposed beam currents. We still need to fine tune this analysis
  Students, JLAB staff.
Alignment of the target will be challenging.
Considering load/lock system to accommodate need for α source

## Slide 3: Hall C HKS Layout
Target

## Slide 4: Cryogenic Distribution System
Use standard 1.5” transfer lines with integrated control valves.
  We have two such lines however they are too short and will have to lengthened.
The 1.5” lines will feed a transfer can to adapt to 0.5” transfer lines.
  PREX T-Lines cannot be reused and new ones will need to be fabricated
  The transfer can
Currently we are optimizing location for the transfer can.
  We can then design (length only) and start fabrication of them.
Low power requirements
  Compatible with MOLLER but we will still need to keep T-lines cold ~200W at 20K.

## Slide 5: Chamber Location Side View
Cryo sup/return
HKS target
New decking attached to SHMS. Transfer can located on deck.
Nominal Pivot
Transfer
Can

## Slide 6: Chamber Location Top View
HKS Target
~260 in downstream from pivot

## Slide 7: Scattering Chamber Requirements
Vacuum connections to three spectrometers
  There will need to be some flexibility in the system for alignment purposes at least.
Target will hang vertically into the beam line
Alpha source swapping will require the chamber to be opened during the run
  Ca, LiH, and Li targets will need to be protected from exposure to oxygen.
  One possible solution is to develop a load/lock
Load/lock system presents some design challenges
  Added length to motion system
  Access ports well above beam line
  Less rigid system so alignment might be sloppy

## Slide 8: HKS Target Concept
Scattering Chamber
(norm beam height)
Motion system
With possible load/lock
Scattering Chamber post
Beam
HKS 14 deg
HES (10 deg)
Enge
45 deg

## Slide 9: Motion System
Adapt principles of the PREX target to HKS.
Cryogenic system
  Component design similar to PREX
Length of travel must be determined
  This can accommodate all solid tgts
  Extra length for load lock
Adding “x”, “z”, “θ” motion
  “y” motion is normal vertical target motion
  This will add to cost and add complexity to design
We can use much of the existing target control system
  Epics based
New controls would be needed.
  Software -> EPICS
  Control cables would be needed. Might be possible to extend current cryotarget control cables

## Slide 10: Solid Target Ladder
11+ solid target positions
  Ca, Li and LiH should not be exposed to air for periods longer than few minutes.
  Possible need for H2 target
H2O target cannot run when target is cold
Need details of alpha source to complete the ladder design.
There is effort from target group to develop LiH as target material
  Needed for polarized target run as well.
LiH can release H atoms if temperature is too high. This “release” temp is below melting point.
  LiH must handle raster off operation
  LiH production may be inconsistent

## Slide 11
For ENGE
Figure from Sho
• 30-deg tilt
• 100 mg/cm2
• Calibration target (α source)
• Same diameter as 40,48Ca
• α target is unmounted during beamtime
• α target is next to carbon hole target (to be surer beam pos.)
• Other requirements
• ENGE vacuum is kept even when the scattering chamber is open
/9
T. Gogami (Kyoto Univ.), HKS Target Meeting, Jan 27, 2026

## Slide 12: Concept Solid Target Ladder
Other Solid Targets
Downstream Face
Ca40 and Ca48 Targets
2 mm integrated hole
Calcium target mount is recessed for cost saving.
Without recess, $120K more in Ca48

## Slide 13: Concept Solid Target Ladder
All components (ex targets) are aluminum 7075
Nuclear grade antiseize used for better thermal cond and to prevent seizing
All 9 targets can be accommodated with full acceptance for all three spectrometers
Clamp
Clamp ring
Target material
Mount

## Slide 14
Thermal Model for Lead-208 Assy.
Beam current 25 microA
Raster 2x2
6W of beam heat
Power density is
Walls held at 10K
Material models
  MPDB for lead
  MPDB and Weisend for Aluminum 7075
Max temp 479K
  Lead melts at ~600K
  FCC below 600K
Held at 10K

## Slide 15: Ladder Summary
Design of ladder is critical to moving the design process forward for the entire target.
Rotation of the solid targets 30 deg from beam normal will present some challenges
  Targets will need to be “wider”
  Increase the cost for Ca48
Somehow, we will have to optimize the rotation with cost and function.

## Slide 16: Cost Estimate Non-labor
Non-labor costs:
  Target materials (detailed on next slide)
    $200K
  Motion system $50K
    Frame $20K
    Bellows $10K
    Flanges/Fittings $10K
    Drive/Misc $10K
  Load lock $25K
  T-lines $20K + $15K
  Transfer Can
    Reuse PREX can for solid targets only
  Chamber/Stand $50K
  Total: ~$400K to $450
  Ca48 Cost will rise with larger targets. Have not priced in 2026

## Slide 17: Solid target costs
Target | Z | A | Thick (mg/cm^2) | Density (g/cc) | Req Thickness (cm) | Required Mass (g) | Cost | Imax (microA)
LiH |  |  | 0.45 | 0.93 | 0.484 | 1.647 | $ ??? | 2
Lithium-6 | 3 | 6 | 0.1 | 0.458 | 0.218 | 0.366 | $ 5,000.00 | 50
Beryllium | 4 | 9 | 0.1 | 1.848 | 0.054 | 0.366 | $ 5,000.00 | 50
Calcium-40 | 20 | 40 | 0.15 | 1.55 | 0.097 | 0.230 | $ 10,000.00 | 50
Calcium-48 | 20 | 48 | 0.15 | 1.86 | 0.081 | 0.230 | $ 100,000 | 50
Carbon-12 | 6 | 12 | 0.15 | 1.8 | 0.083 | 0.549 | $ 500.00 | 50
B-11 (B4C) | 5 | 11 | 0.15 | 2.52 | 0.060 | 0.549 | $ 7,000.00 | 50
Aluminum | 13 | 27 | 0.15 | 2.699 | 0.056 | 0.549 | $ 500.00 | 50
Lead-208 | 82 | 208 | 0.15 | 11.4 | 0.013 | 0.549 | $ 25,000.00 | 25
Spare Lead |  |  |  |  |  |  |  | 
Spare LiH |  |  |  |  |  |  |  | 
CH2? |  |  |  |  |  |  |  | 
Without adjustments to Ca targets, cost would go up at least $120K.

## Slide 18: Labor Resources/Time Required to Fabricate
Design solid targets only
  Design Authority 480 hours
    Load lock and alignment + 80
  Designer 320 hours
    Load lock and alignment + 100
Fabrication
  6 months of calendar time at least for target group
    Need welder, fitter, electrical, DA …
    Machine shop work (build to print components)
    Ca48 can take up to 12 months to procure if approved by DOE. This process has started recently.