## Slide 1: ERR Task List & Run Plan
Elena Long
b1/Azz Tensor Collaboration Meeting
Oct. 13th, 2025

## Slide 2: ERR Task List
  3 Main Topics:
  Target Tasks
  Beamline Tasks
  Documentation Tasks
  + any additional tasks recommended from this morning’s talks

## Slide 3: Target Tasks

## Slide 4: Target Tasks ◦ Maximize ND3 vector polarization
  The JLab Target Group is building a new test lab facility to irradiate ND3
    Irradiation optimization studies with both dose & irrad. Temperature
  Cryostat being built
  Beamline needs shielding for 10uA @ 8 MeV operation
  Aiming for irradiation operations in Spring ‘26
In Progress
10/13
10/14
10/13
10/14
Irradiation
Target
Material

## Slide 5: Target Tasks ◦ Demonstrate Tensor Enhancement on ND3
  Initial studies have been done on warm irradiated ND3
    Compared w/ d-butanol, ssRF is sharper & lasts significantly longer
    Low vector pol. due to 84K irrad
  Cold (1-4K) irradiated ND3 needed
In Progress
10/13
Preliminary
10/13

## Slide 6: Target Tasks ◦ Demonstrate Alost = 2 Agained w/ ssRF
  UVA published results
    D. Keller, EPJ A 53, 155 (2017)
    J. Clements, D. Keller, NIM A 1050, 168177 (2023)
  UNH results in agreement
Complete
Preliminary
Mirror

## Slide 7: Target Tasks ◦ Demonstrate full polarization cycles (P & Q)
  Goal is to create the following plot w/ data:
    Currently working on optimizing & automating ssRF application/measurement cycles + AFP
In Progress
10/13
10/13
10/13
10/13
UNH
UVA
10/14
10/14

## Slide 8: Target Tasks ◦ Design & Optimization of AFP and ssRF
In Progress
  Goal is to create the following plot w/ data:
    Currently working on optimizing & automating ssRF application/measurement cycles + AFP
      Hardware + Software
10/13
10/13
10/13
10/13
UNH
UVA
10/14
10/14

## Slide 9: Target Tasks ◦ Revisit Triumf’s Tensor Target Results
Near Complete
Before HB
After HB
NMR
  No uncertainty listed for
  Scattering data uncertainty is large
    No contradiction within uncertainty between either or

## Slide 10: Target Tasks ◦ Ensure NMR/ssRF coil uniformity
  Want to avoid line-shape issues encountered in Hall B RGC data
  b1/Azz will use NMR coils inside target cups, embedded in material
  Additional work:
In Progress
    3D printing coil forms to improve uniformity
J.I.Kelz, et al, J. Mag. Res. 305, 89 (2019)
Variable pitch increases homogeneity
  J.Mag.Res. 50, 281 (1982)
3D printing coil forms
J. Mag. Res. 305, 89 (2019)

## Slide 11: Target Tasks ◦ Ensure NMR/ssRF coil uniformity
  Want to avoid line-shape issues encountered in Hall B RGC data
  b1/Azz will use NMR coils inside target cups, embedded in material
  Additional work:
In Progress
    3D printing coil forms to improve uniformity
    Measuring coil uniformity w/ ball shift probe
Linear Actuator
VNA
Conductive
Sphere
Coil to Test
Flatness Uniformity
L.C. Maier, J.C. Slater, J.Appl.Phys. 23, 68 (1952)
  J.I. Kelz, et al, J. Mag. Res. 305, 89 (2019)

## Slide 12: Target Tasks ◦ Confirm annealing/material change estimates w/ Hall B RGC data
  Analysis of Hall B RGC data in progress
  Target CLAS Note expected in the near future
Near Complete
10/14
10/13
10/14
10/14

## Slide 13: Target Tasks ◦ Final Design of Target Ladder & Coils
In Progress
  Will use target cups similar to g2p
  ssRF/AFP coil design and optimization in progress
    Currently testing in-line and Helmholtz-like configurations
J. Pierce, et al, NIM A 738, 54 (2014)
Helmholtz-like
In-Line

## Slide 14: Beamline Tasks

## Slide 15: Beamline Tasks: ◦ Build Charge Monitoring Equipment
  Need to keep charge uncertainty below the 10-4 level
  Faraday cup being built & studied for this purpose
    Recommissioned W-Cu calorimeter from Hall A
In Progress
10/14
10/13

## Slide 16: Beamline Tasks: ◦ Commissioning of Slow Raster
  Slow raster of electron beam required for DNP target
Hall A slow raster for g2p
P. Zhu, NIM A 808, 1 (2016)
10/13

## Slide 17: Beamline Tasks: ◦ List Detector & Trigger Configuration
In Progress
  Draft run plans have been created for both Azz and b1
10/13
10/13
10/13
10/13

## Slide 18: Beamline Tasks: ◦ Confirm Beam Pol. & Measurement
In Progress
  b1/Azz need
  Will integrate the helicity states of the pol. e-beam
  Also potential for future datamining to extract beam-target double-spin vector & tensor asymmetries
b1/Azz
10/14

## Slide 19: Documentation Tasks

## Slide 20: Documentation Tasks
  Workforce for running
  Write EH&S Documents
  Complete ERR documentation
Near Complete
In Progress
Not Started
10/13

## Slide 21: Run Plan

## Slide 22: Overhead Assumptions (Real Time)
Beam Assumptions: Beam Current: 85 nA Beam Efficiency: 0.5 (Scaled to 1)
Target Configuration Assumptions: Target Cup Radius: 1.5 cm Target Cup Configuration: 2 cups | || |/ \ Microwaves |ND3 Prod. Mat. |ND3 Prod. Mat. |C Optics |EMP Empty Cell |___
Target Annealing/Material Assumptions: Dose between anneals: 5.25e+15 e/cm^2 Time Between Anneals for 2 Cups: 3 days, 5:42:46 Time required for Anneal: 1:00:00 Time required for Cup Change: 0:10:00 Time Between Cup Changes: 1 day, 14:51:23 Time required for target material change: 4:00:00 Dose between target material changes: 5.00e+16 e/cm^2 Time between target material changes for 2 Cups: 30 days, 20:07:20
Target Polarization, TE, & PF/Dilution Run Assumptions: Time constant for vector pol. spin-up: 0:50:00 # of vector pol. time constants before beam: 3.91 Time required for vector pol. spin-ups: 3:15:30 Time between each vector pol. spin-up: 2 days, 0:00:00 Time required for target TE measurements for all 2 cups: 3:00:00 Time between TEs: 15 days, 10:03:40 (2 b/w Each Material Change) Time required for packing fraction/dilution runs: 3:00:00 # of packing fraction/dilution runs per kinematic setting: 5 Time to Tensor Enhance: 0:00:30 Time to Tensor Unpol: 0:00:10 Time Between Tensor Pol/Unpol Cycles: 0:30:00
Beamline & Hall Configuration Assumptions: Time required for BCM calibration: 2:00:00 Beam time between BCM calibrations: 7 days, 12:00:00 Time required for each Optics run: 4:00:00 Beam time between Optics runs: 20 days, 0:00:00 Time required for each Linac change: 8:00:00 Time required for each Spectrometer Momentum/angle change: 2:00:00
Based on data from P.M. McKee, NIM A 526, 60 (2004)
Based on Hall B RGC Spin-Ups
Based on UVA & UNH data

## Slide 23: Dose Between Anneals & Mat. Changes
  Analyzed data from P.M. McKee, NIM A 526, 60 (2004)
Negative
Subset # | 
1 | 3.265
3 | 6.02
5 | 4.548
7 | 4.188
9 | 4.2964
11 | 4.139
12 | 3.5597
13 | 3.998
15 | 2.3091
Subset # | 
1 | 3.265
3 | 6.02
5 | 4.548
7 | 4.188
9 | 4.2964
11 | 4.139
12 | 3.5597
13 | 3.998
15 | 2.3091
Positive
Subset # | 
2 | 5.35
4 | 5.86
6 | 6.52
8 | 6.967
10 | 3.5
12 | 3.641
14 | 3.9454
Subset # | 
2 | 5.35
4 | 5.86
6 | 6.52
8 | 6.967
10 | 3.5
12 | 3.641
14 | 3.9454
Negative
Positive

## Slide 24: Hall B RGC Spin-Up
  ~ 4 hours to
  AFP will be used between spin-flips to significantly reduce flip time
10/13

## Slide 25: Rapid Tensor Flips: 4 State Measurement
  Rapid tensor enhancement/suppression while maintaining large vector polarization
    Highly suppresses drift effects on systematics
    1 cycle/hour instead of 1 cycle/day
    improved by
D. Keller
E. Long, EPJ A (in review)
10/14

## Slide 26: b1/Azz Kinematics Running
Draft run plan from smallest beam/detector energies to highest
Azz
b1

## Slide 28: Thank you!

## Slide 29
From P. Rossi’s Talk

## Slide 31: Azz Kinematics & Overhead

## Slide 32: b1 Kinematics & Overhead
A
B
C
A+B+C

## Slide 33: Target Tasks ◦ Demonstrate Alost = 2 Agained w/ ssRF
  UVA published results
    D. Keller, EPJ A 53, 155 (2017)
    J. Clements, D. Keller, NIM A 1050, 168177 (2023)
  UNH results in agreement
Complete
Preliminary